## ITMS CTD PLAN(Consolidated)
WBS | Level | Phase | Activity Name | Primary Responsibility | Task Name | % Planned | % Complete | Status | Remarks | Planned Start Date | Planned End Date | Duration | Predecessors | Actual End Date | Actual Start Date | Assigned To | Comments | Start | Finish
1 | 1 |  |  |  | ITMS CTD & RAID (Nexus) — Combined Program Schedule |  | 67.11% |  |  | 2026-05-21 | 2027-05-14 | 358d | [5 empty] | 2026-05-21 | 2027-05-14
1.1 | 2 |  |  |  | Phase 1 — Foundation (through Jul 2026) |  | 84.62% |  |  | 2026-05-21 | 2026-07-31 | 71d | [5 empty] | 2026-05-21 | 2026-07-31
1.1.1 | 3 |  |  |  | Development Team |  | 39.5% |  |  | 2026-05-21 | 2026-07-30 | 70d | [5 empty] | 2026-05-21 | 2026-07-30
1.1.1.1 | 4 | Foundation | ITMS — Development | Sanjay Deman | GST Service shifting Migration SQL Server to Oracle | 100% | 50% | In Progress | EwayBill GSTR3B, GSTR1,COMP01, Registration | 2026-05-21 | 2026-06-05 | 15d |  |  |  | Sanjay Deman |  | 2026-05-21 | 2026-06-05
1.1.1.2 | 4 | Foundation | ITMS — Development | Development Team | Convert Data migration flow and Jobs in Oracle | 100% | 50% | In Progress |  | 2026-06-02 | 2026-06-17 | 15d | 1.1.1.1FS |  |  | Development Team |  | 2026-06-02 | 2026-06-17
1.1.1.3 | 4 | Foundation | ITMS — Development | Development Team | HIT Rate MIS Report | 100% | 100% | Completed | New Mis for HIT Rate | 2026-06-23 | 2026-06-29 | 6d | 1.1.1.2FS | 2026-06-29 | 2026-06-23 | Development Team |  | 2026-06-23 | 2026-06-29
1.1.1.4 | 4 | Foundation | ITMS — Development | Development Team | Asmt-10 Issues | 100% | 100% | Completed | ADD functionality for VIew Details of PARAM7,8,9,10 Add Others Option to add data in ASMT10 | 2026-06-25 | 2026-07-01 | 6d | 1.1.1.3FS | 2026-07-01 | 2026-06-25 | Development Team |  | 2026-06-25 | 2026-07-01
1.1.1.5 | 4 | Foundation | ITMS — Development | DCIT | Registration mobile Email id Update | 100% | 100% | Completed | module for mobile Email id Update by proper officer | 2026-06-26 | 2026-06-29 | 3d | 1.1.1.4FS | 2026-06-29 | 2026-06-26 | DCIT |  | 2026-06-26 | 2026-06-29
1.1.1.6 | 4 | Foundation | ITMS — Development | Audit Desk Review | Audit Desk Review Module | 100% | 90% | In UAT | 1. Automated Selection of Cases | 2026-07-17 | 2026-07-20 | 3d | 1.1.1.5FS |  |  | Audit Desk Review |  | 2026-07-17 | 2026-07-20
1.1.1.6.1 | 5 | Foundation | ITMS — Development | Development Team | Allocation of Cases | 100% | 0% | Not Started |  | 2026-07-17 | 2026-07-17 | 1d |  |  |  | Development Team |  | 2026-07-17 | 2026-07-17
1.1.1.6.2 | 5 | Foundation | ITMS — Development | Development Team | Desk Review + Ratio / Trend Analysis | 100% | 90% | In UAT |  | 2026-07-17 | 2026-07-18 | 1d | 1.1.1.6.1FS |  |  | Development Team |  | 2026-07-17 | 2026-07-18
1.1.1.6.3 | 5 | Foundation | ITMS — Development | Development Team | Anomaly Detection / Checklist and Amount Identification | 100% | 0% | Not Started |  | 2026-07-18 | 2026-07-19 | 1d | 1.1.1.6.2FS |  |  | Development Team |  | 2026-07-18 | 2026-07-19
1.1.1.6.4 | 5 | Foundation | ITMS — Development | Development Team | DAR (Draft Audit Report) Automation | 100% | 0% | Not Started |  | 2026-07-19 | 2026-07-20 | 1d | 1.1.1.6.3FS |  |  | Development Team |  | 2026-07-19 | 2026-07-20
1.1.1.6.5 | 5 | Foundation | ITMS — Development | Development Team | Case Tracking | 100% | 90% | In UAT |  | 2026-07-19 | 2026-07-20 | 1d | 1.1.1.6.4FS |  |  | Development Team |  | 2026-07-19 | 2026-07-20
1.1.1.6.6 | 5 | Foundation | ITMS — Development | Development Team | Persona Creation - Proper Officer | 100% | 0% | Not Started |  | 2026-07-19 | 2026-07-20 | 1d | 1.1.1.6.5FS |  |  | Development Team |  | 2026-07-19 | 2026-07-20
1.1.1.7 | 4 | Foundation | ITMS — Development | VAT Committee | VAT Returns Changes | 100% | 90% | In UAT | 0 | 2026-07-24 | 2026-07-30 | 6d | 1.1.1.6FS |  |  | VAT Committee |  | 2026-07-24 | 2026-07-30
1.1.1.7.1 | 5 | Foundation | ITMS — Development | Development Team | Changes to RET-01 Form Preview | 100% | 0% | Not Started |  | 2026-07-24 | 2026-07-24 | 1d |  |  |  | Development Team |  | 2026-07-24 | 2026-07-24
1.1.1.7.2 | 5 | Foundation | ITMS — Development | Development Team | Changes to RET-01A Utility and JSON file | 100% | 0% | Not Started |  | 2026-07-24 | 2026-07-25 | 1d | 1.1.1.7.1FS |  |  | Development Team |  | 2026-07-24 | 2026-07-25
1.1.1.7.3 | 5 | Foundation | ITMS — Development | Development Team | Changes to RET-01A Form Preview | 100% | 0% | Not Started |  | 2026-07-25 | 2026-07-26 | 1d | 1.1.1.7.2FS |  |  | Development Team |  | 2026-07-25 | 2026-07-26
1.1.1.7.4 | 5 | Foundation | ITMS — Development | Development Team | Changes to RET-02 Form Preview | 100% | 0% | Not Started |  | 2026-07-26 | 2026-07-27 | 1d | 1.1.1.7.3FS |  |  | Development Team |  | 2026-07-26 | 2026-07-27
1.1.1.7.5 | 5 | Foundation | ITMS — Development | Development Team | Changes to RET-03 Utility and JSON file | 100% | 0% | Not Started |  | 2026-07-27 | 2026-07-28 | 1d | 1.1.1.7.4FS |  |  | Development Team |  | 2026-07-27 | 2026-07-28
1.1.1.7.6 | 5 | Foundation | ITMS — Development | Development Team | Changes to RET-03 Form Preview | 100% | 0% | Not Started |  | 2026-07-28 | 2026-07-29 | 1d | 1.1.1.7.5FS |  |  | Development Team |  | 2026-07-28 | 2026-07-29
1.1.1.8 | 4 | Foundation | ITMS — Development | Development Team | VAT Registration Tax Payer | 100% | 0% | Not Started | 1. Registration Amendment | 2026-07-24 | 2026-07-30 | 6d | 1.1.1.7FS |  |  | Development Team |  | 2026-07-24 | 2026-07-30
1.1.1.8.1 | 5 | Foundation | ITMS — Development | Development Team | Cancellation Application | 100% | 0% | Not Started |  | 2026-07-24 | 2026-07-24 | 1d |  |  |  | Development Team |  | 2026-07-24 | 2026-07-24
1.1.1.8.2 | 5 | Foundation | ITMS — Development | Development Team | Reply to Notice for Cancellation of Registrataion | 100% | 0% | Not Started |  | 2026-07-24 | 2026-07-25 | 1d | 1.1.1.8.1FS |  |  | Development Team |  | 2026-07-24 | 2026-07-25
1.1.1.8.3 | 5 | Foundation | ITMS — Development | Development Team | Application for Revocation of Cancellation of Registration | 100% | 0% | Not Started |  | 2026-07-25 | 2026-07-26 | 1d | 1.1.1.8.2FS |  |  | Development Team |  | 2026-07-25 | 2026-07-26
1.1.1.8.4 | 5 | Foundation | ITMS — Development | Development Team | Reply to Rejection of the Application for Revocation of Cancellation of Registration | 100% | 0% | Not Started |  | 2026-07-26 | 2026-07-27 | 1d | 1.1.1.8.3FS |  |  | Development Team |  | 2026-07-26 | 2026-07-27
1.1.1.8.5 | 5 | Foundation | ITMS — Development | Development Team | Declaration of Business Manager | 100% | 0% | Not Started |  | 2026-07-27 | 2026-07-28 | 1d | 1.1.1.8.4FS |  |  | Development Team |  | 2026-07-27 | 2026-07-28
1.1.1.9 | 4 | Foundation | ITMS — Development | Development Team | VAT Registration CRU & Proper Officer | 100% | 0% | Not Started | 1. Order of Amendment | 2026-07-24 | 2026-07-30 | 6d | 1.1.1.8FS |  |  | Development Team |  | 2026-07-24 | 2026-07-30
1.1.1.9.1 | 5 | Foundation | ITMS — Development | Development Team | Notice for Cancellation of Registrataion | 100% | 0% | Not Started |  | 2026-07-24 | 2026-07-24 | 1d |  |  |  | Development Team |  | 2026-07-24 | 2026-07-24
1.1.1.9.2 | 5 | Foundation | ITMS — Development | Development Team | Order for Cancellation | 100% | 0% | Not Started |  | 2026-07-24 | 2026-07-25 | 1d | 1.1.1.9.1FS |  |  | Development Team |  | 2026-07-24 | 2026-07-25
1.1.1.9.3 | 5 | Foundation | ITMS — Development | Development Team | Order for Dropping the proceeding for Cancellation | 100% | 0% | Not Started |  | 2026-07-25 | 2026-07-26 | 1d | 1.1.1.9.2FS |  |  | Development Team |  | 2026-07-25 | 2026-07-26
1.1.1.9.4 | 5 | Foundation | ITMS — Development | Development Team | Rejection to the Application for Revocation of Cancellation of Registration | 100% | 0% | Not Started |  | 2026-07-26 | 2026-07-27 | 1d | 1.1.1.9.3FS |  |  | Development Team |  | 2026-07-26 | 2026-07-27
1.1.1.9.5 | 5 | Foundation | ITMS — Development | Development Team | Order of Revocation of Cancellation of Registration | 100% | 0% | Not Started |  | 2026-07-27 | 2026-07-28 | 1d | 1.1.1.9.4FS |  |  | Development Team |  | 2026-07-27 | 2026-07-28
1.1.1.9.6 | 5 | Foundation | ITMS — Development | Development Team | Approval to the Declaration of Business Manager | 100% | 0% | Not Started |  | 2026-07-28 | 2026-07-29 | 1d | 1.1.1.9.5FS |  |  | Development Team |  | 2026-07-28 | 2026-07-29
1.1.1.10 | 4 | Foundation | ITMS — Development | Development Team | VAT Payments Tax Payer | 100% | 0% | Not Started | District code mapping other than Jaipiur & Dausa (Dependent on RMS - IFMS team) | 2026-07-24 | 2026-07-30 | 6d | 1.1.1.9FS |  |  | Development Team |  | 2026-07-24 | 2026-07-30
1.1.1.11 | 4 | Foundation | ITMS — Development | Development Team | VAT Officer (Returns & Payments) | 100% | 0% | Not Started |  | 2026-07-24 | 2026-07-30 | 6d | 1.1.1.10FS |  |  | Development Team |  | 2026-07-24 | 2026-07-30
1.1.2 | 3 |  |  |  | Analytics Team |  | 72.27% |  |  | 2026-06-06 | 2026-07-31 | 55d | [5 empty] | 2026-06-06 | 2026-07-31
1.1.2.1 | 4 | Foundation | ITMS — Analytics | DP | Lessees RCM liability on royalty | 100% | 100% | Completed | Shared | 2026-06-06 | 2026-06-12 | 6d |  | 2026-06-12 | 2026-06-06 | DP | Taxpayers impacted: 2753.0; Revenue potential: 85.39 Cr | 2026-06-06 | 2026-06-12
1.1.2.2 | 4 | Foundation | ITMS — Analytics | DP, JP | Analysis GTA to GTA Supply | 100% | 100% | Completed | Shared with Sohan sir. | 2026-06-06 | 2026-06-12 | 6d | 1.1.2.1FS | 2026-06-12 | 2026-06-06 | DP, JP |  | 2026-06-06 | 2026-06-12
1.1.2.3 | 4 | Foundation | ITMS — Analytics | DP | Provide Individual taxpayer - Royalty collection and e-Ravnna data | 100% | 100% | Completed | Shared | 2026-06-06 | 2026-06-12 | 6d | 1.1.2.2FS | 2026-06-12 | 2026-06-06 | DP |  | 2026-06-06 | 2026-06-12
1.1.2.4 | 4 | Foundation | ITMS — Analytics | ARJ | SGST to other heads and other heads to SGST payment Transfer Cases | 100% | 100% | Completed | 2024-25 = +114.53 Cr. - 151.87 = -37.34 Cr 2025-26 = -538 Cr. | 2026-06-07 | 2026-07-13 | 36d | 1.1.2.3FS | 2026-07-13 | 2026-06-07 | ARJ |  | 2026-06-07 | 2026-07-13
1.1.2.5 | 4 | Foundation | ITMS — Analytics | JP | Welcome letter Report | 100% | 100% | Completed | Shared with sohan sir | 2026-06-07 | 2026-07-15 | 38d | 1.1.2.4FS | 2026-07-15 | 2026-06-07 | JP |  | 2026-06-07 | 2026-07-15
1.1.2.6 | 4 | Foundation | ITMS — Analytics | Analytics Team | Taxpayers with high Cement purchase but no reversal-ACCT Enforcement | 100% | 100% | Completed | Shared with sohan sir | 2026-06-07 | 2026-07-15 | 38d | 1.1.2.5FS | 2026-07-15 | 2026-06-07 | Analytics Team |  | 2026-06-07 | 2026-07-15
1.1.2.7 | 4 | Foundation | ITMS — Analytics | Analytics Team | "FMCG Taxpayers B2C->B2B ratio analysis (List given by Sohan Sir)" | 100% | 100% | Completed | Shared with Sohan Sir | 2026-06-07 | 2026-06-13 | 6d | 1.1.2.6FS | 2026-06-13 | 2026-06-07 | Analytics Team |  | 2026-06-07 | 2026-06-13
1.1.2.8 | 4 | Foundation | ITMS — Analytics | JP | "LENSKART e-way bill (inward-outward) supplies from e-way bill data. " | 100% | 100% | Completed | Requested from Excise department and data shared to BIU | 2026-06-10 | 2026-07-08 | 28d | 1.1.2.7FS | 2026-07-08 | 2026-06-10 | JP |  | 2026-06-10 | 2026-07-08
1.1.2.9 | 4 | Foundation | ITMS — Analytics | MC | VAT Development functional and Testing support | 100% | 100% | Completed | - Explain the requirement to technical team '- Review of different forms '- Preparing Functional Requirement document for the team '- Functional and Technical Requirement gathering | 2026-06-10 | 2026-06-25 | 15d | 1.1.2.8FS | 2026-06-25 | 2026-06-10 | MC |  | 2026-06-10 | 2026-06-25
1.1.2.10 | 4 | Foundation | ITMS — Analytics | JP | Analysis of Credit Notes issued by service sectors | 100% | 100% | Completed | - Identification of Taxpayers who are primarily dealing in Service Sector '- Identification of taxpayers who are frequently issuing credit notes to the recipient | 2026-06-10 | 2026-06-16 | 6d | 1.1.2.9FS | 2026-06-16 | 2026-06-10 | JP |  | 2026-06-10 | 2026-06-16
1.1.2.11 | 4 | Foundation | ITMS — Analytics | JP | "Share sample cases from 4 various Scenerio ( Cases related to: 1. High Credit Note but No reversal 2. Eway bill mismatch (Inward V/S Outward) FY 2025-26 3. Multiple times Suomotto cancelled and then revocation 4. SAME PAN ( Total approved,cancelled,suspended etc.)" | 100% | 100% | Completed | shared | 2026-06-10 | 2026-07-08 | 28d | 1.1.2.10FS | 2026-07-08 | 2026-06-10 | JP |  | 2026-06-10 | 2026-07-08
1.1.2.12 | 4 | Foundation | ITMS — Analytics | DP | "Purchase from cancelled tax-payers Detailed list for scrutiny of Taxpayers of FY 2022-23" | 100% | 100% | Completed | Shared | 2026-06-10 | 2026-06-16 | 6d | 1.1.2.11FS | 2026-06-16 | 2026-06-10 | DP |  | 2026-06-10 | 2026-06-16
1.1.2.13 | 4 | Foundation | ITMS — Analytics | LP | GST 2.0 Impact analysis | 100% | 100% | Completed | Report has been updated on feedback | 2026-06-12 | 2026-06-18 | 6d | 1.1.2.12FS | 2026-06-18 | 2026-06-12 | LP |  | 2026-06-12 | 2026-06-18
1.1.2.14 | 4 | Foundation | ITMS — Analytics | RK | Zonal Review Meeting | 100% | 100% | Completed | Done | 2026-06-12 | 2026-06-15 | 3d | 1.1.2.13FS | 2026-06-15 | 2026-06-12 | RK |  | 2026-06-12 | 2026-06-15
1.1.2.15 | 4 | Foundation | ITMS — Analytics | JP | Admin Task | 100% | 100% | Completed | Raise ticket to IT cell (Rajesh L) for Whitelisting of SAS Server (db ctd_gst, user: GST_READ) | 2026-06-13 | 2026-06-19 | 6d | 1.1.2.14FS | 2026-06-19 | 2026-06-13 | JP | Taxpayers impacted: 25.0; Revenue potential: | 2026-06-13 | 2026-06-19
1.1.2.16 | 4 | Foundation | ITMS — Analytics | AJ | "As per directions of CMO, ppt for Zonal Presentation: 1) ETO 2) VAT 3) Virtual Hearing " | 100% | 100% | Completed | Shared | 2026-06-13 | 2026-06-16 | 3d | 1.1.2.15FS | 2026-06-16 | 2026-06-13 | AJ |  | 2026-06-13 | 2026-06-16
1.1.2.17 | 4 | Foundation | ITMS — Analytics | JP | Secondment related cases | 100% | 100% | Completed | Jitendra, upload in GDRIVE (RJ CTD), this needs to be verified by BIU Link | 2026-06-13 | 2026-06-19 | 6d | 1.1.2.16FS |  |  | JP | Taxpayers impacted: 25.0; Revenue potential: | 2026-06-13 | 2026-06-19
1.1.2.18 | 4 | Foundation | ITMS — Analytics | DP | Mining ERCC GST Liability | 100% | 100% | Completed | Update ERCC Contract List ( Still have Contract ID don't have lease mapping, So shared contrcat ID's with Mining department for lease mapping) | 2026-06-18 | 2026-06-24 | 6d | 1.1.2.17FS | 2026-06-24 | 2026-06-18 | DP |  | 2026-06-18 | 2026-06-24
1.1.2.19 | 4 | Foundation | ITMS — Analytics | Analytics Team | "Eatries dealing in 12% and shown in counter party of gstr8. Supplying through zomato & swiggy." | 100% | 0% | Blocked | Since aadhaar number is Masked. | 2026-06-24 | 2026-07-14 | 20d | 1.1.2.18FS |  |  | Analytics Team |  | 2026-06-24 | 2026-07-14
1.1.2.20 | 4 | Foundation | ITMS — Analytics | AJ | Dynamic MIS report (Nil Turnover taxpayers etc) | 100% | 100% | Completed | Link | 2026-06-24 | 2026-07-10 | 16d | 1.1.2.19FS | 2026-07-10 | 2026-06-24 | AJ |  | 2026-06-24 | 2026-07-10
1.1.2.21 | 4 | Foundation | ITMS — Analytics | Analytics Team | CYBER FRAUD -I cyber fraud vs bank account details analysis | 100% | 100% | Completed | Shared on Feedback Portal | 2026-06-24 | 2026-06-30 | 6d | 1.1.2.20FS | 2026-06-30 | 2026-06-24 | Analytics Team |  | 2026-06-24 | 2026-06-30
1.1.2.22 | 4 | Foundation | ITMS — Analytics | Analytics Team | CYBER FRAUD -II Pertaining to payments | 100% | 0% | Blocked | Bank account details not available in payment challan API's | 2026-06-25 | 2026-07-01 | 6d | 1.1.2.21FS |  |  | Analytics Team |  | 2026-06-25 | 2026-07-01
1.1.2.23 | 4 | Foundation | ITMS — Analytics | SL+AJ | Data scrapping of reg. data from registration module (BOWEB). Data extracted and report for rejected application from other states in progress | 100% | 100% | Completed | Data Extraction Completed Link | 2026-06-26 | 2026-07-23 | 27d | 1.1.2.22FS |  |  | SL+AJ |  | 2026-06-26 | 2026-07-23
1.1.2.24 | 4 | Foundation | ITMS — Analytics | LP | "LENSKART e-way bill (inward-outward) supplies from e-way bill data. " | 100% | 100% | Completed | Report shared as google sheet. Feedback received and shared | 2026-06-30 | 2026-07-03 | 3d | 1.1.2.23FS | 2026-07-03 | 2026-06-30 | LP |  | 2026-06-30 | 2026-07-03
1.1.2.25 | 4 | Foundation | ITMS — Analytics | AJ+SL | "1) Nil filers more then 6 Months 2) Check with R1,3B & EWAY bill " | 100% | 100% | Completed | Report shared on feedback portal | 2026-06-30 | 2026-07-10 | 10d | 1.1.2.24FS | 2026-07-10 | 2026-06-30 | AJ+SL |  | 2026-06-30 | 2026-07-10
1.1.2.26 | 4 | Foundation | ITMS — Analytics | SL | Re-claim ledger static from last 6 months | 100% | 100% | Completed | Report shared on feedback portal | 2026-06-30 | 2026-07-10 | 10d | 1.1.2.25FS | 2026-07-10 | 2026-06-30 | SL |  | 2026-06-30 | 2026-07-10
1.1.2.27 | 4 | Foundation | ITMS — Analytics | SG | Data Integration Integration with Mining | 100% | 100% | Completed | Team has shared, API related Schema & doc. for further integration process to Mining dept. | 2026-06-30 | 2026-07-31 | 31d | 1.1.2.26FS |  |  | SG |  | 2026-06-30 | 2026-07-31
1.1.2.28 | 4 | Foundation | ITMS — Analytics | MC | Business Audit Module "- Explain the requirements to technical team, 'Development of prototype and discussions with BA Officers, '- Preparing Functional Requirement document for the team, '- Testing and bug identification" | 100% | 40% | In Progress | - Explain the requirements to technical team, 'Development of prototype and discussions with BA Officers, '- Preparing Functional Requirement document for the team, '- Testing and bug identification | 2026-07-03 | 2026-07-18 | 15d | 1.1.2.27FS |  |  | MC |  | 2026-07-03 | 2026-07-18
1.1.2.29 | 4 | Foundation | ITMS — Analytics | SG+JP | 50 Thousand GST Registration data not available. Need to download and integrate with Oracle database | 100% | 100% | Completed | all data is updated for registration as well as in oracle DB | 2026-07-03 | 2026-07-22 | 19d | 1.1.2.28FS | 2026-07-22 | 2026-07-03 | SG+JP |  | 2026-07-03 | 2026-07-22
1.1.2.30 | 4 | Foundation | ITMS — Analytics | SL | "Purchase from cancelled tax-payers Detailed list for scrutiny of Taxpayers of FY 2022-23" | 100% | 100% | Completed | Eatries dealing in 12% and shown in counter party of gstr8. Supplying through zomato & swiggy. | 2026-07-03 | 2026-07-31 | 28d | 1.1.2.29FS |  |  | SL |  | 2026-07-03 | 2026-07-31
1.1.2.31 | 4 | Foundation | ITMS — Analytics | DP | Vahan integration with GST | 100% | 100% | Completed | Analysis done on 1 year data. PAN data requested from DoRIEO | 2026-07-03 | 2026-07-10 | 7d | 1.1.2.30FS | 2026-07-10 | 2026-07-03 | DP |  | 2026-07-03 | 2026-07-10
1.1.2.32 | 4 | Foundation | ITMS — Analytics | Analytics Team | Estimated liability derived from TDS dedcution and GSTR1 against government invoices | 100% | 100% | Completed | Shared on FEEDBACK PORTAL | 2026-07-03 | 2026-07-07 | 4d | 1.1.2.31FS | 2026-07-07 | 2026-07-03 | Analytics Team |  | 2026-07-03 | 2026-07-07
1.1.2.33 | 4 | Foundation | ITMS — Analytics | SG | Electricity report "List fo 197 taxpayers send on feedback portal, need to be pushed again after reverification" | 100% | 100% | Completed | Manufacturer to be added, high turnover low bill. Sheet uploaded:- Drive Link Use-case disucssed Shared with the BIU team, They are preparing the note. | 2026-07-03 | 2026-07-14 | 11d | 1.1.2.32FS |  |  | SG |  | 2026-07-03 | 2026-07-14
1.1.2.34 | 4 | Foundation | ITMS — Analytics | SL+SG | Data Integration + RERA Currently we are scrapping though Public portal" | 100% | 60% | In Progress | RERA letter for integration, has been Shared to RERA dept. Discussion done with RERA. Fields has been shared with RERA for further data integration They are developing API's SPOC: Gaurav Shegal (+91 8860895078) | 2026-07-03 | 2026-07-18 | 15d | 1.1.2.33FS |  |  | SL+SG |  | 2026-07-03 | 2026-07-18
1.1.2.35 | 4 | Foundation | ITMS — Analytics | Analytics Team | cancellations cases list for FIR | 100% | 100% | Completed | ITC 3B Reversal Dashboard Taxpayer wise | 2026-07-03 | 2026-07-18 | 15d | 1.1.2.34FS | 2026-07-18 | 2026-07-03 | Analytics Team |  | 2026-07-03 | 2026-07-18
1.1.2.36 | 4 | Foundation | ITMS — Analytics | SG+AG | Electrictity report "New usecase to be developed using Electricity data(api) for the new tax payers (post feb 2025 )" | 100% | 60% | In Progress | Manufacturer to be added, high turnover low bill. will reverify. Report downloaded & extracting consumption Link TOP 18 CASES Link Shared with the BIU team, They are preparing the note. | 2026-07-03 | 2026-07-24 | 21d | 1.1.2.35FS |  |  | SG+AG |  | 2026-07-03 | 2026-07-24
1.1.2.37 | 4 | Foundation | ITMS — Analytics | JP | New registration (high IGST Sales) | 100% | 100% | Completed | List of taxpayers where welcome letter returned were extracted and shared on Feedback Portal | 2026-07-03 | 2026-07-09 | 6d | 1.1.2.36FS | 2026-07-09 | 2026-07-03 | JP |  | 2026-07-03 | 2026-07-09
1.1.2.38 | 4 | Foundation | ITMS — Analytics | SL | Taxpayers Cancelled on Application with high turnover in short period | 100% | 100% | Completed | R1 vs 3B and 2B vs 3B extracted from Boweb and other Parameters being run for FY 2025-26 | 2026-07-03 | 2026-07-22 | 19d | 1.1.2.37FS |  |  | SL |  | 2026-07-03 | 2026-07-22
1.1.2.39 | 4 | Foundation | ITMS — Analytics | LP | Transaction of cancelled taxpayer with TDS dealer (AG) | 100% | 100% | Completed | Shared with BIU for further verification | 2026-07-03 | 2026-07-16 | 13d | 1.1.2.38FS |  |  | LP |  | 2026-07-03 | 2026-07-16
1.1.2.40 | 4 | Foundation | ITMS — Analytics | DP | RCM Liability on Royality | 100% | 100% | Completed | Report shared on feedback portal | 2026-07-04 | 2026-07-10 | 6d | 1.1.2.39FS | 2026-07-10 | 2026-07-04 | DP |  | 2026-07-04 | 2026-07-10
1.1.2.41 | 4 | Foundation | ITMS — Analytics | JP/LP | GSTR1 HSN Summary Mismatch Correction (FY25-26) | 100% | 60% | In Progress | Shared with BIU for further verification | 2026-07-09 | 2026-07-15 | 6d | 1.1.2.40FS |  |  | JP/LP |  | 2026-07-09 | 2026-07-15
1.1.2.42 | 4 | Foundation | ITMS — Analytics | LP | Data Request Data request to received from RGHS | 100% | 100% | Completed | Identified 3 firms with Lenskart tradename. Link | 2026-07-09 | 2026-07-15 | 6d | 1.1.2.41FS | 2026-07-15 | 2026-07-09 | LP |  | 2026-07-09 | 2026-07-15
1.1.2.43 | 4 | Foundation | ITMS — Analytics | DP+CA | Feedback report - DoRIEO Report Profit and loss (unbilled revenues) | 100% | 60% | In Progress | Report shared, under review. | 2026-07-10 | 2026-07-24 | 14d | 1.1.2.42FS |  |  | DP+CA |  | 2026-07-10 | 2026-07-24
1.1.2.44 | 4 | Foundation | ITMS — Analytics | RK | Quarterly Task Taxpayers Cancelled on Application with high turnover in short period | 100% | 100% | Completed | LINK | 2026-07-10 | 2026-07-23 | 13d | 1.1.2.43FS | 2026-07-23 | 2026-07-10 | RK |  | 2026-07-10 | 2026-07-23
1.1.2.45 | 4 | Foundation | ITMS — Analytics | AJ | Development Task Dynamic MIS report (Nil Turnover taxpayers etc) | 100% | 40% | In Progress | team is developing a service (UI+API+Oracle) | 2026-07-10 | 2026-07-24 | 14d | 1.1.2.44FS |  |  | AJ |  | 2026-07-10 | 2026-07-24
1.1.2.46 | 4 | Foundation | ITMS — Analytics | AJ | One time task New registration and sales to unregistered taxpayers | 100% | 60% | In Progress | Sheet updated on drive, to be discussed with team Link (Based on DGGI Report) | 2026-07-10 | 2026-07-29 | 19d | 1.1.2.45FS |  |  | AJ |  | 2026-07-10 | 2026-07-29
1.1.2.47 | 4 | Foundation | ITMS — Analytics | RK | One time task GSTR9- diff between tax paid and payable | 100% | 60% | In Progress | Review Pending (Based on DGGI Report) with CA | 2026-07-10 | 2026-07-22 | 12d | 1.1.2.46FS |  |  | RK |  | 2026-07-10 | 2026-07-22
1.1.2.48 | 4 | Foundation | ITMS — Analytics | RK+SL | Red Flag Reports | 100% | 40% | In Progress | Under progress | 2026-07-10 | 2026-07-31 | 21d | 1.1.2.47FS |  |  | RK+SL |  | 2026-07-10 | 2026-07-31
1.1.2.49 | 4 | Foundation | ITMS — Analytics | RK | B2C Comparision of Retail Marts-ACCT Enforcement | 100% | 100% | Completed | Completed in SAS | 2026-07-10 | 2026-07-20 | 10d | 1.1.2.48FS | 2026-07-20 | 2026-07-10 | RK |  | 2026-07-10 | 2026-07-20
1.1.2.50 | 4 | Foundation | ITMS — Analytics | Analytics Team | common credit reversal | 100% | 100% | Completed | Shared with Sohan Sir, based on DGGI Report | 2026-07-10 | 2026-07-16 | 6d | 1.1.2.49FS | 2026-07-16 | 2026-07-10 | Analytics Team |  | 2026-07-10 | 2026-07-16
1.1.2.51 | 4 | Foundation | ITMS — Analytics | Analytics Team | marble slurry IGST sales | 100% | 100% | Completed | Uploaded on Drive (Based on DGGI report) | 2026-07-10 | 2026-07-16 | 6d | 1.1.2.50FS | 2026-07-16 | 2026-07-10 | Analytics Team |  | 2026-07-10 | 2026-07-16
1.1.2.52 | 4 | Foundation | ITMS — Analytics | RK | Same bank accounts used by multiple registration | 100% | 0% | Blocked | To discuss with ARJ (Based on DGGI Report) Access available only to Enforcement officers | 2026-07-10 | 2026-07-16 | 6d | 1.1.2.51FS |  |  | RK |  | 2026-07-10 | 2026-07-16
1.1.2.53 | 4 | Foundation | ITMS — Analytics | LP | Eway bill vs gstr (B2b and b2c) parameter 5 of scuntiny | 100% | 100% | Completed | Data prepared, now pending review Link | 2026-07-10 | 2026-07-21 | 11d | 1.1.2.52FS |  |  | LP |  | 2026-07-10 | 2026-07-21
1.1.2.54 | 4 | Foundation | ITMS — Analytics | RK | Transit Cases - Penalty MIS (ewb RELATED OFFENCES) | 100% | 100% | Completed | Review pending LINK (Based on DGGI Report) | 2026-07-10 | 2026-07-16 | 6d | 1.1.2.53FS |  |  | RK |  | 2026-07-10 | 2026-07-16
1.1.2.55 | 4 | Foundation | ITMS — Analytics | AJ | Vehicle Trend Analysis based on Fuel Type/Brand and other Parameters | 100% | 100% | Completed | Reports (ITMS) to be updated - Monthly, Quarterly and Annualy | 2026-07-10 | 2026-07-19 | 9d | 1.1.2.54FS | 2026-07-19 | 2026-07-10 | AJ |  | 2026-07-10 | 2026-07-19
1.1.2.56 | 4 | Foundation | ITMS — Analytics | DP | One time task | 100% | 100% | Completed | Fuel type done | 2026-07-10 | 2026-07-16 | 6d | 1.1.2.55FS | 2026-07-16 | 2026-07-10 | DP |  | 2026-07-10 | 2026-07-16
1.1.2.57 | 4 | Foundation | ITMS — Analytics | JP | Data Request | 100% | 100% | Completed | Shared with sohan sir | 2026-07-10 | 2026-07-15 | 5d | 1.1.2.56FS | 2026-07-15 | 2026-07-10 | JP |  | 2026-07-10 | 2026-07-15
1.1.2.58 | 4 | Foundation | ITMS — Analytics | LP | New registration v/s E-way bill report | 100% | 100% | Completed | Shared with BIU for further verification Link | 2026-07-10 | 2026-07-14 | 4d | 1.1.2.57FS | 2026-07-14 | 2026-07-10 | LP |  | 2026-07-10 | 2026-07-14
1.1.2.59 | 4 | Foundation | ITMS — Analytics | JP/LP | One time task | 100% | 100% | Completed | Data Extraction under progress | 2026-07-10 | 2026-07-23 | 13d | 1.1.2.58FS |  |  | JP/LP |  | 2026-07-10 | 2026-07-23
1.1.2.60 | 4 | Foundation | ITMS — Analytics | DP | One time task | 100% | 100% | Completed | Summary file uploaded on feedback Detailed invoice wise list shared on mails with DCs | 2026-07-10 | 2026-07-17 | 7d | 1.1.2.59FS | 2026-07-17 | 2026-07-10 | DP |  | 2026-07-10 | 2026-07-17
1.1.2.61 | 4 | Foundation | ITMS — Analytics | DP | One time task | 100% | 0% | Not Started | Based on DGGI Report | 2026-07-10 | 2026-07-16 | 6d | 1.1.2.60FS |  |  | DP |  | 2026-07-10 | 2026-07-16
1.1.2.62 | 4 | Foundation | ITMS — Analytics | LP+JP | "-SAC 9966 [5% (Without ITC)] and [18% (With ITC)] '-Non body Corporate to Corporate Pvt. Ltd. (5% with RCM) '-Car Rental cases based on Place of Supply (if Jaipur-> Delhi then SGST+CGST) if it is round trip then IGST '-Second Hand Car sale (Cases of Fake Invoicing) '-Car + Accommodation -> Mix Supply (If not natural bundled)" | 100% | 0% | Not Started | discussed done with Rajesh Gadwal sir | 2026-07-13 | 2026-07-19 | 6d | 1.1.2.61FS |  |  | LP+JP |  | 2026-07-13 | 2026-07-19
1.1.2.63 | 4 | Foundation | ITMS — Analytics | LP | "Electrictity dept. API integration (enhacement), Discuss with Rohitash Meena Sir. 1) Need data for all Financial Year. 2) Get API to get details based on PAN/GSTIN API, currently its on Knumber." | 100% | 40% | In Progress | Letter has been shared to ACCT , by Ashwin Sir on 14th July. We receieved data from RGHS MIS (last 2 years) without GSTIN/PAN, hence required RGHS dept. to provide the same. | 2026-07-13 | 2026-07-28 | 15d | 1.1.2.62FS |  |  | LP |  | 2026-07-13 | 2026-07-28
1.1.2.64 | 4 | Foundation | ITMS — Analytics | MC | Presentation | 100% | 100% | Completed | As per directions of CMO, ppt for Zonal Presentation: 1) ETO 2) VAT 3) Virtual Hearing | 2026-07-13 | 2026-07-17 | 4d | 1.1.2.63FS | 2026-07-17 | 2026-07-13 | MC |  | 2026-07-13 | 2026-07-17
1.1.2.65 | 4 | Foundation | ITMS — Analytics | MC | Cancelled taxpayer cancellations cases list for FIR | 100% | 60% | In Progress | Shared with BIU for further verification | 2026-07-13 | 2026-07-14 | 1d | 1.1.2.64FS |  |  | MC |  | 2026-07-13 | 2026-07-14
1.1.2.67 | 4 | Foundation | ITMS — Analytics | AJ | Letter Template | 100% | 100% | Completed | Will be shared along with Concurrent Scrutiny Data | 2026-07-13 | 2026-07-20 | 7d | 1.1.2.66FS | 2026-07-20 | 2026-07-13 | AJ |  | 2026-07-13 | 2026-07-20
1.1.2.68 | 4 | Foundation | ITMS — Analytics | JP | One time task | 100% | 100% | Completed | Shared with Sohan Sir | 2026-07-14 | 2026-07-20 | 6d | 1.1.2.67FS | 2026-07-20 | 2026-07-14 | JP |  | 2026-07-14 | 2026-07-20
1.1.2.69 | 4 | Foundation | ITMS — Analytics | DP | ERCC GST Liability | 100% | 100% | Completed | Update ERCC Contract List ( Still have Contract ID don't have lease mapping) Contract copy to be recieved from mining dept." | 2026-07-15 | 2026-07-31 | 16d | 1.1.2.68FS |  |  | DP | Taxpayers impacted: 2753.0; Revenue potential: 85.39 Cr | 2026-07-15 | 2026-07-31
1.1.2.70 | 4 | Foundation | ITMS — Analytics | AJ | Presentation | 100% | 100% | Completed | Link | 2026-07-15 | 2026-07-31 | 16d | 1.1.2.69FS | 2026-07-31 | 2026-07-15 | AJ |  | 2026-07-15 | 2026-07-31
1.1.2.71 | 4 | Foundation | ITMS — Analytics | JP | One time task | 100% | 100% | Completed | ACCT BIU had a meeting with Secretary JJM. He directed officers to share a few use cases for analysis with CTD | 2026-07-15 | 2026-07-31 | 16d | 1.1.2.70FS |  |  | JP |  | 2026-07-15 | 2026-07-31
1.1.2.72 | 4 | Foundation | ITMS — Analytics | SG | Officer Jurisdiction sheet to be preprated | 100% | 100% | Completed | Link | 2026-07-15 | 2026-07-15 | 1d | 1.1.2.71FS | 2026-07-15 | 2026-07-15 | SG |  | 2026-07-15 | 2026-07-15
1.1.2.73 | 4 | Foundation | ITMS — Analytics | SL | Monthly Presentation | 100% | 100% | Completed | Meeting Re-scheduled to 25th July PPT shared with Mam | 2026-07-15 | 2026-07-25 | 10d | 1.1.2.72FS | 2026-07-25 | 2026-07-15 | SL |  | 2026-07-15 | 2026-07-25
1.1.2.74 | 4 | Foundation | ITMS — Analytics | SG | Data Integration | 100% | 100% | Completed | Shared the latest status. | 2026-07-15 | 2026-07-30 | 15d | 1.1.2.73FS |  |  | SG |  | 2026-07-15 | 2026-07-30
1.1.2.75 | 4 | Foundation | ITMS — Analytics | Analytics Team | section 71 access to businss premises offline utility | 100% | 0% | Not Started | section 71 access to businss premises offline utility | 2026-07-16 | 2026-07-22 | 6d | 1.1.2.74FS |  |  | Analytics Team |  | 2026-07-16 | 2026-07-22
1.1.2.76 | 4 | Foundation | ITMS — Analytics | DP+SL | Data Integration | 100% | 40% | In Progress | Letter has been shared with dept. 1 year data dump received from SDRI. Re-check with SDRI for relevent data | 2026-07-16 | 2026-07-31 | 15d | 1.1.2.75FS |  |  | DP+SL |  | 2026-07-16 | 2026-07-31
1.1.2.77 | 4 | Foundation | ITMS — Analytics | SG | TMT Bar Manufactures letter (Income tax dept.) | 100% | 60% | In Progress | Link THE IT Department conducted survey on certain GST taxpayers and recovered loose papers and whatsapp chat indicationg suspected supression of turnover. The cases have been taken up generally for all taxpayers for analysis wherever K-Number is available, by comparing electicity consumption with r | 2026-07-16 | 2026-07-19 | 3d | 1.1.2.76FS |  |  | SG |  | 2026-07-16 | 2026-07-19
1.1.2.78 | 4 | Foundation | ITMS — Analytics | Analytics Team | Integration with Mining | 100% | 40% | In Progress | Dept not sharing the API | 2026-07-16 | 2026-07-31 | 15d | 1.1.2.77FS |  |  | Analytics Team |  | 2026-07-16 | 2026-07-31
1.1.2.79 | 4 | Foundation | ITMS — Analytics | Analytics Team | "Purchase from cancelled tax-payers Detailed list for scrutiny of Taxpayers of FY 2022-23" | 100% | 100% | Completed | Shared through email to all field officers | 2026-07-17 | 2026-07-23 | 6d | 1.1.2.78FS | 2026-07-23 | 2026-07-17 | Analytics Team |  | 2026-07-17 | 2026-07-23
1.1.2.80 | 4 | Foundation | ITMS — Analytics | JP | GST ITC-04 Analysis | 100% | 0% | Not Started | Description | 2026-07-17 | 2026-07-23 | 6d | 1.1.2.79FS |  |  | JP |  | 2026-07-17 | 2026-07-23
1.1.2.81 | 4 | Foundation | ITMS — Analytics | LP | GSTN API Verification | 100% | 100% | Completed | Confirmed; Data being extracted for all taxpayers for analysis and verification High_risk profile details.xlsx | 2026-07-17 | 2026-07-23 | 6d | 1.1.2.80FS | 2026-07-23 | 2026-07-17 | LP |  | 2026-07-17 | 2026-07-23
1.1.2.82 | 4 | Foundation | ITMS — Analytics | JP | GSTR1 HSN Summary Mismatch Correction (FY25-26) | 100% | 40% | In Progress | Discussion needed | 2026-07-18 | 2026-07-24 | 6d | 1.1.2.81FS |  |  | JP |  | 2026-07-18 | 2026-07-24
1.1.2.83 | 4 | Foundation | ITMS — Analytics | LP | Misclassification of product | 100% | 60% | In Progress | Report uploaded further discussion with Audit team Link | 2026-07-18 | 2026-07-24 | 6d | 1.1.2.82FS |  |  | LP |  | 2026-07-18 | 2026-07-24
1.1.2.84 | 4 | Foundation | ITMS — Analytics | LP+DP | Pebble taxpayer inward outward analysis | 100% | 60% | In Progress | Data has been shared with BIU. | 2026-07-20 | 2026-07-26 | 6d | 1.1.2.83FS |  |  | LP+DP |  | 2026-07-20 | 2026-07-26
1.1.2.85 | 4 | Foundation | ITMS — Analytics | JK | Top reversal case | 100% | 40% | In Progress | Asked by CCT mam | 2026-07-21 | 2026-07-27 | 6d | 1.1.2.84FS |  |  | JK |  | 2026-07-21 | 2026-07-27
1.1.2.86 | 4 | Foundation | ITMS — Analytics | LP | GSTR9 non-filer list | 100% | 100% | Completed | Data shared with ACCT Sir Link | 2026-07-21 | 2026-07-21 | 1d | 1.1.2.85FS | 2026-07-21 | 2026-07-21 | LP |  | 2026-07-21 | 2026-07-21
1.1.2.87 | 4 | Foundation | ITMS — Analytics | LP | Transaction of cancelled taxpayer with TDS dealer (AG) | 100% | 60% | In Progress | Transactions with composition deal all time. | 2026-07-25 | 2026-07-31 | 6d | 1.1.2.86FS |  |  | LP |  | 2026-07-25 | 2026-07-31
1.1.2.88 | 4 | Foundation | ITMS — Analytics | YK/DP | AI-based P&L doc processing for FY 2023-24 | 100% | 100% | Completed | PPT Prepared Top 5 cases has been created. 1) Mining 2) LEGAL & Professional 3) Freight | 2026-07-25 | 2026-07-31 | 6d | 1.1.2.87FS | 2026-07-31 | 2026-07-25 | YK/DP |  | 2026-07-25 | 2026-07-31
1.1.2.89 | 4 | Foundation | ITMS — Analytics | LP/SG | "Electrictity dept. API integration (enhacement), Discuss with Rohitash Meena Sir. 1) Need data for all Financial Year. 2) Get API to get details based on PAN/GSTIN API, currently its on Knumber." | 100% | 40% | In Progress | Discussion done with Mahipal Ji (JDA), they have requested specific format and data fields required for analysis. Integration data format: Excel Intergration data letter with jda Letter Link recived sample data 24 July | 2026-07-25 | 2026-07-31 | 6d | 1.1.2.88FS |  |  | LP/SG |  | 2026-07-25 | 2026-07-31
1.1.2.90 | 4 | Foundation | ITMS — Analytics | JP | TDS and GSTR1 analysis | 100% | 0% | Not Started | Data needs to computed | 2026-07-25 | 2026-07-31 | 6d | 1.1.2.89FS |  |  | JP |  | 2026-07-25 | 2026-07-31
1.1.3 | 3 |  |  |  | RAID (Nexus) Development |  | 100% |  |  | 2026-06-10 | 2026-07-30 | 50d | [5 empty] | 2026-06-10 | 2026-07-30
1.1.3.1 | 4 | Foundation | Registration Manual Sync/Download | Sanjay (Lead) | Registration Manual Sync dB schema creation | 100% | 100% | Completed | Delivered via Jira KAN-63 (Feature) | 2026-06-10 | 2026-07-21 | 41d |  | 2026-07-21 | 2026-06-10 | Sanjay (Lead) |  | 2026-06-10 | 2026-07-21
1.1.3.2 | 4 | Foundation | Non-Filer & Sector Analytics | Sanjay (Lead) | dB ¦ Sector outlier | 100% | 100% | Completed | Delivered via Jira KAN-115 (Story) | 2026-06-10 | 2026-07-13 | 33d | 1.1.3.1FS | 2026-07-13 | 2026-06-10 | Sanjay (Lead) |  | 2026-06-10 | 2026-07-13
1.1.3.3 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Get Use to SKILLS in claude & vibe coding tools | 100% | 100% | Completed | Delivered via Jira KAN-27 (Task) | 2026-06-10 | 2026-07-21 | 41d | 1.1.3.2FS | 2026-07-21 | 2026-06-10 | Sanjay (Lead) |  | 2026-06-10 | 2026-07-21
1.1.3.4 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Consolidate CM/CS/PSF ppt Deck and break them down into: 1) Progress 2) Action Plan 3) Directions | 100% | 100% | Completed | Delivered via Jira KAN-31 (Feature) | 2026-06-10 | 2026-07-21 | 41d | 1.1.3.3FS | 2026-07-21 | 2026-06-10 | Sanjay (Lead) |  | 2026-06-10 | 2026-07-21
1.1.3.5 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Work with Lokesh for getting 12% GSTN 2.0 impact cases. Specially in cement sector. | 100% | 100% | Completed | Delivered via Jira KAN-38 (Feature) | 2026-06-10 | 2026-07-21 | 41d | 1.1.3.4FS | 2026-07-21 | 2026-06-10 | Sanjay (Lead) |  | 2026-06-10 | 2026-07-21
1.1.3.6 | 4 | Foundation | Platform, DevOps & Core Utility | Sanjay (Lead) | Add deloitte branding theme (Black & Green) on UI | 100% | 100% | Completed | Delivered via Jira KAN-28 (Feature) | 2026-06-10 | 2026-07-21 | 41d | 1.1.3.5FS | 2026-07-21 | 2026-06-10 | Sanjay (Lead) |  | 2026-06-10 | 2026-07-21
1.1.3.7 | 4 | Foundation | P&L Analysis / My Profile / CBT | Sanjay (Lead) | Create My Profile Page, similar to the one we have in ITMS, using screenshots | 100% | 100% | Completed | Delivered via Jira KAN-33 (Feature) | 2026-06-10 | 2026-07-21 | 41d | 1.1.3.6FS | 2026-07-21 | 2026-06-10 | Sanjay (Lead) |  | 2026-06-10 | 2026-07-21
1.1.3.8 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Mail to Navojit WB EOI signed resume | 100% | 100% | Completed | Delivered via Jira KAN-34 (Feature) | 2026-06-10 | 2026-07-21 | 41d | 1.1.3.7FS | 2026-07-21 | 2026-06-10 | Sanjay (Lead) |  | 2026-06-10 | 2026-07-21
1.1.3.9 | 4 | Foundation | Platform, DevOps & Core Utility | Sanjay (Lead) | Run React app on GCP | 100% | 100% | Completed | Delivered via Jira KAN-41 (Feature) | 2026-06-11 | 2026-07-21 | 40d | 1.1.3.8FS | 2026-07-21 | 2026-06-11 | Sanjay (Lead) |  | 2026-06-11 | 2026-07-21
1.1.3.10 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Took Google Cloud access from deloitte (No WBS Code). | 100% | 100% | Completed | Delivered via Jira KAN-36 (Feature) | 2026-06-11 | 2026-07-21 | 40d | 1.1.3.9FS | 2026-07-21 | 2026-06-11 | Sanjay (Lead) |  | 2026-06-11 | 2026-07-21
1.1.3.11 | 4 | Foundation | Platform, DevOps & Core Utility | Sanjay (Lead) | Redesign the UI code, architecturly handing the proper design patters, consisten , organized and consistent across. | 100% | 100% | Completed | Delivered via Jira KAN-30 (Feature) | 2026-06-12 | 2026-07-21 | 39d | 1.1.3.10FS | 2026-07-21 | 2026-06-12 | Sanjay (Lead) |  | 2026-06-12 | 2026-07-21
1.1.3.12 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Connect with Harshvardhan for for West Bengal EOI | 100% | 100% | Completed | Delivered via Jira KAN-29 (Feature) | 2026-06-12 | 2026-07-21 | 39d | 1.1.3.11FS | 2026-07-21 | 2026-06-12 | Sanjay (Lead) |  | 2026-06-12 | 2026-07-21
1.1.3.13 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Took Followuo from HR(Nimisha) 1)Atul & Kewal 2) Ajay | 100% | 100% | Completed | Delivered via Jira KAN-37 (Feature) | 2026-06-12 | 2026-07-21 | 39d | 1.1.3.12FS | 2026-07-21 | 2026-06-12 | Sanjay (Lead) |  | 2026-06-12 | 2026-07-21
1.1.3.14 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Register for GenW.AI academy | 100% | 100% | Completed | Delivered via Jira KAN-35 (Feature) | 2026-06-12 | 2026-07-21 | 39d | 1.1.3.13FS | 2026-07-21 | 2026-06-12 | Sanjay (Lead) |  | 2026-06-12 | 2026-07-21
1.1.3.15 | 4 | Foundation | Non-Filer & Sector Analytics | Sanjay (Lead) | UI ¦ Sector outlier | 100% | 100% | Completed | Delivered via Jira KAN-114 (Story) | 2026-06-12 | 2026-07-09 | 27d | 1.1.3.14FS | 2026-07-09 | 2026-06-12 | Sanjay (Lead) |  | 2026-06-12 | 2026-07-09
1.1.3.16 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Connect with Riddhima for her feedback on RAID | 100% | 100% | Completed | Delivered via Jira KAN-25 (Feature) | 2026-06-15 | 2026-07-21 | 36d | 1.1.3.15FS | 2026-07-21 | 2026-06-15 | Sanjay (Lead) |  | 2026-06-15 | 2026-07-21
1.1.3.17 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Working on Audit utility , liasoning with Meena sir | 100% | 100% | Completed | Delivered via Jira KAN-43 (Feature) | 2026-06-15 | 2026-07-21 | 36d | 1.1.3.16FS | 2026-07-21 | 2026-06-15 | Sanjay (Lead) |  | 2026-06-15 | 2026-07-21
1.1.3.18 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Create Action plan PPT (slide 13) from draft | 100% | 100% | Completed | Delivered via Jira KAN-39 (Feature) | 2026-06-15 | 2026-07-21 | 36d | 1.1.3.17FS | 2026-07-21 | 2026-06-15 | Sanjay (Lead) |  | 2026-06-15 | 2026-07-21
1.1.3.19 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | PPT connect with claude , R&D | 100% | 100% | Completed | Delivered via Jira KAN-26 (Business Development) | 2026-06-18 | 2026-07-21 | 33d | 1.1.3.18FS | 2026-07-21 | 2026-06-18 | Sanjay (Lead) |  | 2026-06-18 | 2026-07-21
1.1.3.20 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | IGRS mail initate for pending data. | 100% | 100% | Completed | Delivered via Jira KAN-44 (Feature) | 2026-06-18 | 2026-07-21 | 33d | 1.1.3.19FS | 2026-07-21 | 2026-06-18 | Sanjay (Lead) |  | 2026-06-18 | 2026-07-21
1.1.3.21 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | dB Scheme design and table data recieved from Jitu ji | 100% | 100% | Completed | Delivered via Jira KAN-45 (Feature) | 2026-06-18 | 2026-07-21 | 33d | 1.1.3.20FS | 2026-07-21 | 2026-06-18 | Sanjay (Lead) |  | 2026-06-18 | 2026-07-21
1.1.3.22 | 4 | Foundation | Platform, DevOps & Core Utility | Sanjay (Lead) | Create and demploy "File Sharing Application-drive" for team productivity | 100% | 100% | Completed | Delivered via Jira KAN-72 (Story) | 2026-06-19 | 2026-07-21 | 32d | 1.1.3.21FS | 2026-07-21 | 2026-06-19 | Sanjay (Lead) |  | 2026-06-19 | 2026-07-21
1.1.3.23 | 4 | Foundation | R3B / GSTR Reports & Reversal | Sanjay (Lead) | API + UI+ DB for R3b Reversal screen | 100% | 100% | Completed | Delivered via Jira KAN-116 (Story) | 2026-06-19 | 2026-07-09 | 20d | 1.1.3.22FS | 2026-07-09 | 2026-06-19 | Sanjay (Lead) |  | 2026-06-19 | 2026-07-09
1.1.3.24 | 4 | Foundation | Non-Filer & Sector Analytics | Sanjay (Lead) | API ¦ sector outlier | 100% | 100% | Completed | Delivered via Jira KAN-113 (Story) | 2026-06-19 | 2026-07-09 | 20d | 1.1.3.23FS | 2026-07-09 | 2026-06-19 | Sanjay (Lead) |  | 2026-06-19 | 2026-07-09
1.1.3.25 | 4 | Foundation | Team, Admin & Business Development | Jitendra P. (Dev) | API & Schema modification for authentication token to include ek & App_key into response | 100% | 100% | Completed | Delivered via Jira KAN-68 (Feature) | 2026-07-09 | 2026-07-21 | 12d | 1.1.3.24FS | 2026-07-21 | 2026-07-09 | Jitendra P. (Dev) |  | 2026-07-09 | 2026-07-21
1.1.3.26 | 4 | Foundation | Settlement Ledger Module | V. Kushwaha (Dev) | API <> Settlement ledger Task ¦ Level 3 API. Parameter Taxperiod & sf_id | 100% | 100% | Completed | Delivered via Jira KAN-60 (Feature) | 2026-07-13 | 2026-07-21 | 8d | 1.1.3.25FS | 2026-07-21 | 2026-07-13 | V. Kushwaha (Dev) |  | 2026-07-13 | 2026-07-21
1.1.3.27 | 4 | Foundation | Platform, DevOps & Core Utility | V. Kushwaha (Dev) | Dynamically add auth token on all the APIs' in utility service. | 100% | 100% | Completed | Delivered via Jira KAN-70 (Bug) | 2026-07-13 | 2026-07-21 | 8d | 1.1.3.26FS | 2026-07-21 | 2026-07-13 | V. Kushwaha (Dev) |  | 2026-07-13 | 2026-07-21
1.1.3.28 | 4 | Foundation | Feedback Portal | V. Kushwaha (Dev) | Task inspiration of Feedback portal (Kaushiki) from assam and design how we'll implement. | 100% | 100% | Completed | Delivered via Jira KAN-32 (Feature) | 2026-07-13 | 2026-07-21 | 8d | 1.1.3.27FS | 2026-07-21 | 2026-07-13 | V. Kushwaha (Dev) |  | 2026-07-13 | 2026-07-21
1.1.3.29 | 4 | Foundation | Team, Admin & Business Development | Ashish Gauttam (Dev) | Took interview of jaipur candidate Analystics /AI/ML named Sourabh Bohra | 100% | 100% | Completed | Delivered via Jira KAN-42 (Feature) | 2026-07-13 | 2026-07-21 | 8d | 1.1.3.28FS | 2026-07-21 | 2026-07-13 | Ashish Gauttam (Dev) |  | 2026-07-13 | 2026-07-21
1.1.3.30 | 4 | Foundation | Team, Admin & Business Development | V. Kushwaha (Dev) | Update Action plan ppt from pdf's (CM APR). Create excel sheet from the 2 .pdf's given | 100% | 100% | Completed | Delivered via Jira KAN-40 (Feature) | 2026-07-13 | 2026-07-21 | 8d | 1.1.3.29FS | 2026-07-21 | 2026-07-13 | V. Kushwaha (Dev) |  | 2026-07-13 | 2026-07-21
1.1.3.31 | 4 | Foundation | Team, Admin & Business Development | V. Kushwaha (Dev) | Take Queries from DB team (JITU & Lokesh) to insert into db. | 100% | 100% | Completed | Delivered via Jira KAN-76 (Story) | 2026-07-13 | 2026-07-21 | 8d | 1.1.3.30FS | 2026-07-21 | 2026-07-13 | V. Kushwaha (Dev) |  | 2026-07-13 | 2026-07-21
1.1.3.32 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | table 2 | 100% | 100% | Completed | Delivered via Jira KAN-47 (Subtask) | 2026-07-13 | 2026-07-28 | 15d | 1.1.3.31FS | 2026-07-28 | 2026-07-13 | Sanjay (Lead) |  | 2026-07-13 | 2026-07-28
1.1.3.33 | 4 | Foundation | Non-Filer & Sector Analytics | Jitendra P. (Dev) | API verification of Non-Filer in Dashboard backend | 100% | 100% | Completed | Delivered via Jira KAN-100 (Story) | 2026-07-13 | 2026-07-21 | 8d | 1.1.3.32FS | 2026-07-21 | 2026-07-13 | Jitendra P. (Dev) |  | 2026-07-13 | 2026-07-21
1.1.3.34 | 4 | Foundation | Non-Filer & Sector Analytics | Sanjay (Lead) | Procedure for getting NON-FILER Data (JITU JI) | 100% | 100% | Completed | Delivered via Jira KAN-57 (Feature) | 2026-07-13 | 2026-07-24 | 11d | 1.1.3.33FS | 2026-07-24 | 2026-07-13 | Sanjay (Lead) |  | 2026-07-13 | 2026-07-24
1.1.3.35 | 4 | Foundation | CRN / ETL Service | Sanjay (Lead) | Payment ETL as discuss with Jitu JI | 100% | 100% | Completed | Delivered via Jira KAN-74 (Story) | 2026-07-13 | 2026-07-28 | 15d | 1.1.3.34FS | 2026-07-28 | 2026-07-13 | Sanjay (Lead) |  | 2026-07-13 | 2026-07-28
1.1.3.36 | 4 | Foundation | Non-Filer & Sector Analytics | Sanjay (Lead) | Sector mapping for all GSTIN. Createlogic from Anant | 100% | 100% | Completed | Delivered via Jira KAN-73 (Story) | 2026-07-14 | 2026-07-21 | 7d | 1.1.3.35FS | 2026-07-21 | 2026-07-14 | Sanjay (Lead) |  | 2026-07-14 | 2026-07-21
1.1.3.37 | 4 | Foundation | DSS V2 / Decision Support System | V. Kushwaha (Dev) | Landing page redesign for DSS (Static vs Dynamic) | 100% | 100% | Completed | Delivered via Jira KAN-96 (Story) | 2026-07-14 | 2026-07-21 | 7d | 1.1.3.36FS | 2026-07-21 | 2026-07-14 | V. Kushwaha (Dev) |  | 2026-07-14 | 2026-07-21
1.1.3.38 | 4 | Foundation | Non-Filer & Sector Analytics | Sanjay (Lead) | Scheduler for calling automatically the NON-FILER Data procedure | 100% | 100% | Completed | Delivered via Jira KAN-58 (Feature) | 2026-07-15 | 2026-07-21 | 6d | 1.1.3.37FS | 2026-07-21 | 2026-07-15 | Sanjay (Lead) |  | 2026-07-15 | 2026-07-21
1.1.3.39 | 4 | Foundation | Registration & Alerts Data Sync (Java Utility) | Sanjay (Lead) | GET Data of registration (3 API) for java Utility (auto-sync). Also create scheduler to get the 3 steps running. | 100% | 100% | Completed | Delivered via Jira KAN-56 (Feature) | 2026-07-15 | 2026-07-21 | 6d | 1.1.3.38FS | 2026-07-21 | 2026-07-15 | Sanjay (Lead) |  | 2026-07-15 | 2026-07-21
1.1.3.40 | 4 | Foundation | DSS V2 / Decision Support System | Sanjay (Lead) | Static DSS, UI Screen for view, edit, delete and execute the stored queries. | 100% | 100% | Completed | Delivered via Jira KAN-95 (Story) | 2026-07-15 | 2026-07-21 | 6d | 1.1.3.39FS | 2026-07-21 | 2026-07-15 | Sanjay (Lead) |  | 2026-07-15 | 2026-07-21
1.1.3.41 | 4 | Foundation | Team, Admin & Business Development | V. Kushwaha (Dev) | Connect with dB team, to discuss on the table/data and sync system | 100% | 100% | Completed | Delivered via Jira KAN-23 (Feature) | 2026-07-16 | 2026-07-21 | 5d | 1.1.3.40FS | 2026-07-21 | 2026-07-16 | V. Kushwaha (Dev) |  | 2026-07-16 | 2026-07-21
1.1.3.42 | 4 | Foundation | Team, Admin & Business Development | V. Kushwaha (Dev) | Bug <> Trigger api sucessfully run, but in export API is giving null, as well as the count of sucess and failure is coming 0 each. | 100% | 100% | Completed | Delivered via Jira KAN-79 (Story) | 2026-07-16 | 2026-07-21 | 5d | 1.1.3.41FS | 2026-07-21 | 2026-07-16 | V. Kushwaha (Dev) |  | 2026-07-16 | 2026-07-21
1.1.3.43 | 4 | Foundation | Non-Filer & Sector Analytics | Sanjay (Lead) | Non filer <> Sector treemap, FE +BE | 100% | 100% | Completed | Delivered via Jira KAN-103 (Story) | 2026-07-16 | 2026-07-21 | 5d | 1.1.3.42FS | 2026-07-21 | 2026-07-16 | Sanjay (Lead) |  | 2026-07-16 | 2026-07-21
1.1.3.44 | 4 | Foundation | R3B / GSTR Reports & Reversal | Sanjay (Lead) | Create scheduler for calling the returns api , first do for GSTR3B. | 100% | 100% | Completed | Delivered via Jira KAN-59 (Feature) | 2026-07-16 | 2026-07-21 | 5d | 1.1.3.43FS | 2026-07-21 | 2026-07-16 | Sanjay (Lead) |  | 2026-07-16 | 2026-07-21
1.1.3.45 | 4 | Foundation | DSS V2 / Decision Support System | V. Kushwaha (Dev) | Create API's for static DSS query. 1) GET All, 2) GET ID, 3) PUT, 4) POST , 5) Exectute , 6) Download API. | 100% | 100% | Completed | Delivered via Jira KAN-77 (Story) | 2026-07-16 | 2026-07-21 | 5d | 1.1.3.44FS | 2026-07-21 | 2026-07-16 | V. Kushwaha (Dev) |  | 2026-07-16 | 2026-07-21
1.1.3.46 | 4 | Foundation | R3B / GSTR Reports & Reversal | Sanjay (Lead) | GSTR3B raw table to have optimized table and review with jitu ji | 100% | 100% | Completed | Delivered via Jira KAN-107 (Story) | 2026-07-21 | 2026-07-21 | 1d | 1.1.3.45FS | 2026-07-21 | 2026-07-21 | Sanjay (Lead) |  | 2026-07-21 | 2026-07-21
1.1.3.47 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Statis query bug: Create new Query from UI and execute was failing | 100% | 100% | Completed | Delivered via Jira KAN-108 (Story) | 2026-07-21 | 2026-07-21 | 1d | 1.1.3.46FS | 2026-07-21 | 2026-07-21 | Sanjay (Lead) |  | 2026-07-21 | 2026-07-21
1.1.3.48 | 4 | Foundation | Feedback Portal | Sanjay (Lead) | Backend API's for Feedback Portal | 100% | 100% | Completed | Delivered via Jira KAN-81 (Story) | 2026-07-21 | 2026-07-30 | 9d | 1.1.3.47FS | 2026-07-30 | 2026-07-21 | Sanjay (Lead) |  | 2026-07-21 | 2026-07-30
1.1.3.49 | 4 | Foundation | Non-Filer & Sector Analytics | Sanjay (Lead) | UI changes in Non-Filer to make it more intutive and detailed. | 100% | 100% | Completed | Delivered via Jira KAN-101 (Story) | 2026-07-21 | 2026-07-21 | 1d | 1.1.3.48FS | 2026-07-21 | 2026-07-21 | Sanjay (Lead) |  | 2026-07-21 | 2026-07-21
1.1.3.50 | 4 | Foundation | Settlement Ledger Module | Sanjay (Lead) | UI <> Settlement Ledger ¦ API Integration for 3rd level - Data Population in the table with dynamic columns along with pagination | 100% | 100% | Completed | Delivered via Jira KAN-85 (Feature) | 2026-07-21 | 2026-07-22 | 1d | 1.1.3.49FS | 2026-07-22 | 2026-07-21 | Sanjay (Lead) |  | 2026-07-21 | 2026-07-22
1.1.3.51 | 4 | Foundation | Feedback Portal | Sanjay (Lead) | UI <> Feedback Portal ¦ Admin Persona ¦ to attach excel file with specific type selection | 100% | 100% | Completed | Delivered via Jira KAN-98 (Task) | 2026-07-21 | 2026-07-21 | 1d | 1.1.3.50FS | 2026-07-21 | 2026-07-21 | Sanjay (Lead) |  | 2026-07-21 | 2026-07-21
1.1.3.52 | 4 | Foundation | Platform, DevOps & Core Utility | Sanjay (Lead) | UI <> Master Service for getting Zones, Circles and Wards | 100% | 100% | Completed | Delivered via Jira KAN-66 (Feature) | 2026-07-21 | 2026-07-23 | 2d | 1.1.3.51FS | 2026-07-23 | 2026-07-21 | Sanjay (Lead) |  | 2026-07-21 | 2026-07-23
1.1.3.53 | 4 | Foundation | Registration Manual Sync/Download | Ashish Gauttam (Dev) | Registraton manual sync API 4, 1) POST API, 2) GET all 3) Trigger API, 4) Export API | 100% | 100% | Completed | Delivered via Jira KAN-62 (Feature) | 2026-07-21 | 2026-07-21 | 1d | 1.1.3.52FS | 2026-07-21 | 2026-07-21 | Ashish Gauttam (Dev) |  | 2026-07-21 | 2026-07-21
1.1.3.54 | 4 | Foundation | Analytics Decision Hub | Sanjay (Lead) | UI <> Anlaytics Decision Hub ¦ API Integration for statistics data | 100% | 100% | Completed | Delivered via Jira KAN-84 (Feature) | 2026-07-21 | 2026-07-23 | 2d | 1.1.3.53FS | 2026-07-23 | 2026-07-21 | Sanjay (Lead) |  | 2026-07-21 | 2026-07-23
1.1.3.55 | 4 | Foundation | Settlement Ledger Module | Ashish Gauttam (Dev) | Core Utiltiy<> DB ¦ Schema addition for settlement ledger. | 100% | 100% | Completed | Delivered via Jira KAN-67 (Feature) | 2026-07-21 | 2026-07-21 | 1d | 1.1.3.54FS | 2026-07-21 | 2026-07-21 | Ashish Gauttam (Dev) |  | 2026-07-21 | 2026-07-21
1.1.3.56 | 4 | Foundation | Settlement Ledger Module | Ashish Gauttam (Dev) | Core Utiltiy <> API ¦ Settlement ledger get api | 100% | 100% | Completed | Delivered via Jira KAN-64 (Feature) | 2026-07-21 | 2026-07-21 | 1d | 1.1.3.55FS | 2026-07-21 | 2026-07-21 | Ashish Gauttam (Dev) |  | 2026-07-21 | 2026-07-21
1.1.3.57 | 4 | Foundation | Feedback Portal | V. Kushwaha (Dev) | UI <> Feedback portal Understanding | 100% | 100% | Completed | Delivered via Jira KAN-80 (Story) | 2026-07-21 | 2026-07-21 | 1d | 1.1.3.56FS | 2026-07-21 | 2026-07-21 | V. Kushwaha (Dev) |  | 2026-07-21 | 2026-07-21
1.1.3.58 | 4 | Foundation | Team, Admin & Business Development | V. Kushwaha (Dev) | UI for Target vs Achived | 100% | 100% | Completed | Delivered via Jira KAN-82 (Story) | 2026-07-21 | 2026-07-21 | 1d | 1.1.3.57FS | 2026-07-21 | 2026-07-21 | V. Kushwaha (Dev) |  | 2026-07-21 | 2026-07-21
1.1.3.59 | 4 | Foundation | Target vs Achieved Module | Ashish Gauttam (Dev) | UI <> Tafrget vs Achieved ¦ UI Screen to upload the taget vs achieved excel on moth basis and showing the previously uploaded list for Admin and Officer both | 100% | 100% | Completed | Delivered via Jira KAN-112 (Task) | 2026-07-22 | 2026-07-22 | 1d | 1.1.3.58FS | 2026-07-22 | 2026-07-22 | Ashish Gauttam (Dev) |  | 2026-07-22 | 2026-07-22
1.1.3.60 | 4 | Foundation | DSS V2 / Decision Support System | Ashish Gauttam (Dev) | UI <> Feeback Portal & DSS V2 ¦ UI design with mock data and DSS V2 filter updation | 100% | 100% | Completed | Delivered via Jira KAN-104 (Task) | 2026-07-22 | 2026-07-22 | 1d | 1.1.3.59FS | 2026-07-22 | 2026-07-22 | Ashish Gauttam (Dev) |  | 2026-07-22 | 2026-07-22
1.1.3.61 | 4 | Foundation | Target vs Achieved Module | Ashish Gauttam (Dev) | API <> Target Vs Achieved ¦ Admin API - Excel to be uploaded from admin as per current month | 100% | 100% | Completed | Delivered via Jira KAN-111 (Task) | 2026-07-22 | 2026-07-22 | 1d | 1.1.3.60FS | 2026-07-22 | 2026-07-22 | Ashish Gauttam (Dev) |  | 2026-07-22 | 2026-07-22
1.1.3.62 | 4 | Foundation | Analytics Decision Hub | Ashish Gauttam (Dev) | UI <> Analytics Decision Hub ¦ Addition of Filters (Months, Nature & Constitution of Business ) and Addition of 3 KPIs | 100% | 100% | Completed | Delivered via Jira KAN-99 (Task) | 2026-07-22 | 2026-07-22 | 1d | 1.1.3.61FS | 2026-07-22 | 2026-07-22 | Ashish Gauttam (Dev) |  | 2026-07-22 | 2026-07-22
1.1.3.63 | 4 | Foundation | Settlement Ledger Module | Ashish Gauttam (Dev) | UI <> Settle ledger task ¦ First level UI represending with mock data | 100% | 100% | Completed | Delivered via Jira KAN-51 (Feature) | 2026-07-22 | 2026-07-22 | 1d | 1.1.3.62FS | 2026-07-22 | 2026-07-22 | Ashish Gauttam (Dev) |  | 2026-07-22 | 2026-07-22
1.1.3.64 | 4 | Foundation | Feedback Portal | Ashish Gauttam (Dev) | UI <> Feedback Portal ¦ Feedback Portal for Admin showing previous uploaded lists along with new list updation | 100% | 100% | Completed | Delivered via Jira KAN-102 (Task) | 2026-07-22 | 2026-07-22 | 1d | 1.1.3.63FS | 2026-07-22 | 2026-07-22 | Ashish Gauttam (Dev) |  | 2026-07-22 | 2026-07-22
1.1.3.65 | 4 | Foundation | Settlement Ledger Module | Ashish Gauttam (Dev) | UI <> Settle ledger task ¦ First level UI represending with Real API | 100% | 100% | Completed | Delivered via Jira KAN-52 (Feature) | 2026-07-22 | 2026-07-22 | 1d | 1.1.3.64FS | 2026-07-22 | 2026-07-22 | Ashish Gauttam (Dev) |  | 2026-07-22 | 2026-07-22
1.1.3.66 | 4 | Foundation | Registration Manual Sync/Download | Ashish Gauttam (Dev) | UI <> Registration Manual Download ¦ Uploading excel and then getting the list of the uploaded excel with mocked data ¦ Have the action button to compute the data ¦ and dwonloading the file again | 100% | 100% | Completed | Delivered via Jira KAN-61 (Feature) | 2026-07-22 | 2026-07-22 | 1d | 1.1.3.65FS | 2026-07-22 | 2026-07-22 | Ashish Gauttam (Dev) |  | 2026-07-22 | 2026-07-22
1.1.3.67 | 4 | Foundation | Registration Manual Sync/Download | Ashish Gauttam (Dev) | UI <> API Integration on Registration Manual Download Page ¦ 4 APIs | 100% | 100% | Completed | Delivered via Jira KAN-69 (Feature) | 2026-07-22 | 2026-07-22 | 1d | 1.1.3.66FS | 2026-07-22 | 2026-07-22 | Ashish Gauttam (Dev) |  | 2026-07-22 | 2026-07-22
1.1.3.68 | 4 | Foundation | Platform, DevOps & Core Utility | Sanjay (Lead) | UI <> Dynamic Environment Configuration based on different Java Utilities | 100% | 100% | Completed | Delivered via Jira KAN-65 (Feature) | 2026-07-23 | 2026-07-23 | 1d | 1.1.3.67FS | 2026-07-23 | 2026-07-23 | Sanjay (Lead) |  | 2026-07-23 | 2026-07-23
1.1.3.69 | 4 | Foundation | DSS V2 / Decision Support System | Sanjay (Lead) | UI <> Decision Support System ¦ Analytics Decision Hub ¦ with filters and dynamic table with mocked data . Along with export CSV. | 100% | 100% | Completed | Delivered via Jira KAN-55 (Feature) | 2026-07-23 | 2026-07-23 | 1d | 1.1.3.68FS | 2026-07-23 | 2026-07-23 | Sanjay (Lead) |  | 2026-07-23 | 2026-07-23
1.1.3.70 | 4 | Foundation | Registration & Alerts Data Sync (Java Utility) | Jitendra P. (Dev) | Get data in the "gst_api_registration" schema on getting alerts data. (JITU JI) | 100% | 100% | Completed | Delivered via Jira KAN-49 (Feature) | 2026-07-23 | 2026-07-23 | 1d | 1.1.3.69FS | 2026-07-23 | 2026-07-23 | Jitendra P. (Dev) |  | 2026-07-23 | 2026-07-23
1.1.3.71 | 4 | Foundation | Team, Admin & Business Development | V. Kushwaha (Dev) | FE ¦ Addition of toggle to switch between mock data vs real API call | 100% | 100% | Completed | Delivered via Jira KAN-50 (Feature) | 2026-07-24 | 2026-07-28 | 4d | 1.1.3.70FS | 2026-07-28 | 2026-07-24 | V. Kushwaha (Dev) |  | 2026-07-24 | 2026-07-28
1.1.3.72 | 4 | Foundation | Third-Party & DISCOM Integration | V. Kushwaha (Dev) | GSTIN <. Knumber get data of 200 GSTINs' from discom API's | 100% | 100% | Completed | Delivered via Jira KAN-78 (Story) | 2026-07-24 | 2026-07-24 | 1d | 1.1.3.71FS | 2026-07-24 | 2026-07-24 | V. Kushwaha (Dev) |  | 2026-07-24 | 2026-07-24
1.1.3.73 | 4 | Foundation | Settlement Ledger Module | Sanjay (Lead) | UI <> Settle Ledger ¦ Third Level UI with mocked Data | 100% | 100% | Completed | Delivered via Jira KAN-54 (Feature) | 2026-07-24 | 2026-07-24 | 1d | 1.1.3.72FS | 2026-07-24 | 2026-07-24 | Sanjay (Lead) |  | 2026-07-24 | 2026-07-24
1.1.3.74 | 4 | Foundation | Third-Party & DISCOM Integration | Sanjay (Lead) | API <> Third-Party API Utility ¦ Created an API to fetch GSTIN data from DISCOM APIs. | 100% | 100% | Completed | Delivered via Jira KAN-88 (Feature) | 2026-07-24 | 2026-07-30 | 6d | 1.1.3.73FS | 2026-07-30 | 2026-07-24 | Sanjay (Lead) |  | 2026-07-24 | 2026-07-30
1.1.3.75 | 4 | Foundation | Settlement Ledger Module | V. Kushwaha (Dev) | API <> Settle ledger task ¦ First level API (time & state code) from dB | 100% | 100% | Completed | Delivered via Jira KAN-53 (Feature) | 2026-07-28 | 2026-07-28 | 1d | 1.1.3.74FS | 2026-07-28 | 2026-07-28 | V. Kushwaha (Dev) |  | 2026-07-28 | 2026-07-28
1.1.3.76 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Table 1 | 100% | 100% | Completed | Delivered via Jira KAN-46 (Subtask) | 2026-07-28 | 2026-07-28 | 1d | 1.1.3.75FS | 2026-07-28 | 2026-07-28 | Sanjay (Lead) |  | 2026-07-28 | 2026-07-28
1.1.3.77 | 4 | Foundation | DSS V2 / Decision Support System | V. Kushwaha (Dev) | Design dB Schema for Static DSS query maker. | 100% | 100% | Completed | Delivered via Jira KAN-75 (Story) | 2026-07-28 | 2026-07-28 | 1d | 1.1.3.76FS | 2026-07-28 | 2026-07-28 | V. Kushwaha (Dev) |  | 2026-07-28 | 2026-07-28
1.1.3.78 | 4 | Foundation | Target vs Achieved Module | Sanjay (Lead) | Backend API's for Target vs Achieved | 100% | 100% | Completed | Delivered via Jira KAN-83 (Story) | 2026-07-30 | 2026-07-30 | 1d | 1.1.3.77FS | 2026-07-30 | 2026-07-30 | Sanjay (Lead) |  | 2026-07-30 | 2026-07-30
1.1.3.79 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Prepared the API requirements Excel sheet for Mining Data. | 100% | 100% | Completed | Delivered via Jira KAN-86 (Task) | 2026-07-30 | 2026-07-30 | 1d | 1.1.3.78FS | 2026-07-30 | 2026-07-30 | Sanjay (Lead) |  | 2026-07-30 | 2026-07-30
1.1.3.80 | 4 | Foundation | Team, Admin & Business Development | Sanjay (Lead) | Scraped GSTIN data using Satyendra Ji's scraping tool. | 100% | 100% | Completed | Delivered via Jira KAN-87 (Business Development) | 2026-07-30 | 2026-07-30 | 1d | 1.1.3.79FS | 2026-07-30 | 2026-07-30 | Sanjay (Lead) |  | 2026-07-30 | 2026-07-30
1.1.3.81 | 4 | Foundation | DSS V2 / Decision Support System | Sanjay (Lead) | API <> DSS V2 ¦ Created a Ward List JSON API for zone-wise data. | 100% | 100% | Completed | Delivered via Jira KAN-89 (Feature) | 2026-07-30 | 2026-07-30 | 1d | 1.1.3.80FS | 2026-07-30 | 2026-07-30 | Sanjay (Lead) |  | 2026-07-30 | 2026-07-30
1.1.3.82 | 4 | Foundation | Settlement Ledger Module | Sanjay (Lead) | API <> Settle Ledger Task ¦ Modified the First-Level API. | 100% | 100% | Completed | Delivered via Jira KAN-90 (Feature) | 2026-07-30 | 2026-07-30 | 1d | 1.1.3.81FS | 2026-07-30 | 2026-07-30 | Sanjay (Lead) |  | 2026-07-30 | 2026-07-30
1.1.3.83 | 4 | Foundation | Settlement Ledger Module | Jitendra P. (Dev) | API <> Settle Ledger Task ¦ Modified ythe Third-Level API. | 100% | 100% | Completed | Delivered via Jira KAN-91 (Feature) | 2026-07-30 | 2026-07-30 | 1d | 1.1.3.82FS | 2026-07-30 | 2026-07-30 | Jitendra P. (Dev) |  | 2026-07-30 | 2026-07-30
1.2 | 2 |  |  |  | Phase 2 — Current Sprint (Aug 2026) |  | 43.36% |  |  | 2026-06-24 | 2026-08-31 | 68d | [5 empty] | 2026-06-24 | 2026-08-31
1.2.1 | 3 |  |  |  | Development Team |  | 29.67% |  |  | 2026-07-21 | 2026-08-31 | 41d | [5 empty] | 2026-07-21 | 2026-08-31
1.2.1.1 | 4 | Current Sprint | ITMS — Development | Audit MCM | Audit MCM Module | 100% | 50% | In Progress | 1. MIS and Case Tracking | 2026-07-21 | 2026-08-05 | 15d |  |  |  | Audit MCM |  | 2026-07-21 | 2026-08-05
1.2.1.1.1 | 5 | Current Sprint | ITMS — Development | Development Team | DAR View, Agenda Creation & MCM review | 100% | 0% | Not Started |  | 2026-07-21 | 2026-07-21 | 15d |  |  |  | Development Team |  | 2026-07-21 | 2026-07-21
1.2.1.2 | 4 | Current Sprint | ITMS — Development | BIU | Feedback Portal | 100% | 75% | Testing In Progress | 1. Information Tool Tip | 2026-08-09 | 2026-08-15 | 6d | 1.2.1.1FS |  |  | BIU |  | 2026-08-09 | 2026-08-15
1.2.1.2.1 | 5 | Current Sprint | ITMS — Development | Development Team | Remarks standardisation in dropdown | 100% | 0% | Not Started |  | 2026-08-09 | 2026-08-09 | 1d |  |  |  | Development Team |  | 2026-08-09 | 2026-08-09
1.2.1.2.2 | 5 | Current Sprint | ITMS — Development | Development Team | Remarks capture time stamp | 100% | 0% | Not Started |  | 2026-08-09 | 2026-08-10 | 1d | 1.2.1.2.1FS |  |  | Development Team |  | 2026-08-09 | 2026-08-10
1.2.1.2.3 | 5 | Current Sprint | ITMS — Development | Development Team | Randomization - Closed Cases to be reviewed by officers for feedback | 100% | 0% | Not Started |  | 2026-08-10 | 2026-08-11 | 1d | 1.2.1.2.2FS |  |  | Development Team |  | 2026-08-10 | 2026-08-11
1.2.1.2.4 | 5 | Current Sprint | ITMS — Development | Development Team | Officer name who is adding the remark to the cases | 100% | 0% | Not Started |  | 2026-08-11 | 2026-08-12 | 1d | 1.2.1.2.3FS |  |  | Development Team |  | 2026-08-11 | 2026-08-12
1.2.1.2.5 | 5 | Current Sprint | ITMS — Development | Development Team | Provide ARN number for the case initiated. | 100% | 0% | Not Started |  | 2026-08-12 | 2026-08-13 | 1d | 1.2.1.2.4FS |  |  | Development Team |  | 2026-08-12 | 2026-08-13
1.2.1.2.6 | 5 | Current Sprint | ITMS — Development | Development Team | Reviewing Officers case allocation through Randomisation | 100% | 0% | Not Started |  | 2026-08-13 | 2026-08-14 | 1d | 1.2.1.2.5FS |  |  | Development Team |  | 2026-08-13 | 2026-08-14
1.2.1.2.7 | 5 | Current Sprint | ITMS — Development | Development Team | DCs can edit the feedback report. | 100% | 0% | Not Started |  | 2026-08-14 | 2026-08-15 | 1d | 1.2.1.2.6FS |  |  | Development Team |  | 2026-08-14 | 2026-08-15
1.2.1.2.8 | 5 | Current Sprint | ITMS — Development | Development Team | Individual case supporting document upload. | 100% | 0% | Not Started |  | 2026-08-14 | 2026-08-15 | 1d | 1.2.1.2.7FS |  |  | Development Team |  | 2026-08-14 | 2026-08-15
1.2.1.3 | 4 | Current Sprint | ITMS — Development | BIU | WhatsApp Integration | 100% | 50% | In Progress | Daily 10 am Message | 2026-08-10 | 2026-08-25 | 15d | 1.2.1.2FS |  |  | BIU |  | 2026-08-10 | 2026-08-25
1.2.1.4 | 4 | Current Sprint | ITMS — Development | BIU | Transport Data Integration | 100% | 20% | Blocked / Awaiting Input | 1 Month Data Shared by Transport Dept. | 2026-08-13 | 2026-08-28 | 15d | 1.2.1.3FS |  |  | BIU |  | 2026-08-13 | 2026-08-28
1.2.1.5 | 4 | Current Sprint | ITMS — Development | Enforcement | Enforcement Officer Feedback | 100% | 80% | In Progress | 1. Dashboard to upload Enforcement cases and circulars | 2026-08-19 | 2026-08-25 | 6d | 1.2.1.4FS |  |  | Enforcement |  | 2026-08-19 | 2026-08-25
1.2.1.5.1 | 5 | Current Sprint | ITMS — Development | Development Team | Feedback from Enforcement Officers | 100% | 0% | Not Started |  | 2026-08-19 | 2026-08-19 | 2d |  |  |  | Development Team |  | 2026-08-19 | 2026-08-19
1.2.1.5.2 | 5 | Current Sprint | ITMS — Development | Development Team | MIS for Case Tracking | 100% | 0% | Not Started |  | 2026-08-19 | 2026-08-21 | 2d | 1.2.1.5.1FS |  |  | Development Team |  | 2026-08-19 | 2026-08-21
1.2.1.5.3 | 5 | Current Sprint | ITMS — Development | Development Team | Persona Creation - CCT, ACCT, DC Enforcement, Enforcement Officers | 100% | 0% | Not Started |  | 2026-08-21 | 2026-08-23 | 2d | 1.2.1.5.2FS |  |  | Development Team |  | 2026-08-21 | 2026-08-23
1.2.1.6 | 4 | Current Sprint | ITMS — Development | VAT Committee | VAT Demand & Recovery | 100% | 0% | Not Started |  | 2026-08-25 | 2026-08-31 | 6d | 1.2.1.5FS |  |  | VAT Committee |  | 2026-08-25 | 2026-08-31
1.2.2 | 3 |  |  |  | Analytics Team |  | 40.45% |  |  | 2026-06-24 | 2026-08-31 | 68d | [5 empty] | 2026-06-24 | 2026-08-31
1.2.2.1 | 4 | Current Sprint | ITMS — Analytics | RK+SL+ SG | Sector Updation for top 1 lakh | 100% | 100% | Completed | Sector mapping to be updated based on inputs from field formations along with HSN Mapping of GSTR1 | 2026-06-24 | 2026-08-07 | 44d |  |  |  | RK+SL+ SG |  | 2026-06-24 | 2026-08-07
| 4 | Current Sprint | ITMS — Analytics | Analytics Team | CYBER FRAUD -I cyber fraud vs bank account details analysis | 100% | 100% | Completed | Shared on Feedback Portal
| 4 | Current Sprint | ITMS — Analytics | SG+AG | Electrictity report "New usecase to be developed using Electricity data(api) for the new tax payers (post feb 2025 )" | 100% | 100% | Completed | Manufacturer to be added, high turnover low bill. will reverify. Report downloaded & extracting consumption Link TOP 18 CASES Link Shared with the BIU team, They are preparing the note.
| 4 | Current Sprint | ITMS — Analytics | YK/DP | AI-based P&L doc processing for FY 2023-24 | 100% | 100% | Completed | PPT Prepared Top 5 cases has been created. 1) Mining 2) LEGAL & Professional 3) Freight
1.2.2.2 | 4 | Current Sprint | ITMS — Analytics | DP | Rate structure analysis on coconut products | 100% | 100% | Completed | HSN name: fresh/tender coconut products. Check outward support, | 2026-07-21 | 2026-08-13 | 23d | 1.2.2.1FS |  |  | DP |  | 2026-07-21 | 2026-08-13
1.2.2.3 | 4 | Current Sprint | ITMS — Analytics | DP | RCM Liability on permit fee based on the data from Mining Dept. | 100% | 40% | In Progress | - Identification of permit fee deposited by the dealer against STP in mining department | 2026-07-29 | 2026-08-13 | 15d | 1.2.2.2FS |  |  | DP |  | 2026-07-29 | 2026-08-13
1.2.2.4 | 4 | Current Sprint | ITMS — Analytics | DP+AJ | GTA to GTA 9966 HSN percentage | 100% | 100% | Completed | 12 % dealing, names to be identified | 2026-07-29 | 2026-08-04 | 6d | 1.2.2.3FS | 2026-08-04 | 2026-07-29 | DP+AJ |  | 2026-07-29 | 2026-08-04
1.2.2.6 | 4 | Current Sprint | ITMS — Analytics | AJ | New GST Registration taxpayer list with very high Turnover | 100% | 100% | Completed | refine 35 cbt tp high TO | 2026-07-30 | 2026-08-05 | 6d | 1.2.2.5FS | 2026-08-05 | 2026-07-30 | AJ |  | 2026-07-30 | 2026-08-05
1.2.2.8 | 4 | Current Sprint | ITMS — Analytics | SL | aerated drinks combo ITC reversal | 100% | 0% | Not Started | aerated drinks combo ITC reversal | 2026-07-31 | 2026-08-06 | 6d | 1.2.2.7FS |  |  | SL |  | 2026-07-31 | 2026-08-06
1.2.2.9 | 4 | Current Sprint | ITMS — Analytics | DP | IBM minerals value avg rate comparison with EWB data on major minerals like Feldspar | 100% | 100% | Completed | IBM minerals value taken from data published on 17th July 2026 | 2026-07-31 | 2026-08-06 | 6d | 1.2.2.8FS |  |  | DP |  | 2026-07-31 | 2026-08-06
1.2.2.10 | 4 | Current Sprint | ITMS — Analytics | SL | amazon business account - GST Rate and Vendor Name Extraction | 100% | 20% | In Progress | amazon business | 2026-08-01 | 2026-08-07 | 6d | 1.2.2.9FS |  |  | SL |  | 2026-08-01 | 2026-08-07
1.2.2.11 | 4 | Current Sprint | ITMS — Analytics | LP | Epoxy Resin Taxpayers HSN 2517 and not dealing in HSN 6502 | 100% | 100% | Completed | epoxy resin | 2026-08-02 | 2026-08-08 | 6d | 1.2.2.10FS | 2026-08-08 | 2026-08-02 | LP |  | 2026-08-02 | 2026-08-08
1.2.2.13 | 4 | Current Sprint | ITMS — Analytics | Analytics Team | physical verification app | 100% | 0% | Not Started | physical verification app Feasibility Study | 2026-08-02 | 2026-08-08 | 6d | 1.2.2.12FS |  |  | Analytics Team |  | 2026-08-02 | 2026-08-08
1.2.2.15 | 4 | Current Sprint | ITMS — Analytics | SL | Integration with Railways Cargo data with EWB comparison | 100% | 10% | In Progress | Railway FOIS integration with GST Note v1.docx Note shared | 2026-08-04 | 2026-08-10 | 6d | 1.2.2.14FS | 2026-08-10 | 2026-08-04 | SL |  | 2026-08-04 | 2026-08-10
1.2.2.16 | 4 | Current Sprint | ITMS — Analytics | SL | restaurants and hotels @5% - ITC reversals | 100% | 100% | Completed | restaurants and hotels @5% - ITC reversals | 2026-08-04 | 2026-08-10 | 6d | 1.2.2.15FS |  |  | SL |  | 2026-08-04 | 2026-08-10
1.2.2.17 | 4 | Current Sprint | ITMS — Analytics | LP | Inward Sugar HSN taxpayers for Survey | 100% | 100% | Completed | Inward Sugar HSN taxpayers | 2026-08-04 | 2026-08-10 | 6d | 1.2.2.16FS | 2026-08-10 | 2026-08-04 | LP |  | 2026-08-04 | 2026-08-10
1.2.2.18 | 4 | Current Sprint | ITMS — Analytics | DP | Reconcile Goods Transport Agency (GTA) | 100% | 100% | Completed | Shared with Sohan Sir with revelant reason | 2026-08-05 | 2026-08-07 | 2d | 1.2.2.17FS | 2026-08-07 | 2026-08-05 | DP |  | 2026-08-05 | 2026-08-07
1.2.2.19 | 4 | Current Sprint | ITMS — Analytics | YK/DP/AJ | Risk Profiling of Taxpayers based on Parameters and Show the same on ITMS Portal | 100% | 100% | Completed | Under Review | 2026-08-09 | 2026-08-15 | 6d | 1.2.2.18FS |  |  | YK/DP/AJ |  | 2026-08-09 | 2026-08-15
1.2.2.20 | 4 | Current Sprint | ITMS — Analytics | AJ |  | 100% | 100% | Completed | Virtual Hearing List | 2026-08-10 | 2026-08-16 | 6d | 1.2.2.19FS |  |  | AJ |  | 2026-08-10 | 2026-08-16
1.2.2.23 | 4 | Current Sprint | ITMS — Analytics | JP | Dealers's GSTR-3B liability set-off trend where net ITC available is negative | 100% | 10% | In Progress | Data Computed | 2026-08-10 | 2026-08-16 | 6d | 1.2.2.22FS |  |  | JP |  | 2026-08-10 | 2026-08-16
1.2.2.25 | 4 | Current Sprint | ITMS — Analytics | LP | Refund Analysis - Detecting outliers based on Sector and Taxpayer Type | 100% | 0% | Not Started | Get RGD-01, RFD-04 and RFD-06 for the period of April-2025 to July-2026 (With Refund Catory gstin wise) | 2026-08-10 | 2026-08-16 | 6d | 1.2.2.24FS |  |  | LP |  | 2026-08-10 | 2026-08-16
1.2.2.27 | 4 | Current Sprint | ITMS — Analytics | AJ | URP Sale in the districts Jhumjhunu, Kishangarh, Jalore | 100% | 100% | Completed | URP Sale in the districts Jhumjhunu, Kishangarh, Jalore | 2026-08-10 | 2026-08-16 | 6d | 1.2.2.26FS |  |  | AJ |  | 2026-08-10 | 2026-08-16
1.2.2.28 | 4 | Current Sprint | ITMS — Analytics | AJ | "Eway bill vs gstr (B2b and b2c) parameter 5 of scuntiny" | 100% | 100% | Completed | eway bill data extracted ,3B data to be incorporated. (Based on DGGI Report) | 2026-08-11 | 2026-08-17 | 6d | 1.2.2.27FS |  |  | AJ |  | 2026-08-11 | 2026-08-17
1.2.2.29 | 4 | Current Sprint | ITMS — Analytics | JP/LP | GSTR1 HSN Summary Mismatch Correction (FY25-26) | 100% | 100% | Completed | Discussion with DOITC team done on 14,July,2026 Mail triggered twice for reconciliation | 2026-08-25 | 2026-08-31 | 6d | 1.2.2.28FS |  |  | JP/LP |  | 2026-08-25 | 2026-08-31
1.2.3 | 3 |  |  |  | RAID (Nexus) Development |  | 74.19% |  |  | 2026-07-21 | 2026-08-31 | 40d | [5 empty] | 2026-07-21 | 2026-08-31
1.2.3.1 | 4 | Current Sprint | DSS V2 / Decision Support System | V. Kushwaha (Dev) | API <> DSS V2 ¦ Developed a Statistics API based on the provided filters. | 100% | 100% | Completed | Delivered via Jira KAN-93 (Feature) | 2026-07-21 | 2026-08-07 | 17d |  | 2026-08-07 | 2026-07-21 | V. Kushwaha (Dev) |  | 2026-07-21 | 2026-08-07
1.2.3.2 | 4 | Current Sprint | DSS V2 / Decision Support System | V. Kushwaha (Dev) | API <> DSS V2 ¦ Created a paginated GSTIN data API based on the provided filters. | 100% | 100% | Completed | Delivered via Jira KAN-94 (Feature) | 2026-07-21 | 2026-08-07 | 17d | 1.2.3.1FS | 2026-08-07 | 2026-07-21 | V. Kushwaha (Dev) |  | 2026-07-21 | 2026-08-07
1.2.3.3 | 4 | Current Sprint | DSS V2 / Decision Support System | V. Kushwaha (Dev) | API <> DSS V2 ¦ Developed a Filter List API to display filters on the DSS page. | 100% | 100% | Completed | Delivered via Jira KAN-92 (Feature) | 2026-08-03 | 2026-08-03 | 1d | 1.2.3.2FS | 2026-08-03 | 2026-08-03 | V. Kushwaha (Dev) |  | 2026-08-03 | 2026-08-03
1.2.3.4 | 4 | Current Sprint | P&L Analysis / My Profile / CBT | V. Kushwaha (Dev) | Get Application requests- cancellation submit, api call to get callellation reason for CBT | 100% | 100% | Completed | Delivered via Jira KAN-97 (Story) | 2026-08-03 | 2026-08-07 | 4d | 1.2.3.3FS | 2026-08-07 | 2026-08-03 | V. Kushwaha (Dev) |  | 2026-08-03 | 2026-08-07
1.2.3.5 | 4 | Current Sprint | CRN / ETL Service | Sanjay (Lead) | CRN List api in ETL service | 100% | 100% | Completed | Delivered via Jira KAN-105 (Story) | 2026-08-12 | 2026-08-12 | 1d | 1.2.3.4FS | 2026-08-12 | 2026-08-12 | Sanjay (Lead) |  | 2026-08-12 | 2026-08-12
1.2.3.6 | 4 | Current Sprint | CRN / ETL Service | Sanjay (Lead) | CRN details data api, in ETL service | 100% | 100% | Completed | Delivered via Jira KAN-106 (Story) | 2026-08-12 | 2026-08-12 | 1d | 1.2.3.5FS | 2026-08-12 | 2026-08-12 | Sanjay (Lead) |  | 2026-08-12 | 2026-08-12
1.2.3.7 | 4 | Current Sprint | R3B / GSTR Reports & Reversal | Sanjay (Lead) | Download gst9c Document api,from .net to Java | 100% | 100% | Completed | Delivered via Jira KAN-109 (Story) | 2026-08-12 | 2026-08-12 | 1d | 1.2.3.6FS | 2026-08-12 | 2026-08-12 | Sanjay (Lead) |  | 2026-08-12 | 2026-08-12
1.2.3.8 | 4 | Current Sprint | Non-Filer & Sector Analytics | Sanjay (Lead) | Sector summary data, to eb preprated, and provide readymade functions | 100% | 100% | Completed | Delivered via Jira KAN-110 (Story) | 2026-08-12 | 2026-08-12 | 1d | 1.2.3.7FS | 2026-08-12 | 2026-08-12 | Sanjay (Lead) |  | 2026-08-12 | 2026-08-12
1.2.3.9 | 4 | Current Sprint | P&L Analysis / My Profile / CBT | V. Kushwaha (Dev) | UI <> P-L Analysis ¦ GSTIN list population in tabular format from mocked data and showing the related PDF in the popup | 100% | 100% | Completed | Delivered via Jira KAN-117 (Task) | 2026-08-12 | 2026-08-12 | 1d | 1.2.3.8FS | 2026-08-12 | 2026-08-12 | V. Kushwaha (Dev) |  | 2026-08-12 | 2026-08-12
1.2.3.10 | 4 | Current Sprint | P&L Analysis / My Profile / CBT | V. Kushwaha (Dev) | UI <> My Profile ¦ Updation of UI in the detail page of the selected GSTIN, to show the cards based on the selected tabs | 100% | 100% | Completed | Delivered via Jira KAN-118 (Task) | 2026-08-12 | 2026-08-12 | 1d | 1.2.3.9FS | 2026-08-12 | 2026-08-12 | V. Kushwaha (Dev) |  | 2026-08-12 | 2026-08-12
1.2.3.11 | 4 | Current Sprint | DSS V2 / Decision Support System | V. Kushwaha (Dev) | UI <> DSS V2 ¦ Added cancellation date filters in the filter options to fetch the data based on selected dates. | 100% | 100% | Completed | Delivered via Jira KAN-119 (Task) | 2026-08-12 | 2026-08-12 | 1d | 1.2.3.10FS | 2026-08-12 | 2026-08-12 | V. Kushwaha (Dev) |  | 2026-08-12 | 2026-08-12
1.2.3.12 | 4 | Current Sprint | Platform, DevOps & Core Utility | V. Kushwaha (Dev) | Regression testing of all Phase-1 modules (Settlement Ledger, DSS V2, Feedback Portal, Registration Sync) | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-08-13 | 2026-08-23 | 10d | 1.2.3.11FS |  |  | V. Kushwaha (Dev) |  | 2026-08-13 | 2026-08-23
1.2.3.13 | 4 | Current Sprint | Platform, DevOps & Core Utility | Sanjay (Lead) | Sprint retrospective & Phase-2 backlog grooming | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-08-24 | 2026-08-27 | 3d | 1.2.3.12FS |  |  | Sanjay (Lead) |  | 2026-08-24 | 2026-08-27
1.2.3.14 | 4 | Current Sprint | Third-Party & DISCOM Integration | V. Kushwaha (Dev) | Complete remaining DISCOM / third-party API error-handling & retry logic | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-08-28 | 2026-08-31 | 3d | 1.2.3.13FS |  |  | V. Kushwaha (Dev) |  | 2026-08-28 | 2026-08-31
1.3 | 2 |  |  |  | Phase 3 — Next Quarter (Sep–Dec 2026) |  | 7.143% |  |  | 2026-08-27 | 2026-12-20 | 115d | [5 empty] | 2026-08-27 | 2026-12-20
1.3.1 | 3 |  |  |  | Development Team |  | 3.846% |  |  | 2026-08-27 | 2026-11-30 | 95d | [5 empty] | 2026-08-27 | 2026-11-30
1.3.1.1 | 4 | Next Quarter | ITMS — Development | BIU | DISCOM Data Integration | 100% | 0% | Not Started | Discussions with DISCOM, yet to start | 2026-08-27 | 2026-09-11 | 15d |  |  |  | BIU |  | 2026-08-27 | 2026-09-11
1.3.1.2 | 4 | Next Quarter | ITMS — Development | Audit | Audit Selection | 100% | 0% | Not Started |  | 2026-08-31 | 2026-09-15 | 15d | 1.3.1.1FS |  |  | Audit |  | 2026-08-31 | 2026-09-15
1.3.1.3 | 4 | Next Quarter | ITMS — Development | BIU | IFMS Data Integration | 100% | 20% | Blocked / Awaiting Input | Pending with IFMS | 2026-09-13 | 2026-09-28 | 15d | 1.3.1.2FS |  |  | BIU |  | 2026-09-13 | 2026-09-28
1.3.1.4 | 4 | Next Quarter | ITMS — Development | BIU | SAS Dashboard Migration to ITMS | 100% | 0% | Not Started | Dashboard and Data to be identified | 2026-09-30 | 2026-10-15 | 15d | 1.3.1.3FS |  |  | BIU |  | 2026-09-30 | 2026-10-15
1.3.1.5 | 4 | Next Quarter | ITMS — Development | VAT Committee | Scrutiny and Assessment | 100% | 0% | Not Started |  | 2026-10-09 | 2026-10-15 | 6d | 1.3.1.4FS |  |  | VAT Committee |  | 2026-10-09 | 2026-10-15
1.3.1.6 | 4 | Next Quarter | ITMS — Development | VAT Committee | Refund | 100% | 0% | Not Started |  | 2026-11-09 | 2026-11-15 | 6d | 1.3.1.5FS |  |  | VAT Committee |  | 2026-11-09 | 2026-11-15
1.3.1.7 | 4 | Next Quarter | ITMS — Development | VAT Committee | Appeal & Revision | 100% | 0% | Not Started |  | 2026-11-24 | 2026-11-30 | 6d | 1.3.1.6FS |  |  | VAT Committee |  | 2026-11-24 | 2026-11-30
1.3.2 | 3 |  |  |  | Analytics Team |  | 78% |  |  | 2026-11-15 | 2026-11-30 | 15d | [5 empty] | 2026-11-15 | 2026-11-30
1.3.2.1 | 4 | Next Quarter | ITMS — Analytics | MC | VAT Development functional and Testing support | 100% | 40% | In Progress | Ongoing activity | 2026-11-15 | 2026-11-30 | 15d |  |  |  | MC |  | 2026-11-15 | 2026-11-30
1.3.2.2 | 4 | Next Quarter | ITMS — Analytics | ARJ | Audit Module | 100% | 40% | In Progress | Checklist and threshold values requested from AUDIT Team. mail shared on 22 June | 2026-11-15 | 2026-11-30 | 15d | 1.3.2.1FS |  |  | ARJ |  | 2026-11-15 | 2026-11-30
1.3.3 | 3 |  |  |  | RAID (Nexus) Development |  | 0% |  |  | 2026-09-01 | 2026-12-20 | 110d | [5 empty] | 2026-09-01 | 2026-12-20
1.3.3.1 | 4 | Next Quarter | Platform, DevOps & Core Utility | Ashish Gauttam (Dev) | Role-based access control (RBAC) design & implementation across modules | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-09-01 | 2026-09-16 | 15d |  |  |  | Ashish Gauttam (Dev) |  | 2026-09-01 | 2026-09-16
1.3.3.2 | 4 | Next Quarter | Platform, DevOps & Core Utility | Jitendra P. (Dev) | Security review (auth, API key handling, input validation) | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-09-17 | 2026-09-27 | 10d | 1.3.3.1FS |  |  | Jitendra P. (Dev) |  | 2026-09-17 | 2026-09-27
1.3.3.3 | 4 | Next Quarter | Platform, DevOps & Core Utility | V. Kushwaha (Dev) | Performance optimization & load testing (Postgres query tuning, React bundle size) | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-09-28 | 2026-10-10 | 12d | 1.3.3.2FS |  |  | V. Kushwaha (Dev) |  | 2026-09-28 | 2026-10-10
1.3.3.4 | 4 | Next Quarter | Analytics Decision Hub | Ashish Gauttam (Dev) | Analytics Decision Hub V2 — additional KPIs & drill-down views | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-10-11 | 2026-10-26 | 15d | 1.3.3.3FS |  |  | Ashish Gauttam (Dev) |  | 2026-10-11 | 2026-10-26
1.3.3.5 | 4 | Next Quarter | DSS V2 / Decision Support System | V. Kushwaha (Dev) | DSS V2 — saved-query sharing & scheduled report export | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-10-27 | 2026-11-08 | 12d | 1.3.3.4FS |  |  | V. Kushwaha (Dev) |  | 2026-10-27 | 2026-11-08
1.3.3.6 | 4 | Next Quarter | Feedback Portal | Ashish Gauttam (Dev) | Feedback Portal — officer-side mobile-responsive UI | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-11-09 | 2026-11-19 | 10d | 1.3.3.5FS |  |  | Ashish Gauttam (Dev) |  | 2026-11-09 | 2026-11-19
1.3.3.7 | 4 | Next Quarter | Platform, DevOps & Core Utility | Sanjay (Lead) | User Acceptance Testing (UAT) with CTD zonal officers | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-11-20 | 2026-11-30 | 10d | 1.3.3.6FS |  |  | Sanjay (Lead) |  | 2026-11-20 | 2026-11-30
1.3.3.8 | 4 | Next Quarter | Platform, DevOps & Core Utility | Jitendra P. (Dev) | UAT feedback triage & fixes | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-12-01 | 2026-12-11 | 10d | 1.3.3.7FS |  |  | Jitendra P. (Dev) |  | 2026-12-01 | 2026-12-11
1.3.3.9 | 4 | Next Quarter | Platform, DevOps & Core Utility | Jitendra P. (Dev) | API & user documentation, developer handbook | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2026-12-12 | 2026-12-20 | 8d | 1.3.3.8FS |  |  | Jitendra P. (Dev) |  | 2026-12-12 | 2026-12-20
1.4 | 2 |  |  |  | Phase 4 — 2027 Roadmap (Jan–Apr 2027) |  | 0% |  |  | 2027-01-05 | 2027-04-15 | 100d | [5 empty] | 2027-01-05 | 2027-04-15
1.4.1 | 3 |  |  |  | Development Team |  | 0% |  |  | 2027-01-09 | 2027-04-15 | 96d | [5 empty] | 2027-01-09 | 2027-04-15
1.4.1.1 | 4 | 2027 Roadmap | ITMS — Development | VAT Committee | Compounding Offence | 100% | 0% | Not Started |  | 2027-01-09 | 2027-01-15 | 6d |  |  |  | VAT Committee |  | 2027-01-09 | 2027-01-15
1.4.1.2 | 4 | 2027 Roadmap | ITMS — Development | VAT Committee | Migration from RajTax & RajVista to ITMS | 100% | 0% | Not Started |  | 2027-02-13 | 2027-02-28 | 15d | 1.4.1.1FS |  |  | VAT Committee |  | 2027-02-13 | 2027-02-28
1.4.1.3 | 4 | 2027 Roadmap | ITMS — Development | VAT Committee | Inspection & Seizure | 100% | 0% | Not Started |  | 2027-02-14 | 2027-02-20 | 6d | 1.4.1.2FS |  |  | VAT Committee |  | 2027-02-14 | 2027-02-20
1.4.1.4 | 4 | 2027 Roadmap | ITMS — Development | FA | AG Audit Para Module | 100% | 0% | Not Started |  | 2027-02-25 | 2027-03-12 | 15d | 1.4.1.3FS |  |  | FA |  | 2027-02-25 | 2027-03-12
1.4.1.5 | 4 | 2027 Roadmap | ITMS — Development | BIU | Development of functionality related to section 71 | 100% | 0% | Not Started |  | 2027-03-09 | 2027-03-24 | 15d | 1.4.1.4FS |  |  | BIU |  | 2027-03-09 | 2027-03-24
1.4.1.6 | 4 | 2027 Roadmap | ITMS — Development | DC-IT | Raj Nivesh Integration | 100% | 0% | Not Started | API need to be developed for 110 forms | 2027-03-21 | 2027-04-05 | 15d | 1.4.1.5FS |  |  | DC-IT |  | 2027-03-21 | 2027-04-05
1.4.1.7 | 4 | 2027 Roadmap | ITMS — Development | DC-IT | RIPS 2024 Integration and module development | 100% | 0% | Not Started | 2 API and workflow. Discussion completed from DoIT. Pending the document from DoIT. | 2027-03-31 | 2027-04-15 | 15d | 1.4.1.6FS |  |  | DC-IT |  | 2027-03-31 | 2027-04-15
1.4.1.8 | 4 | 2027 Roadmap | ITMS — Development | Development Team | RIPS 2014, 2019 & 2022 Integration and module development | 100% | 0% | Not Started |  | 2027-03-31 | 2027-04-15 | 15d | 1.4.1.7FS |  |  | Development Team |  | 2027-03-31 | 2027-04-15
1.4.1.9 | 4 | 2027 Roadmap | ITMS — Development | Development Team | Electricity Duty module Development | 100% | 0% | Not Started |  | 2027-03-31 | 2027-04-15 | 15d | 1.4.1.8FS |  |  | Development Team |  | 2027-03-31 | 2027-04-15
1.4.1.10 | 4 | 2027 Roadmap | ITMS — Development | Development Team | Hotel Reimbursement | 100% | 0% | Not Started |  | 2027-04-09 | 2027-04-15 | 6d | 1.4.1.9FS |  |  | Development Team |  | 2027-04-09 | 2027-04-15
1.4.1.11 | 4 | 2027 Roadmap | ITMS — Development | Development Team | Amnesty Schemes | 100% | 0% | Not Started |  | 2027-04-09 | 2027-04-15 | 6d | 1.4.1.10FS |  |  | Development Team |  | 2027-04-09 | 2027-04-15
1.4.1.12 | 4 | 2027 Roadmap | ITMS — Development | Development Team | eNidaan & request logger | 100% | 0% | Not Started |  | 2027-04-09 | 2027-04-15 | 6d | 1.4.1.11FS |  |  | Development Team |  | 2027-04-09 | 2027-04-15
1.4.2 | 3 |  |  |  | RAID (Nexus) Development |  | 0% |  |  | 2027-01-05 | 2027-03-16 | 70d | [5 empty] | 2027-01-05 | 2027-03-16
1.4.2.1 | 4 | 2027 Roadmap | Platform, DevOps & Core Utility | V. Kushwaha (Dev) | CI/CD pipeline & production environment setup (GCP) | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2027-01-05 | 2027-01-17 | 12d |  |  |  | V. Kushwaha (Dev) |  | 2027-01-05 | 2027-01-17
1.4.2.2 | 4 | 2027 Roadmap | Platform, DevOps & Core Utility | Ashish Gauttam (Dev) | Data migration rehearsal & go-live readiness checklist | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2027-01-18 | 2027-01-28 | 10d | 1.4.2.1FS |  |  | Ashish Gauttam (Dev) |  | 2027-01-18 | 2027-01-28
1.4.2.3 | 4 | 2027 Roadmap | Third-Party & DISCOM Integration | Sanjay (Lead) | Phased rollout to pilot zones/circles | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2027-01-29 | 2027-02-13 | 15d | 1.4.2.2FS |  |  | Sanjay (Lead) |  | 2027-01-29 | 2027-02-13
1.4.2.4 | 4 | 2027 Roadmap | Platform, DevOps & Core Utility | Jitendra P. (Dev) | Production monitoring, logging & alerting setup | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2027-02-14 | 2027-02-22 | 8d | 1.4.2.3FS |  |  | Jitendra P. (Dev) |  | 2027-02-14 | 2027-02-22
1.4.2.5 | 4 | 2027 Roadmap | Platform, DevOps & Core Utility | V. Kushwaha (Dev) | Post go-live stabilization & bug-fixing | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2027-02-23 | 2027-03-10 | 15d | 1.4.2.4FS |  |  | V. Kushwaha (Dev) |  | 2027-02-23 | 2027-03-10
1.4.2.6 | 4 | 2027 Roadmap | Platform, DevOps & Core Utility | Sanjay (Lead) | RAID (Nexus) v1.0 statewide production go-live | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2027-03-11 | 2027-03-16 | 5d | 1.4.2.5FS |  |  | Sanjay (Lead) |  | 2027-03-11 | 2027-03-16
1.5 | 2 |  |  |  | Phase 5 — Program Closure (May 2027) |  | 0% |  |  | 2027-05-01 | 2027-05-14 | 13d | [5 empty] | 2027-05-01 | 2027-05-14
1.5.1 | 3 |  |  |  | RAID (Nexus) Development |  | 0% |  |  | 2027-05-01 | 2027-05-14 | 13d | [5 empty] | 2027-05-01 | 2027-05-14
1.5.1.1 | 4 | Closure | Platform, DevOps & Core Utility | Sanjay (Lead) | Handover, admin training & knowledge transfer | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2027-05-01 | 2027-05-09 | 8d |  |  |  | Sanjay (Lead) |  | 2027-05-01 | 2027-05-09
1.5.1.2 | 4 | Closure | Platform, DevOps & Core Utility | Sanjay (Lead) | Final sign-off & RAID (Nexus) project closure note | 100% | 0% | Not Started | Projected — not in source data; sequence/duration estimated for planning purposes | 2027-05-10 | 2027-05-14 | 4d | 1.5.1.1FS |  |  | Sanjay (Lead) |  | 2027-05-10 | 2027-05-14
1.6 | 2 |  |  |  | Cross-Phase — Ongoing Workstreams |  | 63.07% |  |  | 2026-06-01 | 2026-12-20 | 202d | [5 empty] | 2026-06-01 | 2026-12-20
1.6.1 | 3 |  |  |  | Integrations Tracker |  | 56.02% |  |  | 2026-06-01 | 2026-12-20 | 202d | [5 empty] | 2026-06-01 | 2026-12-20
1.6.1.1 | 4 | Ongoing | Dept. Integration — Mining | Mining | Mining — eRwanna, Transit Pass, ERCC, Challan Summary, RC | 100% | 50% | In Progress | ERCC - lease mapping shared by the mining department and rest data currently accessible through SDRI's systems | 2026-08-01 | 2026-09-15 | 45d |  |  |  | Mining | Letter has been shared with Mining department along with API paramaters | 2026-08-01 | 2026-09-15
1.6.1.2 | 4 | Ongoing | Dept. Integration — Transport | Transport | Transport — Vehicle Owner Detail (Vehicle Registration Data) | 100% | 50% | In Progress | Currently accessible through SDRI's systems,but access connection currently not stable / inconsistent resulting in failure of queries | 2026-08-13 | 2026-09-27 | 45d | 1.6.1.1FS |  |  | Transport | Letter has been shared with Transport department, along with field information | 2026-08-13 | 2026-09-27
1.6.1.3 | 4 | Ongoing | Dept. Integration — Electricity | Electricity | Electricity — Consumption Data | 100% | 100% | Completed | Currently have access of API, but primary parameter is K No and only last 12 months consumption data is available. Have written mail / letter to get access to all K-Number data read only access | 2026-08-25 | 2026-10-09 | 45d | 1.6.1.2FS |  |  | Electricity | Letter has been shared with electricity department with additional paramter as consumption period, to access consumption data of each subscribers | 2026-08-25 | 2026-10-09
1.6.1.4 | 4 | Ongoing | Dept. Integration — JDA | JDA | JDA — Invoice wise detail of payment done against the contracts | 100% | 50% | In Progress | High level Contract data has been shared by the JDA, but for analysis purpose we require invoice wise payment detail along with TDS deducted at JDA end. Had discussion with Mahipal Ji (ACP), and have shared the fields that they require. Sample data has been received on 24th July. | 2026-09-06 | 2026-10-21 | 45d | 1.6.1.3FS |  |  | JDA | Reminder letter for API integration along with data required already shared with JDA | 2026-09-06 | 2026-10-21
1.6.1.5 | 4 | Ongoing | Dept. Integration — IGRS | IGRS | IGRS — Joint Development Agreement, Property Registration | 100% | 100% | Completed | We have requested data related to RIPS benefit, JDA and Rental agreement from IGRS. They have shared the required APIs, data is being extracted from these APIs. | 2026-06-01 | 2026-07-06 | 35d | 1.6.1.4FS | 2026-07-06 | 2026-06-01 | IGRS | API integration done and data is available against our requirement | 2026-06-01 | 2026-07-06
1.6.1.6 | 4 | Ongoing | Dept. Integration — IFMS | IFMS | IFMS — Invoice wise detail of payment done against the vendors | 100% | 50% | In Progress | On time data has been shared by CTD related to TDS deducted under SNA Sparsh system. We had requested data sharing for contracts and payments being made to vendors. We have shared the required fields but IFMS is yet to share the API for our consumption | 2026-09-18 | 2026-11-02 | 45d | 1.6.1.5FS |  |  | IFMS | Letter has been shared and also shared the API documents | 2026-09-18 | 2026-11-02
1.6.1.7 | 4 | Ongoing | Dept. Integration — RERA | RERA | RERA — Property sold, project detail | 100% | 50% | In Progress | Currently this information is available on public portal and extracted via Scrapping. Request was made for API integrations and fields were shared to concerned person for the same. API development currnetly under process | 2026-09-30 | 2026-11-14 | 45d | 1.6.1.6FS |  |  | RERA | We have shared the letter with RERA to get access of APIs | 2026-09-30 | 2026-11-14
1.6.1.8 | 4 | Ongoing | Dept. Integration — RGHS | RGHS | RGHS — Hospital/Pharmacy payment detail, re-imbursement of employee bills and payment of other check-up | 100% | 50% | In Progress | Sample data has been shared by the RGHS department, team is currently analysing the same. We are analyzing the data to check if the data will be useful for future use cases. | 2026-10-12 | 2026-11-26 | 45d | 1.6.1.7FS |  |  | RGHS | Letter has been shared with RGHS for API integration | 2026-10-12 | 2026-11-26
1.6.1.9 | 4 | Ongoing | Dept. Integration — UDH | UDH | UDH — Development Services provided by development authorities , Auction processing fees, Lease of land , Sales of commercial plots , Licensing fees and development charges , Joint Development Agreements, Details of ongoing and completed projects (roads, housing, infrastructure, etc.) , Contract values and corresponding payment schedules , Contractor Information | 100% | 50% | In Progress | Only JDA partial data has been received | 2026-10-24 | 2026-12-08 | 45d | 1.6.1.8FS |  |  | UDH | Letter has been shared with data requirement | 2026-10-24 | 2026-12-08
1.6.1.10 | 4 | Ongoing | Dept. Integration — RIPS | RIPS | RIPS — RIPS Applicant and benefits detail | 100% | 60% | In Progress | TCS database for RIPS 2022 application is done. Integration with Industries is under process. | 2026-11-05 | 2026-12-20 | 45d | 1.6.1.9FS |  |  | RIPS |  | 2026-11-05 | 2026-12-20
1.6.2 | 3 |  |  |  | SAS Dashboards (Recurring) |  | 100% |  |  | 2026-08-01 | 2026-08-07 | 6d | [5 empty] | 2026-08-01 | 2026-08-07
1.6.2.1 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | Non filer dashboard | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d |  | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07
1.6.2.2 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | Sector Analysis (Top 1 Lakh) | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d | 1.6.2.1FS | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07
1.6.2.3 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | Zonal Performance | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d | 1.6.2.2FS | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07
1.6.2.4 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | Sector Outliers | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d | 1.6.2.3FS | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07
1.6.2.5 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | Adjudication done during the month | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d | 1.6.2.4FS | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07
1.6.2.6 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | SCN Issued during the month | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d | 1.6.2.5FS | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07
1.6.2.7 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | Recovery Pendency Report | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d | 1.6.2.6FS | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07
1.6.2.8 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | Appeal Dashboard | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d | 1.6.2.7FS | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07
1.6.2.9 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | Revenue Dashboard | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d | 1.6.2.8FS | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07
1.6.2.10 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | Zonal Profile Dashboard | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d | 1.6.2.9FS | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07
1.6.2.11 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | Sector Analysis (Commodity Level) | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d | 1.6.2.10FS | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07
1.6.2.12 | 4 | Ongoing / Monthly | Recurring Reporting | Analytics Team | Zone wise revenue report (A,B,C,D ) | 100% | 100% | Completed | Recurring — repeats monthly (cycle shown is the current/next cycle) through project close, May 2027 | 2026-08-01 | 2026-08-07 | 7d | 1.6.2.11FS | 2026-08-07 | 2026-08-01 | Analytics Team | Recurring — repeats monthly through project close, May 2027 | 2026-08-01 | 2026-08-07