## Laos IFMIS PC_PMP Updated
WBS | Level | Phase | Activity Name | Primary Responsibility | Task Name | % Planned | % Complete | Status | Remarks | Planned Start Date | Planned End Date | Duration | Predecessors | Actual End Date | Actual Start Date | Assigned To | Comments | Start | Finish
1 | 1 |  |  |  | Laos PDR - IFMIS Implementation Schedule |  | 15% |  |  | 2025-04-21 | 2027-08-30 | 616d
1.1 | 2 |  |  |  | Project Initiation and Planning | 100% | 100% |  |  | 2025-04-21 | 2025-04-29 | 7d
1.1.1 | 3 |  |  |  | Project Kick Off | 100% | 100% |  |  | 2025-04-21 | 2025-04-29 | 7d
1.1.1.1 | 4 | Initiation | Kickoff | TBG | Submission of Performance Guarantee (PG) | 100% | 100% | Complete | On Time | 2025-04-21 | 2025-04-24 | 4d |  |  |  | TBG
1.1.1.2 | 4 | Initiation | Kickoff | TBG | Identify the Stakeholder | 100% | 100% | Complete | On Time | 2025-04-21 | 2025-04-23 | 3d | 4SS |  |  | PIU
1.1.1.3 | 4 | Initiation | Kickoff | PIU | Schedule Kickoff Meeting arrangement | 100% | 100% | Complete | On Time | 2025-04-24 | 2025-04-29 | 4d | 5 |  |  | PIU/TBG
1.1.1.4 | 4 | Initiation | Kickoff | PIU | Conduct Kick Off Meeting and Project Launch | 100% | 100% | Complete | On Time | 2025-04-28 | 2025-04-28 | 0.5d |  |  |  | TBG
| 2 |  |  |  | Pre-Development Phase |  | 66% |  |  | 2025-04-28 | 2025-11-26 | 153d
1.1.2 | 3 |  |  |  | Inception Report Preparation | 100% | 100% |  |  | 2025-04-28 | 2025-07-04 | 50d
1.1.2.1 | 4 | Pre-Development | Inception Report | TBG | Preparing and Submission of Inception Report | 100% | 100% | Complete | On Time | 2025-04-28 | 2025-05-14 | 13d |  | 05/14/25 | 04/28/25 | TBG
1.1.2.2 | 4 | Pre-Development | Inception Report | IFMIS Committee | Review of Inception Report | 100% | 100% | Complete | On Time | 2025-05-15 | 2025-06-18 | 25d |  | 06/18/25 | 05/15/25 | PIU
1.1.2.3 | 4 | Pre-Development | Inception Report | TBG | Incorporating Review Comments and Recommendations | 100% | 100% | Complete | On Time | 2025-05-23 | 2025-06-19 | 20d |  | 06/19/25 | 05/23/25 | TBG
1.1.2.4 | 4 | Pre-Development | Inception Report | TBG | Submission of Final Inception Report | 100% | 100% | Complete | On Time | 2025-06-20 | 2025-06-20 | 1d |  | 06/20/25 | 06/20/25 | TBG
1.1.2.5 | 4 | Pre-Development | Inception Report | IFMIS Committee | Inception Report Sign Off | 100% | 100% | Complete | On Time | 2025-07-04 | 2025-07-04 | 0 | 13FS +10d | 07/04/25 | 07/04/25 | PIU
1.1.3 | 3 |  |  |  | Project Charter/Project Management Plan Preparation | 100% | 100% |  |  | 2025-04-28 | 2025-07-04 | 50d
1.1.3.1 | 4 | Pre-Development | PMP/Project Plan | TBG | Preparation and Submission of PC/PMP | 100% | 100% | Complete | On Time | 2025-04-28 | 2025-05-14 | 13d | 10SS | 05/14/25 | 04/28/25 | TBG
1.1.3.2 | 4 | Pre-Development | PMP/Project Plan | IFMIS Committee | Review of PC/Project Management Plan | 100% | 100% | Complete | On Time | 2025-05-15 | 2025-06-18 | 25d | 11SS | 06/18/25 | 05/15/25 | PIU
1.1.3.3 | 4 | Pre-Development | PMP/Project Plan | TBG | Incorporating Review Comments and Recommendations | 100% | 100% | Complete | On Time | 2025-05-23 | 2025-06-19 | 20d | 12SS | 06/19/25 | 05/23/25 | TBG
1.1.3.4 | 4 | Pre-Development | PMP/Project Plan | TBG | Submit Final PC/Project Management Plan | 100% | 100% | Complete | On Time | 2025-06-20 | 2025-06-20 | 1d | 13SS | 06/20/25 | 06/20/25 | TBG
1.1.3.5 | 4 | Pre-Development | PMP/Project Plan | IFMIS Committee | PC/Project Management Plan Sign off | 100% | 100% | Complete | On Time | 2025-07-04 | 2025-07-04 | 0 | 19FS +10d | 07/04/25 | 07/04/25 | PIU
1.2 | 3 |  |  |  | Requirement Study Stage | 100% | 80% |  |  | 2025-05-19 | 2025-09-09 | 82d
1.2.1 | 4 |  |  |  | As-Is Process Documentation and Analysis | 100% | 80% |  |  | 2025-05-19 | 2025-09-09 | 82d
1.2.1.1 | 5 |  |  |  | Module 1: As-Is Documentation/Analysis | 100% | 79% |  |  | 2025-05-19 | 2025-07-15 | 42d
1.2.1.1.1 | 6 |  |  |  | Accounting and Reconciliation | 100% | 87% |  |  | 2025-05-19 | 2025-07-15 | 42d
1.2.1.1.1.1 | 7 | Pre-Development | System Requirement Study | TBG | Documents Review and Analysis | 100% | 100% | Complete | Delayed | 2025-05-19 | 2025-06-10 | 17d |  | 06/10/25 | 05/19/25 | TBG
1.2.1.1.1.2 | 6 | Pre-Development | System Requirement Study | PMC | Knowledge Transfer with Deloitte | 100% | 100% | Complete | On Time | 2025-05-27 | 2025-05-27 | 0.5d |  | 05/27/25 | 05/27/25 | Deloitte
1.2.1.1.1.3 | 6 | Pre-Development | System Requirement Study | TBG | Clarification Meetings with Owner Departments | 100% | 100% | Complete | Delayed | 2025-05-21 | 2025-06-26 | 27d |  |  |  | TBG/NT
|  | Pre-Development | System Requirement Study | TBG | Collection of information related to Accounting and Reconciliation | 100% | 70% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d
|  | Pre-Development | System Requirement Study | TBG | Validation of As Is Understanding | 100% | 50% | In Progress | Delayed | 2025-05-28 | 2025-06-12 | 12d | 27FF -10d
1.2.1.1.1.4 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Preparation | 100% | 100% | Complete | Delayed | 2025-05-27 | 2025-06-30 | 25d | 27SS +4d |  |  | TBG
1.2.1.1.1.8 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Translation | 100% | 100% | Complete | Delayed | 2025-07-14 | 2025-07-15 | 2d | 30FF +11d |  |  | TBG
1.2.1.1.2 | 5 |  |  |  | Procurement and Contract | 100% | 67% |  |  | 2025-05-19 | 2025-07-15 | 42d
1.2.1.1.2.1 | 6 | Pre-Development | System Requirement Study | TBG | Documents Review and Analysis | 100% | 100% | Complete | Delayed | 2025-05-19 | 2025-06-10 | 17d | 25SS |  |  | TBG
1.2.1.1.2.2 | 6 | Pre-Development | System Requirement Study | PMC | Knowledge Transfer with Deloitte | 100% | 100% | Complete | On Time | 2025-05-29 | 2025-05-29 | 0.5d |  |  |  | Deloitte
1.2.1.1.2.3 | 6 | Pre-Development | System Requirement Study | TBG | Clarification Meetings with Ministry | 100% | 100% | Complete | Delayed | 2025-05-21 | 2025-06-26 | 27d |  |  |  | PIU-TBA
|  | Pre-Development | System Requirement Study | TBG | Clarification Meetings with Province | 100% | 100% | Complete | Delayed | 2025-06-24 | 2025-06-26 | 3d
|  | Pre-Development | System Requirement Study | TBG | Clarification meeting with PPMD | 100% | 0% | Not Started | Delayed | 2025-06-09 | 2025-06-20 | 10d
|  | Pre-Development | System Requirement Study | TBG | Collection of Procurement Related forms/templates/information | 100% | 50% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d
1.2.1.1.2.4 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Preparation | 100% | 50% | In Progress | Delayed | 2025-05-27 | 2025-06-30 | 25d | 30SS |  |  | TBG
1.2.1.1.2.8 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Translation | 100% | 50% | In Progress | Delayed | 2025-07-10 | 2025-07-15 | 4d | 39FF +11d |  |  | PIU
1.2.1.1.3 | 5 |  |  |  | Commitment and Cash Management | 100% | 82% |  |  | 2025-05-19 | 2025-07-15 | 42d
1.2.1.1.3.1 | 6 | Pre-Development | System Requirement Study | TBG | Documents Review and Analysis | 100% | 100% | Complete | Delayed | 2025-05-19 | 2025-06-10 | 17d | 25SS |  |  | TBG
1.2.1.1.3.2 | 6 | Pre-Development | System Requirement Study | PMC | Knowledge Transfer with Deloitte | 100% | 100% | Complete | On Time | 2025-05-28 | 2025-05-28 | 0.5d |  |  |  | Deloitte
1.2.1.1.3.3 | 6 | Pre-Development | System Requirement Study | TBG | Clarification Meetings with Owner Departments | 100% | 100% | Complete | Delayed | 2025-05-21 | 2025-06-26 | 27d | 27SS |  |  | PIU-TBA
|  | Pre-Development | System Requirement Study | TBG | Validation of As Is Understanding for Cash Management | 100% | 50% | In Progress | Delayed | 2025-06-18 | 2025-06-26 | 7d
|  | Pre-Development | System Requirement Study | TBG | Validation of As Is Understanding for Commitment Management | 100% | 50% | In Progress | Delayed | 2025-06-18 | 2025-06-26 | 7d
|  | Pre-Development | System Requirement Study | TBG | Collection of Forms/Information/Templates | 100% | 50% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d
1.2.1.1.3.4 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Preparation | 100% | 100% | Complete | Delayed | 2025-05-27 | 2025-06-30 | 25d | 30SS |  |  | TBG
1.2.1.1.3.8 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Translation | 100% | 100% | Complete | Delayed | 2025-07-10 | 2025-07-15 | 4d | 48FF +11d |  |  | PIU
1.2.1.1.4 | 5 |  |  |  | Bill Processing | 100% | 93% |  |  | 2025-05-19 | 2025-07-15 | 42d
1.2.1.1.4.1 | 6 | Pre-Development | System Requirement Study | TBG | Documents Review and Analysis | 100% | 100% | In Progress | Delayed | 2025-05-19 | 2025-06-10 | 17d | 25SS |  |  | TBG
1.2.1.1.4.2 | 6 | Pre-Development | System Requirement Study | PMC | Knowledge Transfer with Deloitte | 100% | 100% | Complete | On Time | 2025-05-23 | 2025-05-23 | 0.5d |  |  |  | Deloitte
1.2.1.1.4.3 | 6 | Pre-Development | System Requirement Study | TBG | Clarification Meetings with Owner Departments | 100% | 100% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d | 27SS |  |  | PIU-TBA
|  | Pre-Development | System Requirement Study | TBG | Validation of understanding of Bill Processing | 100% | 70% | In Progress | Delayed | 2025-06-18 | 2025-06-26 | 7d
|  | Pre-Development | System Requirement Study | TBG | Collection of Information related to forms, types of payments, reports | 100% | 80% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d | 53SS
1.2.1.1.4.4 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Preparation | 100% | 100% | Complete | Delayed | 2025-05-27 | 2025-06-30 | 25d | 30SS |  |  | TBG
1.2.1.1.4.8 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Translation | 100% | 100% | Complete | Delayed | 2025-07-10 | 2025-07-15 | 4d | 56FF +11d |  |  | PIU
1.2.1.1.5 | 5 |  |  |  | Payment, Receipt & Reconciliation | 100% | 90% |  |  | 2025-05-19 | 2025-07-15 | 42d
1.2.1.1.5.1 | 6 | Pre-Development | System Requirement Study | TBG | Documents Review and Analysis | 100% | 100% | Complete | Delayed | 2025-05-19 | 2025-06-10 | 17d | 25SS |  |  | TBG
1.2.1.1.5.2 | 6 | Pre-Development | System Requirement Study | PMC | Knowledge Transfer with Deloitte | 100% | 100% | Complete | On Time | 2025-05-26 | 2025-05-26 | 0.5d |  |  |  | Deloitte
1.2.1.1.5.3 | 6 | Pre-Development | System Requirement Study | TBG | Clarification Meetings with Owner Departments | 100% | 100% | Complete | Delayed | 2025-05-21 | 2025-06-26 | 27d | 27SS |  |  | PIU/NT
|  | Pre-Development | System Requirement Study | TBG | Validation of understanding with Owner Department | 100% | 60% | In Progress | Delayed | 2025-06-18 | 2025-06-26 | 7d
|  | Pre-Development | System Requirement Study | TBG | Collection of forms/information/reports | 100% | 70% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d
1.2.1.1.5.4 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Preparation | 100% | 100% | Complete | Delayed | 2025-05-27 | 2025-06-30 | 25d | 30SS |  |  | TBG
1.2.1.1.5.8 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Translation | 100% | 100% | Complete | Delayed | 2025-07-10 | 2025-07-15 | 4d | 64FF +11d |  |  | PIU
1.2.1.1.6 | 5 |  |  |  | Asset Management | 100% | 80% |  |  | 2025-05-19 | 2025-07-15 | 42d
1.2.1.1.6.1 | 6 | Pre-Development | System Requirement Study | TBG | Documents Review and Analysis | 100% | 100% | In Progress | Delayed | 2025-05-19 | 2025-06-10 | 17d | 25SS |  |  | TBG
1.2.1.1.6.2 | 6 | Pre-Development | System Requirement Study | PMC | Knowledge Transfer with Deloitte | 100% | 100% | Complete | On Time | 2025-05-29 | 2025-05-29 | 0.5d |  |  |  | Deloitte
1.2.1.1.6.3 | 6 | Pre-Development | System Requirement Study | TBG | Clarification Meetings with Owner Departments | 100% | 100% | Complete | Delayed | 2025-05-21 | 2025-06-26 | 27d | 27SS |  |  | PIU-TBA
|  | Pre-Development | System Requirement Study | TBG | Collection of forms/information/reports | 100% | 40% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d
|  | Pre-Development | System Requirement Study | TBG | Validation of understanding with Owner Department | 100% | 20% | Not Started | Delayed | 2025-06-18 | 2025-06-26 | 7d
1.2.1.1.6.4 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Preparation | 100% | 100% | In Progress | Delayed | 2025-05-27 | 2025-06-30 | 25d | 30SS |  |  | TBG
1.2.1.1.6.8 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Translation | 100% | 100% | In Progress | Delayed | 2025-07-10 | 2025-07-15 | 4d | 72FF +11d |  |  | PIU
1.2.1.1.7 | 5 |  |  |  | Other Accounts | 100% | 57% |  |  | 2025-05-19 | 2025-07-15 | 42d
1.2.1.1.7.1 | 6 | Pre-Development | System Requirement Study | TBG | Documents Review and Analysis | 100% | 50% | In Progress | Delayed | 2025-05-19 | 2025-05-30 | 10d | 25SS |  |  | TBG
1.2.1.1.7.2 | 6 | Pre-Development | System Requirement Study | PMC | Knowledge Transfer with Deloitte | 100% | 100% | Complete | On Time | 2025-05-29 | 2025-05-29 | 0.5d |  |  |  | Deloitte
1.2.1.1.7.3 | 6 | Pre-Development | System Requirement Study | TBG | Clarification Meetings with Owner Departments | 100% | 50% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d | 27SS |  |  | PIU-TBA
|  | Pre-Development | System Requirement Study | TBG | Collection of forms/information/reports | 100% | 20% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d
|  | Pre-Development | System Requirement Study | TBG | Validation of understanding with Owner Department | 100% | 50% | In Progress | Delayed | 2025-06-18 | 2025-06-26 | 7d
1.2.1.1.7.4 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Preparation | 100% | 100% | In Progress | Delayed | 2025-05-27 | 2025-06-30 | 25d | 30SS |  |  | TBG
1.2.1.1.7.8 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Translation | 100% | 100% | In Progress | Delayed | 2025-07-10 | 2025-07-15 | 4d | 80FF +11d |  |  | PIU
1.2.1.2 | 4 |  |  |  | Module 2: As-Is Documentation/Analysis | 100% | 93% |  |  | 2025-05-19 | 2025-07-21 | 46d
1.2.1.2.1 | 5 |  |  |  | Budget Preparation | 100% | 94% |  |  | 2025-05-19 | 2025-07-21 | 46d
1.2.1.2.1.1 | 6 | Pre-Development | System Requirement Study | TBG | Documents Review and Analysis | 100% | 100% | Complete | On Time | 2025-05-19 | 2025-06-10 | 17d | 25SS |  |  | TBG
1.2.1.2.1.2 | 6 | Pre-Development | System Requirement Study | PMC | Knowledge Transfer with Deloitte | 100% | 100% | Complete | On Time | 2025-05-20 | 2025-05-20 | 0.5d |  |  |  | Deloitte
1.2.1.2.1.3 | 6 | Pre-Development | System Requirement Study | TBG | Clarification Meetings with Owner Departments | 100% | 100% | Complete | Delayed | 2025-05-21 | 2025-06-26 | 27d | 27SS |  |  | SBD
|  | Pre-Development | System Requirement Study | TBG | Collection of forms/information/reports | 100% | 90% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d
|  | Pre-Development | System Requirement Study | TBG | Validation of understanding with Owner Department | 100% | 50% | In Progress | Delayed | 2025-06-18 | 2025-06-26 | 7d
1.2.1.2.1.4 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Preparation | 100% | 100% | Complete | Delayed | 2025-05-27 | 2025-06-30 | 25d | 30SS |  |  | TBG
1.2.1.2.1.8 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Translation | 100% | 100% | Complete | Delayed | 2025-07-16 | 2025-07-21 | 4d | 89FS +11d |  |  | PIU
1.2.1.2.2 | 5 |  |  |  | Budget Allocation and Distribution | 100% | 92% |  |  | 2025-05-19 | 2025-07-15 | 42d
1.2.1.2.2.1 | 6 | Pre-Development | System Requirement Study | TBG | Documents Review and Analysis | 100% | 100% | Complete | On Time | 2025-05-19 | 2025-06-10 | 17d | 25SS |  |  | TBG
1.2.1.2.2.2 | 6 | Pre-Development | System Requirement Study | PMC | Knowledge Transfer with Deloitte | 100% | 100% | Complete | On Time | 2025-05-20 | 2025-05-20 | 0.5d |  |  |  | Deloitte
1.2.1.2.2.3 | 6 | Pre-Development | System Requirement Study | TBG | Clarification Meetings with Owner Departments | 100% | 100% | Complete | Delayed | 2025-05-21 | 2025-06-26 | 27d | 27SS |  |  | SBD
|  | Pre-Development | System Requirement Study | TBG | Collection of forms/information/reports | 100% | 80% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d
|  | Pre-Development | System Requirement Study | TBG | Validation of understanding with Owner Department | 100% | 50% | In Progress | Delayed | 2025-06-18 | 2025-06-26 | 7d
1.2.1.2.2.4 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Preparation | 100% | 100% | Complete | Delayed | 2025-05-27 | 2025-06-30 | 25d | 30SS |  |  | TBG
1.2.1.2.2.8 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Translation | 100% | 100% | Complete | Delayed | 2025-07-10 | 2025-07-15 | 4d | 97FF +11d |  |  | PIU
1.2.1.2.3 | 5 |  |  |  | Bill Creation | 100% | 94% |  |  | 2025-05-19 | 2025-07-15 | 42d
1.2.1.2.3.1 | 6 | Pre-Development | System Requirement Study | TBG | Documents Review and Analysis | 100% | 100% | Complete | Delayed | 2025-05-19 | 2025-06-10 | 17d | 25SS |  |  | TBG
1.2.1.2.3.2 | 6 | Pre-Development | System Requirement Study | PMC | Knowledge Transfer with Deloitte | 100% | 100% | Complete | On Time | 2025-05-23 | 2025-05-23 | 0.5d |  |  |  | Deloitte
1.2.1.2.3.3 | 6 | Pre-Development | System Requirement Study | TBG | Clarification Meetings with Owner Departments | 100% | 100% | Complete | Delayed | 2025-05-21 | 2025-06-26 | 27d | 27SS |  |  | SBD
|  | Pre-Development | System Requirement Study | TBG | Collection of forms/information/reports | 100% | 90% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d
|  | Pre-Development | System Requirement Study | TBG | Validation of understanding with Owner Department | 100% | 50% | In Progress | Delayed | 2025-06-18 | 2025-06-26 | 7d
1.2.1.2.3.4 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Preparation | 100% | 100% | Complete | Delayed | 2025-05-27 | 2025-06-30 | 25d | 30SS |  |  | TBG
1.2.1.2.3.8 | 6 | Pre-Development | System Requirement Study | TBG | As Is Document Translation | 100% | 100% | Complete | Delayed | 2025-07-10 | 2025-07-15 | 4d | 105FF +11d |  |  | PIU
1.2.1.3 | 4 |  |  |  | Integration Components | 100% | 100% |  |  | 2025-06-25 | 2025-07-03 | 7d
1.2.1.3.1 | 5 | Pre-Development | System Requirement Study | TBG | Validation of Current Status of Source Systems | 100% | 100% | Complete | Delayed | 2025-06-25 | 2025-07-01 | 5d |  |  |  | TBG/PIU
1.2.1.3.2 | 5 | Pre-Development | System Requirement Study | TBG | Finalizing Integration Components' List | 100% | 100% | Complete | Delayed | 2025-07-02 | 2025-07-03 | 2d | 108 |  |  | TBG
1.2.1.4 | 4 |  |  |  | Report Requirement Analysis and Mapping | 100% | 30% |  |  | 2025-05-21 | 2025-07-04 | 33d
1.2.1.4.1 | 5 |  |  |  | Module 1 Reports | 100% | 30% |  |  | 2025-05-21 | 2025-07-04 | 33d
1.2.1.4.1.1 | 6 | Pre-Development | System Requirement Study | TBG | Collecting Report List and Sample Reports (Templates) | 100% | 50% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d | 35SS |  |  | TBG/PIU-TBA
|  | Pre-Development | System Requirement Study | TBG | Analyzing and finding gaps for IFMIS implementation | 100% | 10% | In Progress | Delayed | 2025-05-31 | 2025-07-04 | 26d
1.2.1.4.2 | 5 |  |  |  | Module 2 Reports | 100% | 30% |  |  | 2025-05-21 | 2025-07-04 | 33d
1.2.1.4.2.1 | 6 | Pre-Development | System Requirement Study | TBG | Collecting Report List and Sample Reports (Templates) | 100% | 50% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d | 35SS |  |  | TBG/PIU-TBA
|  | Pre-Development | System Requirement Study | TBG | Analyzing and finding gaps for IFMIS implementation | 100% | 10% | In Progress | Delayed | 2025-05-31 | 2025-07-04 | 26d
1.2.1.4.3 | 5 |  |  |  | Management Reports | 100% | 30% |  |  | 2025-05-21 | 2025-07-04 | 33d
1.2.1.4.3.1 | 6 | Pre-Development | System Requirement Study | TBG | Collecting Report List and Sample Reports (Templates) | 100% | 50% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d | 35SS |  |  | TBG/PIU-TBA
|  | Pre-Development | System Requirement Study | TBG | Analyzing and finding gaps for IFMIS implementation | 100% | 10% | In Progress | Delayed | 2025-05-31 | 2025-07-04 | 26d
1.2.1.4.4 | 5 |  |  |  | Statutory Reports | 100% | 30% |  |  | 2025-05-21 | 2025-07-04 | 33d
1.2.1.4.4.1 | 6 | Pre-Development | System Requirement Study | TBG | Collecting Report List and Sample Reports (Templates) | 100% | 50% | In Progress | Delayed | 2025-05-21 | 2025-06-26 | 27d | 35SS |  |  | TBG/PIU-TBA
|  | Pre-Development | System Requirement Study | TBG | Analyzing and finding gaps for IFMIS implementation | 100% | 10% | In Progress | Delayed | 2025-05-31 | 2025-07-04 | 26d
1.2.1.5 | 4 |  |  |  | Finalizing As Is Documentation | 100% | 100% |  |  | 2025-07-01 | 2025-09-09 | 51d
1.2.1.5.1 | 5 | Pre-Development | System Requirement Study | TBG | Consolidation, Finalizing and Submission of As Is Document (Both Languages) | 100% | 100% | Complete | On Time | 2025-07-01 | 2025-07-21 | 15d | 30 |  |  | TBG
1.2.1.5.2 | 5 | Pre-Development | System Requirement Study | PMC | As Is Document Review (Both Languages) | 100% | 100% | Complete | Delayed | 2025-07-23 | 2025-07-29 | 5d | 124FS +1d |  |  | PIU/Departments
1.2.1.5.3 | 5 | Pre-Development | System Requirement Study | TBG | Incorporating comments (Both Languages) | 100% | 100% | Complete | Delayed | 2025-07-31 | 2025-08-19 | 14d | 125FS +1d |  |  | TBG
1.2.1.5.4 | 5 | Pre-Development | System Requirement Study | TBG | Submission of Final Consolidated As is Document | 100% | 100% | Complete | Delayed | 2025-08-20 | 2025-08-26 | 5d | 126 |  |  | TBG
|  | Pre-Development | System Requirement Study | IFMIS Committee | Final Review of As Is Document | 100% | 100% | Complete | Delayed | 2025-08-27 | 2025-09-09 | 10d | 127
1.2.1.5.5 | 5 | Pre-Development | System Requirement Study | IFMIS Committee | Completion of System Requirement Study (Submission) | 100% | 100% | Complete | Delayed | 2025-08-27 | 2025-08-27 | 0 | 127FS +1d |  |  | TBG/PIU
1.3 | 3 |  |  |  | Design Documentation Stage | 100% | 23% |  |  | 2025-07-07 | 2025-11-26 | 103d
1.3.1 | 3 |  |  |  | To-Be Process Flows Documentation | 100% | 26% |  |  | 2025-07-07 | 2025-10-03 | 64.5d
1.3.1.1 | 4 |  |  |  | Module 1: To Be Process Flows Workshop & Documentation | 100% | 25% |  |  | 2025-08-06 | 2025-10-03 | 42.5d
1.3.1.1.1 | 5 |  |  |  | Accounting and Reconciliation | 100% | 55% |  |  | 2025-08-06 | 2025-09-11 | 26.5d
1.3.1.1.1.1 | 6 | Pre-Development | BSDD | TBG | Prepare To Be Process Flow (L5) | 100% | 100% | In Progress | Delayed | 2025-08-06 | 2025-08-25 | 14d | 129FS -16d |  |  | TBG
1.3.1.1.1.2 | 6 | Pre-Development | BSDD | TBG | Other Accounts Mapping | 100% | 100% | In Progress | Delayed | 2025-08-06 | 2025-08-25 | 14d | 134SS
1.3.1.1.1.3 | 6 | Pre-Development | BSDD | TBG | Process Mapping & Traceability Matrix Documentation | 100% | 25% | In Progress | Delayed | 2025-08-08 | 2025-08-27 | 14d | 134SS +2d |  |  | TBG
1.3.1.1.1.4 | 6 | Pre-Development | BSDD | TBG | Translate To Be Process Flows | 100% | 25% | In Progress | Delayed | 2025-08-11 | 2025-08-28 | 14d | 134SS +3d |  |  | TBG
1.3.1.1.1.5 | 6 | Pre-Development | BSDD | TBG | Submission of To Be Process Flows to Process Owners (Both Languages) | 100% | 50% | In Progress | Delayed | 2025-09-01 | 2025-09-01 | 0.5d | 137FS +1d |  |  | TBG
1.3.1.1.1.6 | 6 | Pre-Development | BSDD | TBG | Workshop on Proposed To Be L5 Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-03 | 2025-09-05 | 2d | 138FS +2d |  |  | TBG/PIU-NT
1.3.1.1.1.7 | 6 | Pre-Development | BSDD | Accounting Dept. | Validation and Consent with Process Owners | 100% | 0% | Not Started | Delayed | 2025-09-03 | 2025-09-09 | 4d | 139SS |  |  | TBG/PIU-NT
1.3.1.1.1.8 | 6 | Pre-Development | BSDD | TBG | Finalize To Be Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-09 | 2025-09-11 | 2d | 140 |  |  | TBG
1.3.1.1.2 | 5 |  |  |  | Procurement and Contract | 100% | 84% |  |  | 2025-08-06 | 2025-09-16 | 29.5d
1.3.1.1.2.1 | 6 | Pre-Development | BSDD | TBG | Prepare To Be Process Flow (L5) | 100% | 100% | In Progress | Delayed | 2025-08-06 | 2025-08-25 | 14d | 134SS |  |  | TBG
1.3.1.1.2.2 | 6 | Pre-Development | BSDD | TBG | Process Mapping & Traceability Matrix Documentation | 100% | 100% | In Progress | Delayed | 2025-08-08 | 2025-08-27 | 14d | 136SS |  |  | TBG
1.3.1.1.2.3 | 6 | Pre-Development | BSDD | TBG | Translate To Be Process Flows | 100% | 100% | In Progress | Delayed | 2025-08-11 | 2025-08-28 | 14d | 137SS |  |  | TBG
1.3.1.1.2.4 | 6 | Pre-Development | BSDD | TBG | Submission of To Be Process Flows to Process Owners (Both Languages) | 100% | 100% | In Progress | Delayed | 2025-09-01 | 2025-09-01 | 0.5d | 138SS |  |  | TBG
1.3.1.1.2.5 | 6 | Pre-Development | BSDD | TBG | Workshop on Proposed To Be L5 Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-08 | 2025-09-10 | 2d | 139FS +1d |  |  | TBG/PIU-TBA
1.3.1.1.2.6 | 6 | Pre-Development | BSDD | IFMIS Committee | Validation and Consent with Process Owners | 100% | 0% | Not Started | Delayed | 2025-09-08 | 2025-09-12 | 4d | 147SS |  |  | TBG/PIU-TBA
1.3.1.1.2.7 | 6 | Pre-Development | BSDD | TBG | Finalize To Be Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-12 | 2025-09-16 | 2d | 148 |  |  | TBG
1.3.1.1.3 | 5 |  |  |  | Commitment Management | 100% | 0% |  |  | 2025-08-06 | 2025-09-18 | 31.5d
1.3.1.1.3.1 | 6 | Pre-Development | BSDD | TBG | Prepare To Be Process Flow (L5) | 100% | 0% | In Progress | Delayed | 2025-08-06 | 2025-08-25 | 14d | 134SS |  |  | TBG
1.3.1.1.3.2 | 6 | Pre-Development | BSDD | TBG | Process Mapping & Traceability Matrix Documentation | 100% | 0% | In Progress | Delayed | 2025-08-08 | 2025-08-27 | 14d | 136SS |  |  | TBG
1.3.1.1.3.3 | 6 | Pre-Development | BSDD | TBG | Translate To Be Process Flows | 100% | 0% | Not Started | Delayed | 2025-08-11 | 2025-08-28 | 14d | 137SS |  |  | TBG
1.3.1.1.3.4 | 6 | Pre-Development | BSDD | TBG | Submission of To Be Process Flows to Process Owners (Both Languages) | 100% | 0% | Not Started | Delayed | 2025-09-01 | 2025-09-01 | 0.5d | 138SS |  |  | TBG
1.3.1.1.3.5 | 6 | Pre-Development | BSDD | TBG | Workshop on Proposed To Be L5 Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-10 | 2025-09-12 | 2d | 147 |  |  | TBG/PIU-TBA
1.3.1.1.3.6 | 6 | Pre-Development | BSDD | SBD | Validation and Consent with Process Owners | 100% | 0% | Not Started | Delayed | 2025-09-10 | 2025-09-16 | 4d | 155SS |  |  | TBG/PIU-TBA
1.3.1.1.3.7 | 6 | Pre-Development | BSDD | TBG | Finalize To Be Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-16 | 2025-09-18 | 2d | 156 |  |  | TBG
1.3.1.1.4 | 5 |  |  |  | Cash Management | 100% | 0% |  |  | 2025-08-06 | 2025-09-19 | 32.5d
1.3.1.1.4.1 | 6 | Pre-Development | BSDD | TBG | Prepare To Be Process Flow (L5) | 100% | 0% | In Progress | Delayed | 2025-08-06 | 2025-08-25 | 14d | 134SS |  |  | TBG
1.3.1.1.4.2 | 6 | Pre-Development | BSDD | TBG | Process Mapping & Traceability Matrix Documentation | 100% | 0% | In Progress | Delayed | 2025-08-08 | 2025-08-27 | 14d | 136SS |  |  | TBG
1.3.1.1.4.3 | 6 | Pre-Development | BSDD | TBG | Translate To Be Process Flows | 100% | 0% | In Progress | Delayed | 2025-08-11 | 2025-08-28 | 14d | 137SS |  |  | TBG
1.3.1.1.4.4 | 6 | Pre-Development | BSDD | TBG | Submission of To Be Process Flows to Process Owners (Both Languages) | 100% | 0% | In Progress | Delayed | 2025-09-01 | 2025-09-01 | 0.5d | 138SS |  |  | TBG
1.3.1.1.4.5 | 6 | Pre-Development | BSDD | TBG | Workshop on Proposed To Be L5 Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-11 | 2025-09-15 | 2d | 155FS -1d |  |  | TBG/PIU-TBA
1.3.1.1.4.6 | 6 | Pre-Development | BSDD | NT | Validation and Consent with Process Owners | 100% | 0% | Not Started | Delayed | 2025-09-11 | 2025-09-17 | 4d | 163SS |  |  | TBG/PIU-TBA
1.3.1.1.4.7 | 6 | Pre-Development | BSDD | TBG | Finalize To Be Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-17 | 2025-09-19 | 2d | 164 |  |  | TBG
1.3.1.1.5 | 5 |  |  |  | Bill Processing |  | 27% |  |  | 2025-08-06 | 2025-10-03 | 42.5d
1.3.1.1.5.1 | 6 | Pre-Development | BSDD | TBG | Prepare To Be Process Flow (L5) | 100% | 25% | In Progress | Delayed | 2025-08-06 | 2025-08-25 | 14d | 134SS |  |  | TBG
1.3.1.1.5.2 | 6 | Pre-Development | BSDD | TBG | Process Mapping & Traceability Matrix Documentation | 100% | 30% | In Progress | Delayed | 2025-08-08 | 2025-08-27 | 14d | 136SS |  |  | TBG
1.3.1.1.5.3 | 6 | Pre-Development | BSDD | TBG | Translate To Be Process Flows | 100% | 25% | In Progress | Delayed | 2025-08-11 | 2025-08-28 | 14d | 137SS |  |  | TBG
1.3.1.1.5.4 | 6 | Pre-Development | BSDD | TBG | Submission of To Be Process Flows to Process Owners (Both Languages) | 100% | 100% | Complete | Delayed | 2025-09-01 | 2025-09-01 | 0.5d | 138SS |  |  | TBG
1.3.1.1.5.5 | 6 | Pre-Development | BSDD | TBG | Workshop on Proposed To Be L5 Process Flows | 100% | 30% | Complete | Delayed | 2025-09-25 | 2025-09-29 | 2d | 212FS -2d |  |  | TBG/PIU-TBA
1.3.1.1.5.6 | 6 | Pre-Development | BSDD | NT | Validation and Consent with Process Owners | 100% | 30% | In Progress | Delayed | 2025-09-25 | 2025-10-01 | 4d | 171SS |  |  | TBG/PIU-TBA
1.3.1.1.5.7 | 6 | Pre-Development | BSDD | TBG | Finalize To Be Process Flows | 100% | 0% | Not Started | Delayed | 2025-10-01 | 2025-10-03 | 2d | 172 |  |  | TBG
1.3.1.1.6 | 5 |  |  |  | Payment, Receipt & Reconciliation |  | 22% |  |  | 2025-08-06 | 2025-10-02 | 41.5d
1.3.1.1.6.1 | 6 | Pre-Development | BSDD | TBG | Prepare To Be Process Flow (L5) | 100% | 25% | In Progress | Delayed | 2025-08-06 | 2025-08-25 | 14d | 134SS |  |  | TBG
1.3.1.1.6.2 | 6 | Pre-Development | BSDD | TBG | Process Mapping & Traceability Matrix Documentation | 100% | 30% | In Progress | Delayed | 2025-08-08 | 2025-08-27 | 14d | 136SS |  |  | TBG
1.3.1.1.6.3 | 6 | Pre-Development | BSDD | TBG | Translate To Be Process Flows | 100% | 25% | In Progress | Delayed | 2025-08-11 | 2025-08-28 | 14d | 137SS |  |  | TBG
1.3.1.1.6.4 | 6 | Pre-Development | BSDD | TBG | Submission of To Be Process Flows to Process Owners (Both Languages) | 100% | 50% | In Progress | Delayed | 2025-09-01 | 2025-09-01 | 0.5d | 138SS |  |  | TBG
1.3.1.1.6.5 | 6 | Pre-Development | BSDD | TBG | Workshop on Proposed To Be L5 Process Flows | 100% | 0% | Not Started | On Time | 2025-09-24 | 2025-09-29 | 3d | 171FS -3d |  |  | TBG/PIU-NT
1.3.1.1.6.6 | 6 | Pre-Development | BSDD | NT | Validation and Consent with Process Owners | 100% | 0% | Not Started | On Time | 2025-09-24 | 2025-09-30 | 4d | 179SS |  |  | TBG/PIU-NT
1.3.1.1.6.7 | 6 | Pre-Development | BSDD | TBG | Finalize To Be Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-30 | 2025-10-02 | 2d | 180 |  |  | TBG
1.3.1.1.7 | 5 |  |  |  | Asset Management |  | 0% |  |  | 2025-08-06 | 2025-09-26 | 37.5d
1.3.1.1.7.1 | 6 | Pre-Development | BSDD | TBG | Prepare To Be Process Flow (L5) | 100% | 0% | In Progress | Delayed | 2025-08-06 | 2025-08-25 | 14d | 134SS |  |  | TBG
1.3.1.1.7.2 | 6 | Pre-Development | BSDD | TBG | Process Mapping & Traceability Matrix Documentation | 100% | 0% | In Progress | Delayed | 2025-08-08 | 2025-08-27 | 14d | 136SS |  |  | TBG
1.3.1.1.7.3 | 6 | Pre-Development | BSDD | TBG | Translate To Be Process Flows | 100% | 0% | In Progress | Delayed | 2025-08-11 | 2025-08-28 | 14d | 137SS |  |  | TBG/PIU-TBA
1.3.1.1.7.4 | 6 | Pre-Development | BSDD | TBG | Submission of To Be Process Flows to Process Owners (Both Languages) | 100% | 0% | Not Started | Delayed | 2025-09-01 | 2025-09-01 | 0.5d | 138SS |  |  | TBG
1.3.1.1.7.5 | 6 | Pre-Development | BSDD | TBG | Workshop on Proposed To Be L5 Process Flows | 0% | 0% | Not Started | Delayed | 2025-09-23 | 2025-09-25 | 2d | 179FS -4d |  |  | TBG/PIU-TBA
1.3.1.1.7.6 | 6 | Pre-Development | BSDD | State Asset Dept | Validation and Consent with Process Owners | 0% | 0% | Not Started | Delayed | 2025-09-23 | 2025-09-26 | 3d | 187SS |  |  | TBG/PIU-TBA
1.3.1.1.7.7 | 6 | Pre-Development | BSDD | TBG | Finalize To Be Process Flows | 0% | 0% | Not Started | Delayed | 2025-09-24 | 2025-09-26 | 2d | 188SS +1d |  |  | TBG
1.3.1.2 | 4 |  |  |  | Module 2: To Be Process Flows Workshops & Documentation | 100% | 17% |  |  | 2025-08-06 | 2025-10-03 | 42.5d
1.3.1.2.1 | 5 |  |  |  | Budget Preparation | 100% | 22% |  |  | 2025-08-06 | 2025-09-11 | 26.5d
1.3.1.2.1.1 | 6 | Pre-Development | BSDD | TBG | Prepare To Be Process Flow (L5) | 100% | 25% | Complete | Delayed | 2025-08-06 | 2025-08-19 | 10d | 134SS |  |  | TBG
1.3.1.2.1.2 | 6 | Pre-Development | BSDD | TBG | Process Mapping & Traceability Matrix Documentation | 100% | 25% | In Progress | Delayed | 2025-08-08 | 2025-08-21 | 10d | 136SS |  |  | TBG
1.3.1.2.1.3 | 6 | Pre-Development | BSDD | TBG | Translate To Be Process Flows | 100% | 25% | In Progress | Delayed | 2025-08-11 | 2025-08-22 | 10d | 137SS |  |  | TBG
1.3.1.2.1.4 | 6 | Pre-Development | BSDD | TBG | Submission of To Be Process Flows to Process Owners (Both Languages) | 100% | 100% | Complete | Delayed | 2025-09-01 | 2025-09-01 | 0.5d | 138SS |  |  | TBG
1.3.1.2.1.5 | 6 | Pre-Development | BSDD | TBG | Workshop on Proposed To Be L5 Process Flows | 100% | 30% | In Progress | Delayed | 2025-09-03 | 2025-09-05 | 2d | 139SS |  |  | TBG/PIU-SBD
1.3.1.2.1.6 | 6 | Pre-Development | BSDD | SBD | Validation and Consent with Process Owners | 100% | 0% | Not Started | Delayed | 2025-09-03 | 2025-09-09 | 4d | 196SS |  |  | TBG/PIU-SBD
1.3.1.2.1.7 | 6 | Pre-Development | BSDD | TBG | Finalize To Be Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-09 | 2025-09-11 | 2d | 197 |  |  | TBG
1.3.1.2.2 | 5 |  |  |  | Budget Allocation and Distribution |  | 0% |  |  | 2025-08-06 | 2025-09-17 | 30.5d
1.3.1.2.2.1 | 6 | Pre-Development | BSDD | TBG | Prepare To Be Process Flow (L5) | 100% | 0% | In Progress | Delayed | 2025-08-06 | 2025-08-19 | 10d | 134SS |  |  | TBG
1.3.1.2.2.2 | 6 | Pre-Development | BSDD | TBG | Process Mapping & Traceability Matrix Documentation | 100% | 0% | In Progress | Delayed | 2025-08-08 | 2025-08-21 | 10d | 136SS |  |  | TBG
1.3.1.2.2.3 | 6 | Pre-Development | BSDD | TBG | Translate To Be Process Flows | 100% | 0% | In Progress | Delayed | 2025-08-11 | 2025-08-22 | 10d | 137SS |  |  | TBG
1.3.1.2.2.4 | 6 | Pre-Development | BSDD | TBG | Submission of To Be Process Flows to Process Owners (Both Languages) | 100% | 0% | Not Started | Delayed | 2025-09-01 | 2025-09-01 | 0.5d | 138SS |  |  | TBG
1.3.1.2.2.5 | 6 | Pre-Development | BSDD | TBG | Workshop on Proposed To Be L5 Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-09 | 2025-09-11 | 2d | 196FS +2d |  |  | TBG/PIU-SBD
1.3.1.2.2.6 | 6 | Pre-Development | BSDD | SBD | Validation and Consent with Process Owners | 100% | 0% | Not Started | Delayed | 2025-09-09 | 2025-09-15 | 4d | 204SS |  |  | TBG/PIU-SBD
1.3.1.2.2.7 | 6 | Pre-Development | BSDD | TBG | Finalize To Be Process Flows | 100% | 0% | Not Started | Delayed | 2025-09-15 | 2025-09-17 | 2d | 205 |  |  | TBG
1.3.1.2.3 | 5 |  |  |  | Bill Creation |  | 25% |  |  | 2025-08-06 | 2025-10-03 | 42.5d
1.3.1.2.3.1 | 6 | Pre-Development | BSDD | TBG | Prepare To Be Process Flow (L5) | 100% | 25% | In Progress | Delayed | 2025-08-06 | 2025-08-25 | 14d | 134SS |  |  | TBG
1.3.1.2.3.2 | 6 | Pre-Development | BSDD | TBG | Process Mapping & Traceability Matrix Documentation | 100% | 25% | In Progress | Delayed | 2025-08-08 | 2025-08-27 | 14d | 136SS |  |  | TBG
1.3.1.2.3.3 | 6 | Pre-Development | BSDD | TBG | Translate To Be Process Flows | 100% | 25% | In Progress | Delayed | 2025-08-11 | 2025-08-28 | 14d | 137SS |  |  | TBG
1.3.1.2.3.4 | 6 | Pre-Development | BSDD | TBG | Submission of To Be Process Flows to Process Owners (Both Languages) | 100% | 100% | Complete | Delayed | 2025-09-01 | 2025-09-01 | 0.5d | 138SS |  |  | TBG
1.3.1.2.3.5 | 6 | Pre-Development | BSDD | TBG | Workshop on Proposed To Be L5 Process Flows | 100% | 30% | In Progress | Delayed | 2025-09-25 | 2025-09-29 | 2d | 163FS +8d |  |  | TBG/PIU-SBD
1.3.1.2.3.6 | 6 | Pre-Development | BSDD | NT | Validation and Consent with Process Owners | 100% | 25% | Not Started | Delayed | 2025-09-25 | 2025-10-01 | 4d | 212SS |  |  | TBG/PIU-SBD
1.3.1.2.3.7 | 6 | Pre-Development | BSDD | TBG | Finalize To Be Process Flows | 100% | 0% | Not Started | Delayed | 2025-10-01 | 2025-10-03 | 2d | 213 |  |  | TBG
1.3.1.3 | 4 |  |  |  | Integration Components | 100% | 38% |  |  | 2025-07-07 | 2025-07-24 | 14d
1.3.1.3.1 | 5 |  |  |  | DMFAS Integration | 100% | 58% |  |  | 2025-07-07 | 2025-07-14 | 6d
1.3.1.3.1.1 | 6 | Pre-Development | BSDD | Other Dept | Engagement with DMFAS Team | 100% | 100% | Complete | Delayed | 2025-07-07 | 2025-07-07 | 1d |  |  |  | TBG/PIU
1.3.1.3.1.2 | 6 | Pre-Development | BSDD | TBG | Identify and Document Integration Points | 100% | 50% | In Progress | Delayed | 2025-07-08 | 2025-07-14 | 5d | 217 |  |  | TBG/DMFAS
1.3.1.3.2 | 5 |  |  |  | TaxRIS Integration | 100% | 58% |  |  | 2025-07-08 | 2025-07-15 | 6d
1.3.1.3.2.2 | 6 | Pre-Development | BSDD | Other Dept | Engagement with TaxRIS Team | 100% | 100% | Complete | Delayed | 2025-07-08 | 2025-07-08 | 1d | 217 |  |  | TBG/PIU
1.3.1.3.2.3 | 6 | Pre-Development | BSDD | TBG | Identify and Document Integration Points | 100% | 50% | Complete | Delayed | 2025-07-09 | 2025-07-15 | 5d | 220 |  |  | TBG/TMIS/TaxRIS
[5 empty] | EasyTax Integration |  | 58% |  |  | 2025-07-15 | 2025-07-22 | 6d
| 6 | Pre-Development | BSDD | TBG | Engagement with EasyTax Team | 100% | 100% | Complete | Delayed | 2025-07-15 | 2025-07-15 | 1d | 221FF
| 6 | Pre-Development | BSDD | TBG | Identify and Document Integration Points | 100% | 50% | Complete | Delayed | 2025-07-16 | 2025-07-22 | 5d | 223
1.3.1.3.3 | 5 |  |  |  | PIMS Integration | 100% | 29% |  |  | 2025-07-09 | 2025-07-17 | 7d
1.3.1.3.3.1 | 6 | Pre-Development | BSDD | Other Dept | Engagement with PIMS Team | 100% | 100% | Complete | Delayed | 2025-07-09 | 2025-07-10 | 2d | 220 |  |  | TBG/PIU
1.3.1.3.3.2 | 6 | Pre-Development | BSDD | TBG | Identify and Document Integration Points | 100% | 0% | In Progress | Delayed | 2025-07-11 | 2025-07-17 | 5d | 226 |  |  | TBG/PIMS
1.3.1.3.4 | 5 |  |  |  | Payroll Systems Integration | 100% | 17% |  |  | 2025-07-11 | 2025-07-18 | 6d
1.3.1.3.4.1 | 6 | Pre-Development | BSDD | Other Dept | Engagement with Payroll System Team | 100% | 100% | Complete | Delayed | 2025-07-11 | 2025-07-11 | 1d | 226 |  |  | TBG/PIU
1.3.1.3.4.2 | 6 | Pre-Development | BSDD | TBG | Identify and Document Integration Points | 100% | 0% | In Progress | Delayed | 2025-07-14 | 2025-07-18 | 5d | 229 |  |  | TBG/Payroll
1.3.1.3.7 | 5 |  |  |  | ASYCUDA Integration | 100% | 25% |  |  | 2025-07-14 | 2025-07-21 | 6d
1.3.1.3.7.1 | 6 | Pre-Development | BSDD | Other Dept | Engagement with ASYCUDA Team | 100% | 50% | In Progress | Delayed | 2025-07-14 | 2025-07-14 | 1d | 229 |  |  | TBG/PIU
1.3.1.3.7.2 | 6 | Pre-Development | BSDD | TBG | Identify and Document Integration Points | 100% | 20% | In Progress | Delayed | 2025-07-15 | 2025-07-21 | 5d | 232 |  |  | TBG/ASYCUDA
1.3.1.3.8 | 5 |  |  |  | FINLINK Integration | 100% | 38% |  |  | 2025-07-15 | 2025-07-22 | 6d
1.3.1.3.8.1 | 6 | Pre-Development | BSDD | FITD | Engagement with Banking Systems Team | 100% | 75% | In Progress | Delayed | 2025-07-15 | 2025-07-15 | 1d | 232 |  |  | TBG/PIU
1.3.1.3.8.2 | 6 | Pre-Development | BSDD | TBG | Identify and Document Integration Points | 100% | 30% | In Progress | Delayed | 2025-07-16 | 2025-07-22 | 5d | 235 |  |  | TBG/Banks
1.3.1.3.10 | 5 |  |  |  | AMIS (Asset Department) |  | 0% |  |  | 2025-07-16 | 2025-07-23 | 6d
1.3.1.3.10.1 | 6 | Pre-Development | BSDD | Other Dept | Engagement with AMIS Team | 100% | 0% | In Progress | Delayed | 2025-07-16 | 2025-07-16 | 1d | 235 |  |  | TBG/PIU
1.3.1.3.10.2 | 6 | Pre-Development | BSDD | TBG | Identify and Document Integration Points | 100% | 0% | Not Started | Delayed | 2025-07-17 | 2025-07-23 | 5d | 238 |  |  | TBG/AMIS
1.3.1.3.11 | 5 |  |  |  | Any Other System Identified |  | 58% |  |  | 2025-07-17 | 2025-07-24 | 6d
1.3.1.3.11.1 | 6 | Pre-Development | BSDD | Other Dept | Engagement with concerned Team | 100% | 100% | Complete | Delayed | 2025-07-17 | 2025-07-17 | 1d | 238 |  |  | TBG/PIU
1.3.1.3.11.2 | 6 | Pre-Development | BSDD | TBG | Identify and Document Integration Points | 100% | 50% | In Progress | Delayed | 2025-07-18 | 2025-07-24 | 5d | 241 |  |  | TBG/PIU
1.3.1.4 | 4 |  |  |  | Finalizing Requirement Traceability Matrix | 97% | 50% |  |  | 2025-08-22 | 2025-09-24 | 24d
1.3.1.4.1 | 5 | Pre-Development | BSDD | TBG | Updating and Finalizing Requirement Traceability Matrix | 100% | 50% | In Progress | Delayed | 2025-08-22 | 2025-09-24 | 24d
1.3.1.5 | 4 |  |  |  | Report Traceability Matrix Preparation | 100% | 10% |  |  | 2025-08-22 | 2025-09-24 | 24d
1.3.1.5.1 | 5 | Pre-Development | BSDD | TBG | Preparation of Report Traceability Matrix | 100% | 10% | In Progress | Delayed | 2025-08-22 | 2025-09-24 | 24d | 244SS |  |  | TBG
1.3.2 | 3 |  |  |  | Business Solution Design Documentation | 100% | 23% |  |  | 2025-07-15 | 2025-11-26 | 97d
1.3.2.1 | 4 | Pre-Development | BSDD | TBG | Design Overall Solution Architecture | 100% | 50% | Complete | Delayed | 2025-07-15 | 2025-08-25 | 30d |  |  |  | TBG
| 4 | Pre-Development | BSDD | PMC | Review of Solution Architecture | 100% | 70% | In Progress | Delayed | 2025-08-26 | 2025-09-08 | 10d | 248
| 4 | Pre-Development | BSDD | TBG | Incorporating feedback and resubmission | 100% | 0% | Not Started | Delayed | 2025-09-09 | 2025-09-17 | 7d | 249
1.3.2.2 | 4 |  |  |  | Integration Design Documentation |  | 17% |  |  | 2025-07-15 | 2025-09-08 | 40d
1.3.2.2.1 | 5 |  |  |  | DMFAS Integration Design |  | 38% |  |  | 2025-07-15 | 2025-08-28 | 33d
1.3.2.2.1.1 | 6 | Pre-Development | BSDD | TBG | IFMIS-DMFAS Design Preparation | 100% | 50% | In Progress | Delayed | 2025-07-15 | 2025-08-04 | 15d | 218 |  |  | TBG
1.3.2.2.1.2 | 6 | Pre-Development | BSDD | TBG | Design Review Meeting | 100% | 0% | Not Started | Delayed | 2025-08-05 | 2025-08-18 | 10d | 253 |  |  | TBG/PIU/DMFAS
1.3.2.2.1.3 | 6 | Pre-Development | BSDD | TBG | Finalize Design Document | 100% | 0% | Not Started | Delayed | 2025-08-07 | 2025-08-18 | 8d | 254SS +2d |  |  | TBG
1.3.2.2.1.4 | 6 | Pre-Development | BSDD | PMC | Review of Design Document | 100% | 100% | Complete | On Time | 2025-08-19 | 2025-08-28 | 8d | 255 |  |  | TBG/PIU/DMFAS
1.3.2.2.1.5 | 6 | Pre-Development | BSDD | IFMIS Committee | Approval of Design Document | 100% | 0% | Not Started | Delayed | 2025-08-28 | 2025-08-28 | 0 | 256 |  |  | PIU
1.3.2.2.2 | 5 |  |  |  | TMIS & TaxRIS Integration Design |  | 38% |  |  | 2025-07-16 | 2025-08-29 | 33d
1.3.2.2.2.2 | 6 | Pre-Development | BSDD | TBG | IFMIS-TaxRIS Design Preparation | 100% | 50% | In Progress | Delayed | 2025-07-16 | 2025-08-05 | 15d | 221 |  |  | TBG
1.3.2.2.2.4 | 6 | Pre-Development | BSDD | TBG | Design Review Meeting - TaxRIS | 100% | 0% | Not Started | Delayed | 2025-08-06 | 2025-08-19 | 10d | 259 |  |  | TBG/PIU/TaxRIS
1.3.2.2.2.5 | 6 | Pre-Development | BSDD | TBG | Finalize Design Document | 100% | 0% | Not Started | Delayed | 2025-08-08 | 2025-08-19 | 8d | 260SS +2d |  |  | TBG
1.3.2.2.2.6 | 6 | Pre-Development | BSDD | PMC | Review of Design Document | 100% | 100% | Complete | On Time | 2025-08-20 | 2025-08-29 | 8d | 261 |  |  | PIU/TMIS/TaxRIS
1.3.2.2.2.7 | 6 | Pre-Development | BSDD | IFMIS Committee | Approval of Design Document | 100% | 0% | Not Started | Delayed | 2025-08-29 | 2025-08-29 | 0 | 262 |  |  | PIU
1.3.2.2.3 | 5 |  |  |  | PIMS Integration Design | 36% | 0% |  |  | 2025-07-18 | 2025-09-02 | 33d
1.3.2.2.3.1 | 6 | Pre-Development | BSDD | TBG | IFMIS-PMIS Design Preparation | 100% | 0% | Not Started | Delayed | 2025-07-18 | 2025-08-07 | 15d | 227 |  |  | TBG
1.3.2.2.3.2 | 6 | Pre-Development | BSDD | TBG | Design Review Meeting | 100% | 0% | Not Started | Delayed | 2025-08-08 | 2025-08-21 | 10d | 265 |  |  | TBG/PIU/PIMS
1.3.2.2.3.3 | 6 | Pre-Development | BSDD | TBG | Finalize Design Document | 100% | 0% | Not Started | Delayed | 2025-08-12 | 2025-08-21 | 8d | 266SS +2d |  |  | TBG
1.3.2.2.3.4 | 6 | Pre-Development | BSDD | FITD | Review of Design Document | 100% | 0% | Not Started | Delayed | 2025-08-22 | 2025-09-02 | 8d | 267 |  |  | PIU/PIMS
1.3.2.2.3.5 | 6 | Pre-Development | BSDD | IFMIS Committee | Approval of Design Document | 100% | 0% | Not Started | Delayed | 2025-09-02 | 2025-09-02 | 0 | 268 |  |  | PIU
1.3.2.2.4 | 5 |  |  |  | Payroll Systems Integration Design (Various Ministries) | 33% | 7% |  |  | 2025-07-21 | 2025-09-03 | 33d
1.3.2.2.4.1 | 6 | Pre-Development | BSDD | TBG | IFMIS-Payroll Systems Design Preparation | 100% | 20% | In Progress | Delayed | 2025-07-21 | 2025-08-08 | 15d | 230 |  |  | TBG
1.3.2.2.4.2 | 6 | Pre-Development | BSDD | TBG | Design Review Meeting | 100% | 0% | Not Started | Delayed | 2025-08-11 | 2025-08-22 | 10d | 271 |  |  | TBG/PIU/Payroll
1.3.2.2.4.3 | 6 | Pre-Development | BSDD | TBG | Finalize Design Document | 100% | 0% | Not Started | Delayed | 2025-08-13 | 2025-08-22 | 8d | 272SS +2d |  |  | TBG
1.3.2.2.4.4 | 6 | Pre-Development | BSDD | FITD | Review of Design Document | 100% | 0% | Not Started | Delayed | 2025-08-25 | 2025-09-03 | 8d | 273 |  |  | TBG/PIU/Payroll
1.3.2.2.4.5 | 6 | Pre-Development | BSDD | IFMIS Committee | Approval of Design Document | 0% | 0% | Not Started | Delayed | 2025-09-03 | 2025-09-03 | 0 | 274 |  |  | PIU
1.3.2.2.7 | 5 |  |  |  | ASYCUDA Integration Design |  | 27% |  |  | 2025-07-22 | 2025-09-04 | 33d
1.3.2.2.7.1 | 6 | Pre-Development | BSDD | TBG | IFMIS-ASYCUDA Design Preparation | 100% | 20% | In Progress | Delayed | 2025-07-22 | 2025-08-11 | 15d | 233 |  |  | TBG
1.3.2.2.7.2 | 6 | Pre-Development | BSDD | TBG | Design Review Meeting | 100% | 0% | Not Started | Delayed | 2025-08-12 | 2025-08-25 | 10d | 277 |  |  | TBG/PIU/ASYCUDA
1.3.2.2.7.3 | 6 | Pre-Development | BSDD | TBG | Finalize Design Document | 100% | 0% | Not Started | Delayed | 2025-08-14 | 2025-08-25 | 8d | 278SS +2d |  |  | TBG
1.3.2.2.7.4 | 6 | Pre-Development | BSDD | FITD | Review of Design Document | 100% | 100% | Complete | On Time | 2025-08-26 | 2025-09-04 | 8d | 279 |  |  | PIU/ASYCUDA
1.3.2.2.7.5 | 6 | Pre-Development | BSDD | IFMIS Committee | Approval of Design Document | 0% | 0% | Not Started | Delayed | 2025-09-04 | 2025-09-04 | 0 | 280 |  |  | PIU
1.3.2.2.8 | 5 |  |  |  | Banking Systems Integration Design |  | 11% |  |  | 2025-07-23 | 2025-09-05 | 33d
1.3.2.2.8.1 | 6 | Pre-Development | BSDD | TBG | IFMIS-Banking Systems Design Preparation | 100% | 30% | In Progress | Delayed | 2025-07-23 | 2025-08-12 | 15d | 236 |  |  | TBG
1.3.2.2.8.2 | 6 | Pre-Development | BSDD | TBG | Design Review Meeting | 100% | 0% | Not Started | Delayed | 2025-08-13 | 2025-08-26 | 10d | 283 |  |  | TBG/PIU/Banks
1.3.2.2.8.3 | 6 | Pre-Development | BSDD | TBG | Finalize Design Document | 100% | 0% | Not Started | Delayed | 2025-08-15 | 2025-08-26 | 8d | 284SS +2d |  |  | TBG
1.3.2.2.8.4 | 6 | Pre-Development | BSDD | FITD | Review of Design Document | 100% | 0% | Not Started | Delayed | 2025-08-27 | 2025-09-05 | 8d | 285 |  |  | PIU/Banks
1.3.2.2.8.5 | 6 | Pre-Development | BSDD | IFMIS Committee | Approval of Design Document | 0% | 0% | Not Started | Delayed | 2025-09-05 | 2025-09-05 | 0 | 286 |  |  | PIU
1.3.2.2.10 | 5 |  |  |  | AMIS (Asset Department - Future) Integration Design |  | 0% |  |  | 2025-07-24 | 2025-09-08 | 33d
1.3.2.2.10.1 | 6 | Pre-Development | BSDD | TBG | IFMIS-AMIS Design Preparation | 100% | 0% | In Progress | Delayed | 2025-07-24 | 2025-08-13 | 15d | 239 |  |  | TBG
1.3.2.2.10.2 | 6 | Pre-Development | BSDD | TBG | Design Review Meeting | 100% | 0% | Not Started | Delayed | 2025-08-14 | 2025-08-27 | 10d | 289 |  |  | TBG/PIU/AMIS
1.3.2.2.10.3 | 6 | Pre-Development | BSDD | TBG | Finalize Design Document | 100% | 0% | Not Started | Delayed | 2025-08-18 | 2025-08-27 | 8d | 290SS +2d |  |  | TBG
1.3.2.2.10.4 | 6 | Pre-Development | BSDD | State Asset Dept | Review of Design Document | 100% | 0% | Not Started | Delayed | 2025-08-28 | 2025-09-08 | 8d | 291 |  |  | PIU/AMIS
1.3.2.2.10.5 | 6 | Pre-Development | BSDD | IFMIS Committee | Approval of Design Document | 100% | 0% | Not Started | Delayed | 2025-09-08 | 2025-09-08 | 0 | 292 |  |  | PIU
1.3.2.2.11 | 5 | Pre-Development | BSDD | TBG | Integration Design Documentation Submission | 100% | 0% | Not Started | Delayed | 2025-09-08 | 2025-09-08 | 0 | 293 |  |  | TBG
1.3.2.3 | 4 |  |  |  | Business Continuity Plan (BCP) |  | 25% |  |  | 2025-08-26 | 2025-09-22 | 20d
1.3.2.3.1 | 5 | Pre-Development | BSDD | TBG | Initiation and Risk Assessment | 100% | 50% | In Progress | Delayed | 2025-08-26 | 2025-09-01 | 5d | 248
1.3.2.3.2 | 5 | Pre-Development | BSDD | TBG | Design Business Continuity Plan (BCP) Strategy | 100% | 50% | In Progress | Delayed | 2025-09-02 | 2025-09-08 | 5d | 296
1.3.2.3.3 | 5 | Pre-Development | BSDD | TBG | Develop Plan and Finalize Tools | 100% | 0% | Not Started | Delayed | 2025-09-09 | 2025-09-12 | 4d | 297
1.3.2.3.4 | 5 | Pre-Development | BSDD | FITD | Review and Sign Off | 100% | 0% | Not Started | Delayed | 2025-09-15 | 2025-09-22 | 6d | 298
1.3.2.4 | 4 |  |  |  | Finalizing Consolidated BSDD |  | 7% |  |  | 2025-09-12 | 2025-11-26 | 53.5d
1.3.2.4.1 | 5 | Pre-Development | BSDD | TBG | Consolidating To Be Process for all Components | 100% | 10% | In Progress | Delayed | 2025-09-12 | 2025-10-24 | 30d | 141FS +1d |  |  | TBG
1.3.2.4.2 | 5 | Pre-Development | BSDD | TBG | Incorporating Integration Design | 100% | 10% | In Progress | Delayed | 2025-09-26 | 2025-10-17 | 15d | 301SS +10d |  |  | TBG
1.3.2.4.3 | 5 | Pre-Development | BSDD | TBG | Incorporating Solution Architecture Design | 100% | 10% | In Progress | Delayed | 2025-09-26 | 2025-10-17 | 15d | 301SS +10d |  |  | TBG
1.3.2.4.4 | 5 | Pre-Development | BSDD | TBG | Submission of Draft BSDD (Both Languages) | 0% | 0% | Not Started | Delayed | 2025-10-20 | 2025-10-20 | 0.5d | 303FS +1d |  |  | TBG
1.3.2.4.5 | 5 | Pre-Development | BSDD | TBG | Presentation of BSDD to MoF Stakeholders | 0% | 0% | Not Started | Delayed | 2025-10-22 | 2025-10-28 | 5d | 304FS +1d |  |  | TBG
1.3.2.4.6 | 5 | Pre-Development | BSDD | PMC | Review of BSDD | 0% | 0% | Not Started | Delayed | 2025-10-22 | 2025-11-11 | 15d | 304FS +1d |  |  | PIU/TBA
1.3.2.4.7 | 5 | Pre-Development | BSDD | TBG | Review Comment Incorporation | 0% | 0% | Not Started | Delayed | 2025-11-12 | 2025-11-25 | 10d | 306 |  |  | TBG
1.3.2.4.8 | 5 | Pre-Development | BSDD | TBG | Final BSDD Submission | 0% | 0% | Not Started | Delayed | 2025-11-26 | 2025-11-26 | 1d | 307 |  |  | TBG
1.3.2.4.9 | 5 | Pre-Development | BSDD | IFMIS Committee | Business Solution Design Document (BSDD) Sign Off | 0% | 0% | Not Started | Delayed | 2025-11-26 | 2025-11-26 | 0 | 308 |  |  | PIU
1.3.3 | 3 |  |  |  | Cloud Service Provision (IaaS) |  | 0% |  |  | 2025-10-20 | 2025-10-24 | 5d
1.3.3.1 | 4 | Development |  | TBG | Provisioning of cloud services for hosting the development version of IFMIS |  | 0% | Complete | On Time | 2025-10-20 | 2025-10-24 | 5d |  |  |  | TBG
1.3.4 | 2 |  |  |  | Development Stage |  | 0% |  |  | 2025-08-19 | 2026-12-29 | 356d
1.3.4.1 | 3 | Development |  |  | Development environment Setup and Configuration |  | 0% | Not Started |  | 2025-10-27 | 2025-10-31 | 5d | 311
1.3.4.2 | 3 |  |  |  | CRP1: Standard Solution Validation |  | 0% |  |  | 2025-10-27 | 2026-02-09 | 76d
1.3.4.2.1 | 4 | Development |  |  | CRP Sessions Planning and Preparation |  | 0% | Not Started |  | 2025-10-27 | 2025-10-31 | 5d | 311
1.3.4.2.2 | 4 |  |  |  | Budget Preparation to Management Process |  | 0% |  |  | 2025-11-27 | 2026-01-05 | 28d
1.3.4.2.2.1 | 5 | Development |  |  | Setup and Configuration |  | 0% | Not Started |  | 2025-11-27 | 2025-12-31 | 25d | 308
1.3.4.2.2.2 | 5 | Development |  |  | Conducting CRP Sessions |  | 0% | Not Started |  | 2025-12-05 | 2026-01-01 | 20d | 317SS +6d
1.3.4.2.2.3 | 5 | Development |  |  | Documenting Gaps and Feedbacks |  | 0% | Not Started |  | 2025-12-09 | 2026-01-05 | 20d | 318SS +2d
1.3.4.2.3 | 4 |  |  |  | Procurement |  | 0% |  |  | 2025-11-27 | 2026-01-05 | 28d
1.3.4.2.3.1 | 5 | Development |  |  | Setup and Configuration |  | 0% | Not Started |  | 2025-11-27 | 2025-12-31 | 25d | 317SS
1.3.4.2.3.2 | 5 | Development |  |  | Conducting CRP Sessions |  | 0% | Not Started |  | 2025-12-05 | 2026-01-01 | 20d | 321SS +6d
1.3.4.2.3.3 | 5 | Development |  |  | Documenting Gaps and Feedbacks |  | 0% | Not Started |  | 2025-12-09 | 2026-01-05 | 20d | 322SS +2d
1.3.4.2.4 | 4 |  |  |  | Bill Creation and Processing |  | 0% |  |  | 2025-11-27 | 2025-12-22 | 18d
1.3.4.2.4.1 | 5 | Development |  |  | Setup and Configuration |  | 0% | Not Started |  | 2025-11-27 | 2025-12-17 | 15d | 321SS
1.3.4.2.4.2 | 5 | Development |  |  | Conducting CRP Sessions |  | 0% | Not Started |  | 2025-12-05 | 2025-12-18 | 10d | 325SS +6d
1.3.4.2.4.3 | 5 | Development |  |  | Documenting Gaps and Feedbacks |  | 0% | Not Started |  | 2025-12-09 | 2025-12-22 | 10d | 326SS +2d
1.3.4.2.5 | 4 |  |  |  | Cash Planning and Commitment Process |  | 0% |  |  | 2025-11-27 | 2026-01-05 | 28d
1.3.4.2.5.1 | 5 | Development |  |  | Setup and Configuration |  | 0% | Not Started |  | 2025-11-27 | 2025-12-31 | 25d | 325SS
1.3.4.2.5.2 | 5 | Development |  |  | Conducting CRP Sessions |  | 0% | Not Started |  | 2025-12-05 | 2026-01-01 | 20d | 329SS +6d
1.3.4.2.5.3 | 5 | Development |  |  | Documenting Gaps and Feedbacks |  | 0% | Not Started |  | 2025-12-09 | 2026-01-05 | 20d | 330SS +2d
1.3.4.2.6 | 4 |  |  |  | Asset Management Process |  | 0% |  |  | 2025-12-18 | 2026-01-12 | 18d
1.3.4.2.6.1 | 5 | Development |  |  | Setup and Configuration |  | 0% | Not Started |  | 2025-12-18 | 2026-01-07 | 15d | 329SS +15d
1.3.4.2.6.2 | 5 | Development |  |  | Conducting CRP Sessions |  | 0% | Not Started |  | 2025-12-26 | 2026-01-08 | 10d | 333SS +6d
1.3.4.2.6.3 | 5 | Development |  |  | Documenting Gaps and Feedbacks |  | 0% | Not Started |  | 2025-12-30 | 2026-01-12 | 10d | 334SS +2d
1.3.4.2.7 | 4 |  |  |  | Accounting to Reconciliation Process |  | 0% |  |  | 2026-01-01 | 2026-02-09 | 28d
1.3.4.2.7.1 | 5 | Development |  |  | Setup and Configuration |  | 0% | Not Started |  | 2026-01-01 | 2026-02-04 | 25d | 329
1.3.4.2.7.2 | 5 | Development |  |  | Conducting CRP Sessions |  | 0% | Not Started |  | 2026-01-09 | 2026-02-05 | 20d | 337SS +6d
1.3.4.2.7.3 | 5 | Development |  |  | Documenting Gaps and Feedbacks |  | 0% | Not Started |  | 2026-01-13 | 2026-02-09 | 20d | 338SS +2d
1.3.4.3 | 3 |  |  |  | Enhancement of CRP1 Gaps Identified |  | 0% |  |  | 2025-12-23 | 2026-03-09 | 55d
1.3.4.3.1 | 4 | Development |  |  | Enhancements on Budget Preparation to Management Gaps |  | 0% | Not Started |  | 2026-01-06 | 2026-02-02 | 20d | 319
1.3.4.3.2 | 4 | Development |  |  | Enhancements on Procure to Pay Gaps |  | 0% | Not Started |  | 2026-01-06 | 2026-02-02 | 20d | 323
1.3.4.3.3 | 4 | Development |  |  | Enhancements on Receipt to Cash Gaps |  | 0% | Not Started |  | 2025-12-23 | 2026-01-12 | 15d | 327
1.3.4.3.4 | 4 | Development |  |  | Enhancements on Cash Planning and Commitment Gaps |  | 0% | Not Started |  | 2026-01-06 | 2026-02-09 | 25d | 331
1.3.4.3.5 | 4 | Development |  |  | Enhancements on Asset Management Gaps |  | 0% | Not Started |  | 2026-01-13 | 2026-02-09 | 20d | 335
1.3.4.3.6 | 4 | Development |  |  | Enhancements on Accounting to Reconciliation Gaps |  | 0% | Not Started |  | 2026-02-10 | 2026-03-09 | 20d | 339
1.3.4.4 | 3 |  |  |  | Report Development |  | 0% |  |  | 2025-11-27 | 2026-03-04 | 70d
1.3.4.4.1 | 4 | Development |  |  | Custom Report Develoment activities as per the RRTM |  | 0% | Not Started |  | 2025-11-27 | 2026-03-04 | 70d | 317SS
1.3.4.5 | 3 |  |  |  | CRP2: Enhanced Solution Validation Workshops |  | 0% |  |  | 2025-12-29 | 2026-03-25 | 63d
1.3.4.5.1 | 4 | Development |  |  | CRP2 Sessions Planning and Preparation |  | 0% | Not Started |  | 2025-12-29 | 2026-01-02 | 5d
1.3.4.5.2 | 4 | Development |  |  | Budget Preparation to Management process gap validation |  | 0% | Not Started |  | 2026-02-05 | 2026-02-18 | 10d | 341FS +2d
1.3.4.5.3 | 4 | Development |  |  | Procure to Pay process validation workshop |  | 0% | Not Started |  | 2026-02-05 | 2026-02-18 | 10d | 342FS +2d
1.3.4.5.4 | 4 | Development |  |  | Receipt to Cash process validation workshop |  | 0% | Not Started |  | 2026-01-15 | 2026-01-26 | 8d | 343FS +2d
1.3.4.5.5 | 4 | Development |  |  | Cash Planning and Commitment process validation workshop |  | 0% | Not Started |  | 2026-02-12 | 2026-02-25 | 10d | 344FS +2d
1.3.4.5.6 | 4 | Development |  |  | Asset Management process gap validation workshop |  | 0% | Not Started |  | 2026-02-12 | 2026-02-25 | 10d | 345FS +2d
1.3.4.5.7 | 4 | Development |  |  | Accounting to Reconciliation procss gap validation workshop |  | 0% | Not Started |  | 2026-03-12 | 2026-03-25 | 10d | 346FS +2d
1.3.4.5.8 | 4 | Development |  |  | Documentation of Gaps and Feedbacks |  | 0% | Not Started |  | 2026-02-09 | 2026-02-24 | 12d | 351SS +2d
1.3.4.6 | 3 |  |  |  | Integration Development |  | 0% |  |  | 2025-08-19 | 2025-11-14 | 64d
1.3.4.6.1 | 4 |  |  |  | DMFAS Integration Development |  | 0% |  |  | 2025-08-29 | 2025-11-06 | 50d
1.3.4.6.1.1 | 5 | Development |  |  | Design of Integration (API) Specification |  | 0% | Not Started |  | 2025-08-29 | 2025-09-11 | 10d | 257
1.3.4.6.1.2 | 5 | Development |  |  | Prepare of Sandbox environment |  | 0% | Not Started |  | 2025-08-29 | 2025-09-11 | 10d | 360SS
1.3.4.6.1.3 | 5 | Development |  |  | Integrations Development |  | 0% | Not Started |  | 2025-09-12 | 2025-10-16 | 25d | 360
1.3.4.6.1.4 | 5 | Development |  |  | Integrations Unit/Internal Testing |  | 0% | Not Started |  | 2025-10-17 | 2025-10-30 | 10d | 362
1.3.4.6.1.5 | 5 | Development |  |  | Finalizing Integrations & Test Script Preparation |  | 0% | Not Started |  | 2025-10-31 | 2025-11-06 | 5d | 363
1.3.4.6.2 | 4 |  |  |  | TMIS & TaxRIS Integration Development |  | 0% |  |  | 2025-09-01 | 2025-11-07 | 50d
1.3.4.6.2.1 | 5 | Development |  |  | Design of Integration (API) Specification |  | 0% | Not Started |  | 2025-09-01 | 2025-09-12 | 10d | 263
1.3.4.6.2.2 | 5 | Development |  |  | Prepare of Sandbox environment |  | 0% | Not Started |  | 2025-09-01 | 2025-09-12 | 10d | 366SS
1.3.4.6.2.3 | 5 | Development |  |  | Integrations Development |  | 0% | Not Started |  | 2025-09-15 | 2025-10-17 | 25d | 366
1.3.4.6.2.4 | 5 | Development |  |  | Integrations Unit/Internal Testing |  | 0% | Not Started |  | 2025-10-20 | 2025-10-31 | 10d | 368
1.3.4.6.2.5 | 5 | Development |  |  | Finalizing Integrations & Test Script Preparation |  | 0% | Not Started |  | 2025-11-03 | 2025-11-07 | 5d | 369
1.3.4.6.3 | 4 |  |  |  | PIMS Integration Development |  | 0% |  |  | 2025-09-03 | 2025-11-11 | 50d
1.3.4.6.3.1 | 5 | Development |  |  | Design of Integration (API) Specification |  | 0% | Not Started |  | 2025-09-03 | 2025-09-16 | 10d | 269
1.3.4.6.3.2 | 5 | Development |  |  | Prepare of Sandbox environment |  | 0% | Not Started |  | 2025-09-03 | 2025-09-16 | 10d | 372SS
1.3.4.6.3.3 | 5 | Development |  |  | Integrations Development |  | 0% | Not Started |  | 2025-09-17 | 2025-10-21 | 25d | 372
1.3.4.6.3.4 | 5 | Development |  |  | Integrations Unit/Internal Testing |  | 0% | Not Started |  | 2025-10-22 | 2025-11-04 | 10d | 374
1.3.4.6.3.5 | 5 | Development |  |  | Finalizing Integrations & Test Script Preparation |  | 0% | Not Started |  | 2025-11-05 | 2025-11-11 | 5d | 375
1.3.4.6.4 | 4 |  |  |  | Payroll Systems Ingegration Development |  | 0% |  |  | 2025-09-04 | 2025-11-12 | 50d
1.3.4.6.4.1 | 5 | Development |  |  | Design of Integration (API) Specification |  | 0% | Not Started |  | 2025-09-04 | 2025-09-17 | 10d | 275
1.3.4.6.4.2 | 5 | Development |  |  | Prepare of Sandbox environment |  | 0% | Not Started |  | 2025-09-04 | 2025-09-17 | 10d | 378SS
1.3.4.6.4.3 | 5 | Development |  |  | Integrations Development |  | 0% | Not Started |  | 2025-09-18 | 2025-10-22 | 25d | 378
1.3.4.6.4.4 | 5 | Development |  |  | Integrations Unit/Internal Testing |  | 0% | Not Started |  | 2025-10-23 | 2025-11-05 | 10d | 380
1.3.4.6.4.5 | 5 | Development |  |  | Finalizing Integrations & Test Script Preparation |  | 0% | Not Started |  | 2025-11-06 | 2025-11-12 | 5d | 381
1.3.4.6.5 | 4 |  |  |  | SmartTax Integration Development |  | 0% |  |  | 2025-08-19 | 2025-10-27 | 50d
1.3.4.6.5.1 | 5 | Development |  |  | Design of Integration (API) Specification |  | 0% | Not Started |  | 2025-08-19 | 2025-09-01 | 10d | #REF
1.3.4.6.5.2 | 5 | Development |  |  | Prepare of Sandbox environment |  | 0% | Not Started |  | 2025-08-19 | 2025-09-01 | 10d | 384SS
1.3.4.6.5.3 | 5 | Development |  |  | Integrations Development |  | 0% | Not Started |  | 2025-09-02 | 2025-10-06 | 25d | 384
1.3.4.6.5.4 | 5 | Development |  |  | Integrations Unit/Internal Testing |  | 0% | Not Started |  | 2025-10-07 | 2025-10-20 | 10d | 386
1.3.4.6.5.5 | 5 | Development |  |  | Finalizing Integrations & Test Script Preparation |  | 0% | Not Started |  | 2025-10-21 | 2025-10-27 | 5d | 387
1.3.4.6.6 | 4 |  |  |  | EasyTax Integration Development |  | 0% |  |  | 2025-08-20 | 2025-10-28 | 50d
1.3.4.6.6.1 | 5 | Development |  |  | Design of Integration (API) Specification |  | 0% | Not Started |  | 2025-08-20 | 2025-09-02 | 10d | #REF
1.3.4.6.6.2 | 5 | Development |  |  | Prepare of Sandbox environment |  | 0% | Not Started |  | 2025-08-20 | 2025-09-02 | 10d | 390SS
1.3.4.6.6.3 | 5 | Development |  |  | Integrations Development |  | 0% | Not Started |  | 2025-09-03 | 2025-10-07 | 25d | 390
1.3.4.6.6.4 | 5 | Development |  |  | Integrations Unit/Internal Testing |  | 0% | Not Started |  | 2025-10-08 | 2025-10-21 | 10d | 392
1.3.4.6.6.5 | 5 | Development |  |  | Finalizing Integrations & Test Script Preparation |  | 0% | Not Started |  | 2025-10-22 | 2025-10-28 | 5d | 393
1.3.4.6.7 | 4 |  |  |  | ASYCUDA Integration Development |  | 0% |  |  | 2025-09-05 | 2025-11-13 | 50d
1.3.4.6.7.1 | 5 | Development |  |  | Design of Integration (API) Specification |  | 0% | Not Started |  | 2025-09-05 | 2025-09-18 | 10d | 281
1.3.4.6.7.2 | 5 | Development |  |  | Prepare of Sandbox environment |  | 0% | Not Started |  | 2025-09-05 | 2025-09-18 | 10d | 396SS
1.3.4.6.7.3 | 5 | Development |  |  | Integrations Development |  | 0% | Not Started |  | 2025-09-19 | 2025-10-23 | 25d | 396
1.3.4.6.7.4 | 5 | Development |  |  | Integrations Unit/Internal Testing |  | 0% | Not Started |  | 2025-10-24 | 2025-11-06 | 10d | 398
1.3.4.6.7.5 | 5 | Development |  |  | Finalizing Integrations & Test Script Preparation |  | 0% | Not Started |  | 2025-11-07 | 2025-11-13 | 5d | 399
1.3.4.6.8 | 4 |  |  |  | Banking Systems Integration Development |  | 0% |  |  | 2025-09-08 | 2025-11-14 | 50d
1.3.4.6.8.1 | 5 | Development |  |  | Design of Integration (API) Specification |  | 0% | Not Started |  | 2025-09-08 | 2025-09-19 | 10d | 287
1.3.4.6.8.2 | 5 | Development |  |  | Prepare of Sandbox environment |  | 0% | Not Started |  | 2025-09-08 | 2025-09-19 | 10d | 402SS
1.3.4.6.8.3 | 5 | Development |  |  | Integrations Development |  | 0% | Not Started |  | 2025-09-22 | 2025-10-24 | 25d | 402
1.3.4.6.8.4 | 5 | Development |  |  | Integrations Unit/Internal Testing |  | 0% | Not Started |  | 2025-10-27 | 2025-11-07 | 10d | 404
1.3.4.6.8.5 | 5 | Development |  |  | Finalizing Integrations & Test Script Preparation |  | 0% | Not Started |  | 2025-11-10 | 2025-11-14 | 5d | 405
1.3.4.6.9 | 4 |  |  |  | E-Procurement Portal Integration Development |  | 0% |  |  | 2025-08-25 | 2025-10-31 | 50d
1.3.4.6.9.1 | 5 | Development |  |  | Design of Integration (API) Specification |  | 0% | Not Started |  | 2025-08-25 | 2025-09-05 | 10d | #REF
1.3.4.6.9.2 | 5 | Development |  |  | Prepare of Sandbox environment |  | 0% | Not Started |  | 2025-08-25 | 2025-09-05 | 10d | 408SS
1.3.4.6.9.3 | 5 | Development |  |  | Integrations Development |  | 0% | Not Started |  | 2025-09-08 | 2025-10-10 | 25d | 408
1.3.4.6.9.4 | 5 | Development |  |  | Integrations Unit/Internal Testing |  | 0% | Not Started |  | 2025-10-13 | 2025-10-24 | 10d | 410
1.3.4.6.9.5 | 5 | Development |  |  | Finalizing Integrations & Test Script Preparation |  | 0% | Not Started |  | 2025-10-27 | 2025-10-31 | 5d | 411
1.3.4.6.10 | 4 |  |  |  | AMIS (Asset Department) Development |  | 0% |  |  | 2025-09-09 | 2025-11-03 | 40d
1.3.4.6.10.1 | 5 | Development |  |  | Design of Integration (API) Specification |  | 0% | Not Started |  | 2025-09-09 | 2025-09-18 | 8d | 293
1.3.4.6.10.2 | 5 | Development |  |  | Prepare of Sandbox environment |  | 0% | Not Started |  | 2025-09-09 | 2025-09-18 | 8d | 414SS
1.3.4.6.10.3 | 5 | Development |  |  | Integrations Development |  | 0% | Not Started |  | 2025-09-19 | 2025-10-16 | 20d | 414
1.3.4.6.10.4 | 5 | Development |  |  | Integrations Unit/Internal Testing |  | 0% | Not Started |  | 2025-10-17 | 2025-10-28 | 8d | 416
1.3.4.6.10.5 | 5 | Development |  |  | Finalizing Integrations & Test Script Preparation |  | 0% | Not Started |  | 2025-10-29 | 2025-11-03 | 4d | 417
1.3.4.6.11 | 4 | Development |  |  | Prepare Integration Component Completion Report |  | 0% | Not Started |  | 2025-11-03 | 2025-11-13 | 9d | 412
1.3.4.6.12 | 4 | Development |  |  | Development of Integration Layers for IFMIS Sign Off |  | 0% | Not Started |  | 2025-09-15 | 2025-09-18 | 4d | 409FS +5d
1.3.4.7 | 3 |  |  |  | CRP3: Solution Validation with Integration |  | 0% |  |  | 2025-09-19 | 2025-11-25 | 48d
1.3.4.7.1 | 4 | Development |  |  | CRP3 Sessions Detail Plan for each Integration Compoents |  | 0% | Not Started |  | 2025-09-19 | 2025-09-25 | 5d | 420
1.3.4.7.2 | 4 | Development |  |  | Integration Component Workshops |  | 0% | Not Started |  | 2025-09-26 | 2025-10-23 | 20d | 422
1.3.4.7.3 | 4 | Development |  |  | CRP2 Process Gaps Fix Verification for all Tracks |  | 0% | Not Started |  | 2025-10-24 | 2025-11-06 | 10d | 423
1.3.4.7.4 | 4 | Development |  |  | Documentation of Gaps and Feedbacks for All Components |  | 0% | Not Started |  | 2025-10-27 | 2025-11-14 | 15d | 424SS +1d
1.3.4.7.5 | 4 | Development |  |  | Enhancing and Fixing Reported Gaps |  | 0% | Not Started |  | 2025-10-07 | 2025-11-17 | 30d | 423SS +7d
1.3.4.7.6 | 4 | Development |  |  | Verifying Finalization of CRP Gaps |  | 0% | Not Started |  | 2025-11-18 | 2025-11-25 | 6d | 426
1.3.4.8 | 3 |  |  |  | End to End Solution Demo |  | 0% |  |  | 2025-12-01 | 2026-01-02 | 25d
1.3.4.8.1 | 4 | Development |  |  | Preparation for End to End Demonstration |  | 0% | Not Started |  | 2025-12-01 | 2025-12-05 | 5d | 427FS +3d
1.3.4.8.2 | 4 | Development |  |  | Identifying and communicating participants |  | 0% | Not Started |  | 2025-12-01 | 2025-12-05 | 5d | 429SS
1.3.4.8.3 | 4 | Development |  |  | Conducting End to End Demonstration |  | 0% | Not Started |  | 2025-12-11 | 2025-12-24 | 10d | 430FS +3d
1.3.4.8.4 | 4 | Development |  |  | Addressing gaps and feedbacks received |  | 0% | Not Started |  | 2025-12-15 | 2025-12-26 | 10d | 431SS +2d
1.3.4.8.5 | 4 | Development |  |  | Verifying the Closure of Development stage |  | 0% | Not Started |  | 2025-12-29 | 2026-01-02 | 5d | 432
1.3.4.9 | 3 |  |  |  | Testing/User Acceptance Testing (UAT) Stage |  | 0% |  |  | 2025-09-26 | 2026-05-19 | 168d
1.3.4.9.1 | 4 |  |  |  | Pre-Testing Preparation Activities |  | 0% |  |  | 2025-09-26 | 2026-02-24 | 108d
1.3.4.9.1.1 | 5 |  |  |  | Test Strategy and Plan |  | 0% |  |  | 2025-09-26 | 2025-11-11 | 33d
1.3.4.9.1.1.1 | 6 | Development |  |  | Preparation of Test Strategy and Plan |  | 0% | Not Started |  | 2025-09-26 | 2025-10-23 | 20d | 422
1.3.4.9.1.1.2 | 6 | Development |  |  | Test Strategy and Plan Review |  | 0% | Not Started |  | 2025-10-24 | 2025-11-06 | 10d | 437
1.3.4.9.1.1.3 | 6 | Development |  |  | Test Strategy and Plan Translation |  | 0% | Not Started |  | 2025-10-24 | 2025-10-30 | 5d | 438SS
1.3.4.9.1.1.4 | 6 | Development |  |  | Translated Test Strategy and Plan Review |  | 0% | Not Started |  | 2025-10-31 | 2025-11-11 | 8d | 439
1.3.4.9.1.1.5 | 6 | Development |  |  | Approval of Test Strategy and Plan |  | 0% | Not Started |  | 2025-11-11 | 2025-11-11 | 0 | 440
1.3.4.9.1.2 | 5 |  |  |  | DCM Strategy and Plan |  | 0% |  |  | 2025-09-26 | 2025-11-27 | 45d
1.3.4.9.1.2.1 | 6 | Development |  |  | Prepare DCM Strategy and Plan |  | 0% | Not Started |  | 2025-09-26 | 2025-10-23 | 20d | 437SS
1.3.4.9.1.2.2 | 6 | Development |  |  | DCM Strategy and Plan Review |  | 0% | Not Started |  | 2025-10-24 | 2025-11-06 | 10d | 443
1.3.4.9.1.2.3 | 6 | Development |  |  | DCM Strategy and Plan Translation |  | 0% | Not Started |  | 2025-10-24 | 2025-10-30 | 5d | 444SS
1.3.4.9.1.2.4 | 6 | Development |  |  | Translated DCM Strategy and Plan Review |  | 0% | Not Started |  | 2025-10-31 | 2025-11-11 | 8d | 445
1.3.4.9.1.2.5 | 6 | Development |  |  | Approval of DCM Strategy and Plan |  | 0% | Not Started |  | 2025-11-11 | 2025-11-11 | 0 | 446
1.3.4.9.1.2.6 | 6 | Development |  |  | Prepare DCM Templates |  | 0% | Not Started |  | 2025-10-24 | 2025-11-13 | 15d | 443
1.3.4.9.1.2.7 | 6 | Development |  |  | DCM Templates Review |  | 0% | Not Started |  | 2025-11-14 | 2025-11-27 | 10d | 448
1.3.4.9.1.2.8 | 6 | Development |  |  | Approval of DCM Templates |  | 0% | Not Started |  | 2025-11-27 | 2025-11-27 | 0 | 449
1.3.4.9.1.3 | 5 |  |  |  | Training Program |  | 0% |  |  | 2025-09-26 | 2025-12-04 | 50d
1.3.4.9.1.3.1 | 6 | Development |  |  | Prepare Training Program |  | 0% | Not Started |  | 2025-09-26 | 2025-11-06 | 30d | 443SS
1.3.4.9.1.3.2 | 6 | Development |  |  | Training Progream Review |  | 0% | Not Started |  | 2025-11-07 | 2025-11-27 | 15d | 452
1.3.4.9.1.3.3 | 6 | Development |  |  | Training Program Translation |  | 0% | Not Started |  | 2025-11-07 | 2025-11-20 | 10d | 453SS
1.3.4.9.1.3.4 | 6 | Development |  |  | Translated Training Program Review |  | 0% | Not Started |  | 2025-11-21 | 2025-12-04 | 10d | 454
1.3.4.9.1.3.5 | 6 | Development |  |  | Approval of Training Program |  | 0% | Not Started |  | 2025-12-04 | 2025-12-04 | 0 | 455
1.3.4.9.1.4 | 5 |  |  |  | Test Case and Test Script Preparation |  | 0% |  |  | 2025-11-12 | 2026-01-01 | 37d
1.3.4.9.1.4.1 | 6 | Development |  |  | Prepare Test Case and Test Script for each Tracks |  | 0% | Not Started |  | 2025-11-12 | 2025-12-09 | 20d | 441
1.3.4.9.1.4.2 | 6 | Development |  |  | Test Case and Test Script Review |  | 0% | Not Started |  | 2025-12-10 | 2025-12-23 | 10d | 458
1.3.4.9.1.4.3 | 6 | Development |  |  | Test Case and Test Script Translation |  | 0% | Not Started |  | 2025-12-10 | 2025-12-23 | 10d | 459SS
1.3.4.9.1.4.4 | 6 | Development |  |  | Translated Test Case and Test Script Review |  | 0% | Not Started |  | 2025-12-24 | 2026-01-01 | 7d | 460
1.3.4.9.1.4.5 | 6 | Development |  |  | Approval of Test Case and Test Script |  | 0% | Not Started |  | 2026-01-01 | 2026-01-01 | 0 | 461
1.3.4.9.1.5 | 5 | Development |  |  | Provisioning of the UAT Environment |  | 0% | Not Started |  | 2026-01-05 | 2026-01-13 | 7d | 433
1.3.4.9.1.6 | 5 | Development |  |  | Setup and Configuration of IFMIS Tracks |  | 0% | Not Started |  | 2026-01-14 | 2026-02-03 | 15d | 463
1.3.4.9.1.7 | 5 |  |  |  | Training of Testers |  | 0% |  |  | 2026-01-21 | 2026-02-24 | 25d
1.3.4.9.1.7.1 | 6 | Development |  |  | Tester Identification for each Track |  | 0% | Not Started |  | 2026-01-21 | 2026-01-27 | 5d | 464FS -10d
1.3.4.9.1.7.2 | 6 | Development |  |  | Prepare Tester Training Program |  | 0% | Not Started |  | 2026-01-21 | 2026-01-29 | 7d | 466SS
1.3.4.9.1.7.3 | 6 | Development |  |  | Conduct Testers Training and Practice for each Track |  | 0% | Not Started |  | 2026-02-04 | 2026-02-24 | 15d | 464
1.3.4.9.1.7.4 | 6 | Development |  |  | Assess Testers readiness for testing |  | 0% | Not Started |  | 2026-02-18 | 2026-02-24 | 5d | 468SS +10d
1.3.4.9.2 | 4 |  |  |  | Testing and UAT Activities |  | 0% |  |  | 2026-01-14 | 2026-05-19 | 90d
1.3.4.9.2.1 | 5 |  |  |  | Testing Stage: DCM Activities |  | 0% |  |  | 2026-01-14 | 2026-02-24 | 30d
1.3.4.9.2.1.1 | 6 | Development |  |  | Sample Data Collection (Master/Open Balance/Transactions) |  | 0% | Not Started |  | 2026-01-14 | 2026-02-10 | 20d | 463
1.3.4.9.2.1.2 | 6 | Development |  |  | Data Conversion and Cleansing |  | 0% | Not Started |  | 2026-01-28 | 2026-02-19 | 17d | 472SS +10d
1.3.4.9.2.1.3 | 6 | Development |  |  | Data Verification and Testing |  | 0% | Not Started |  | 2026-02-06 | 2026-02-19 | 10d | 473SS +7d
1.3.4.9.2.1.4 | 6 | Development |  |  | Data Migration to the Test Instance |  | 0% | Not Started |  | 2026-02-13 | 2026-02-24 | 8d | 474SS +5d
1.3.4.9.2.2 | 5 |  |  |  | Internal Testing Activities |  | 0% |  |  | 2026-02-04 | 2026-03-12 | 27d
1.3.4.9.2.2.1 | 6 | Development |  |  | Conduct Budget Preparation to Management process testing |  | 0% | Not Started |  | 2026-02-04 | 2026-02-12 | 7d | 464
1.3.4.9.2.2.2 | 6 | Development |  |  | Conduct Procure to Pay process testing |  | 0% | Not Started |  | 2026-02-04 | 2026-02-12 | 7d | 477SS
1.3.4.9.2.2.3 | 6 | Development |  |  | Conduct Receipt to Cash process testing |  | 0% | Not Started |  | 2026-02-04 | 2026-02-12 | 7d | 478SS
1.3.4.9.2.2.4 | 6 | Development |  |  | Conduct Cash Planning and Commitment process testing |  | 0% | Not Started |  | 2026-02-17 | 2026-02-25 | 7d | 479FS +2d
1.3.4.9.2.2.5 | 6 | Development |  |  | Conduct Asset Management testing |  | 0% | Not Started |  | 2026-02-17 | 2026-02-23 | 5d | 480SS
1.3.4.9.2.2.6 | 6 | Development |  |  | Conduct Local Debt Management process testing |  | 0% | Not Started |  | 2026-02-17 | 2026-02-23 | 5d | 481SS
1.3.4.9.2.2.7 | 6 | Development |  |  | Conduct Accounting to Reconciliation process testing |  | 0% | Not Started |  | 2026-02-24 | 2026-03-04 | 7d | 482
1.3.4.9.2.2.8 | 6 | Development |  |  | Compiling Internal Testing Issue Log |  | 0% | Not Started |  | 2026-02-17 | 2026-02-23 | 5d | 477FS +2d
1.3.4.9.2.2.9 | 6 | Development |  |  | Fixing of Issue Log |  | 0% | Not Started |  | 2026-02-17 | 2026-03-02 | 10d | 484SS
1.3.4.9.2.2.10 | 6 | Development |  |  | Prepare Internal Testing Result Report |  | 0% | Not Started |  | 2026-02-26 | 2026-03-05 | 6d | 483SS +2d
1.3.4.9.2.2.11 | 6 | Development |  |  | Internal Testing Result Report Review |  | 0% | Not Started |  | 2026-03-06 | 2026-03-12 | 5d | 486
1.3.4.9.2.3 | 5 |  |  |  | End to End System Testing |  | 0% |  |  | 2026-02-16 | 2026-03-19 | 24d
1.3.4.9.2.3.1 | 6 | Development |  |  | Identify participants for Ene to End Testing |  | 0% | Not Started |  | 2026-02-16 | 2026-02-20 | 5d | 483SS -6d
1.3.4.9.2.3.2 | 6 | Development |  |  | Plan End to End System Testing |  | 0% | Not Started |  | 2026-02-16 | 2026-02-20 | 5d | 489SS
1.3.4.9.2.3.3 | 6 | Development |  |  | Conducting E2E System Testing |  | 0% | Not Started |  | 2026-02-26 | 2026-03-06 | 7d | 490FS +3d
1.3.4.9.2.3.4 | 6 | Development |  |  | Prepare Testing Result Report |  | 0% | Not Started |  | 2026-03-09 | 2026-03-13 | 5d | 491
1.3.4.9.2.3.5 | 6 | Development |  |  | Review Testing Result Report |  | 0% | Not Started |  | 2026-03-16 | 2026-03-19 | 4d | 492
1.3.4.9.2.3.6 | 6 | Development |  |  | Test Result Report Sign Off |  | 0% | Not Started |  | 2026-03-19 | 2026-03-19 | 0 | 493
1.3.4.9.2.4 | 5 |  |  |  | User Acceptance Testing Activities |  | 0% |  |  | 2026-02-16 | 2026-05-19 | 67d
1.3.4.9.2.4.1 | 6 | Development |  |  | Prepare UAT Detail Plan |  | 0% | Not Started |  | 2026-02-16 | 2026-03-13 | 20d | 490SS
1.3.4.9.2.4.2 | 6 | Development |  |  | Perform UAT readiness activities |  | 0% | Not Started |  | 2026-03-09 | 2026-03-13 | 5d | 496FS -5d
1.3.4.9.2.4.3 | 6 | Development |  |  | Conduct Budget Preparation to Management process testing |  | 0% | Not Started |  | 2026-03-16 | 2026-04-03 | 15d | 497SS +5d
1.3.4.9.2.4.4 | 6 | Development |  |  | Conduct Procure to Pay process testing |  | 0% | Not Started |  | 2026-03-16 | 2026-04-03 | 15d | 498SS
1.3.4.9.2.4.5 | 6 | Development |  |  | Conduct Receipt to Cash process testing |  | 0% | Not Started |  | 2026-03-16 | 2026-03-27 | 10d | 498SS
1.3.4.9.2.4.6 | 6 | Development |  |  | Conduct Cash Planning and Commitment process testing |  | 0% | Not Started |  | 2026-04-06 | 2026-04-24 | 15d | 499
1.3.4.9.2.4.7 | 6 | Development |  |  | Conduct Asset Management testing |  | 0% | Not Started |  | 2026-04-06 | 2026-04-14 | 7d | 501SS
1.3.4.9.2.4.8 | 6 | Development |  |  | Conduct Local Debt Management process testing |  | 0% | Not Started |  | 2026-04-06 | 2026-04-14 | 7d | 501SS
1.3.4.9.2.4.9 | 6 | Development |  |  | Conduct Accounting to Reconciliation process testing |  | 0% | Not Started |  | 2026-04-06 | 2026-04-17 | 10d | 501SS
1.3.4.9.2.4.10 | 6 | Development |  |  | Compiling UAT Issue Log |  | 0% | Not Started |  | 2026-03-17 | 2026-04-20 | 25d | 498SS +1d
1.3.4.9.2.4.11 | 6 | Development |  |  | Fixing/Resolving UAT Issues |  | 0% | Not Started |  | 2026-03-17 | 2026-04-23 | 28d | 505SS
1.3.4.9.2.4.12 | 6 | Development |  |  | Prepare UAT Report by the Testers |  | 0% | Not Started |  | 2026-04-02 | 2026-04-29 | 20d | 500FS +3d
1.3.4.9.2.4.13 | 6 | Development |  |  | UAT Result Report Review |  | 0% | Not Started |  | 2026-04-30 | 2026-05-13 | 10d | 507
1.3.4.9.2.4.14 | 6 | Development |  |  | UAT Result Report Translation |  | 0% | Not Started |  | 2026-04-30 | 2026-05-06 | 5d | 508SS
1.3.4.9.2.4.15 | 6 | Development |  |  | Translated UAT Result Report Review |  | 0% | Not Started |  | 2026-05-07 | 2026-05-14 | 6d | 509
1.3.4.9.2.4.16 | 6 | Development |  |  | Submission of Final UAT Result Report |  | 0% | Not Started |  | 2026-05-15 | 2026-05-19 | 3d | 510
1.3.4.9.2.4.17 | 6 | Development |  |  | Sign Off UAT Certificate |  | 0% | Not Started |  | 2026-05-19 | 2026-05-19 | 0 | 511
1.3.4.10 | 4 |  |  |  | Pilot Phase Implementation |  | 0% |  |  | 2026-02-20 | 2026-12-29 | 223d
1.3.4.10.1 | 5 | Development |  |  | Detail Pilot Implementation Planning |  | 0% | Not Started |  | 2026-03-20 | 2026-03-26 | 5d | 494 |  |  | TBG
1.3.4.10.2 | 5 | Development |  |  | Location/Site Readiness Assessment |  | 0% | Not Started |  | 2026-03-25 | 2026-04-07 | 10d | 514FS -2d |  |  | PIU/TBG/LaoOdd
1.3.4.10.3 | 5 | Development |  |  | Provision of cloud service facility for Pilot including Cloud environment setup with High Availability and Disaster Recovery |  | 0% | Not Started |  | 2026-04-10 | 2026-04-16 | 5d | 514FS +10d |  |  | TBG
1.3.4.10.4 | 5 | Development |  |  | Configuration of Production Environment for Pilot sites |  | 0% | Not Started |  | 2026-04-10 | 2026-04-23 | 10d | 516FS -5d |  |  | TBG
1.3.4.10.5 | 5 |  |  |  | Data Collection and Migration Activities |  | 0% |  |  | 2026-03-25 | 2026-05-15 | 38d
1.3.4.10.5.1 | 6 | Development |  |  | Data Collection Template distribution and orientation |  | 0% | Not Started |  | 2026-03-25 | 2026-03-31 | 5d | 515SS |  |  | PIU/TBG/LaoOdd
1.3.4.10.5.2 | 6 | Development |  |  | Data Collection as per the Templates and Cleansing |  | 0% | Not Started |  | 2026-04-01 | 2026-04-28 | 20d | 519 |  |  | PIU/TBG/LaoOdd
1.3.4.10.5.3 | 6 | Development |  |  | Data Verification and Sign Off |  | 0% | Not Started |  | 2026-04-06 | 2026-05-01 | 20d | 520SS +3d |  |  | PIU
1.3.4.10.5.4 | 6 | Development |  |  | Data Migration to Production as of Cut-Off Date |  | 0% | Not Started |  | 2026-04-27 | 2026-05-15 | 15d | 521SS +15d |  |  | TBG
1.3.4.10.5.5 | 6 | Development |  |  | Data Migration of Master Data |  | 0% | Not Started |  | 2026-05-11 | 2026-05-11 | 0 | 522FS -4d |  |  | TBG
1.3.4.10.5.6 | 6 | Development |  |  | Data Migration of Cut-over data for pilot |  | 0% | Not Started |  | 2026-05-15 | 2026-05-15 | 0 | 522 |  |  | TBG
1.3.4.10.6 | 5 |  |  |  | Training and Change Management |  | 0% |  |  | 2026-02-20 | 2026-05-01 | 51d
1.3.4.10.6.1 | 6 | Development |  |  | Training Material Preparation |  | 0% | Not Started |  | 2026-02-20 | 2026-03-19 | 20d | 494FS -20d |  |  | LaoOddo
1.3.4.10.6.2 | 6 | Development |  |  | Change Management Program and Preparation |  | 0% | Not Started |  | 2026-03-25 | 2026-04-02 | 7d | 515SS |  |  | TBG/PIU
1.3.4.10.6.3 | 6 | Development |  |  | Conduct Change Management Activities |  | 0% | Not Started |  | 2026-04-03 | 2026-04-16 | 10d | 527 |  |  | TBG
1.3.4.10.6.4 | 6 | Development |  |  | Pilot Site Trainee Identification |  | 0% | Not Started |  | 2026-03-25 | 2026-04-07 | 10d | 515SS |  |  | PIU
1.3.4.10.6.5 | 6 | Development |  |  | Preparing Detail Training Program |  | 0% | Not Started |  | 2026-03-06 | 2026-03-19 | 10d | 526FS -10d |  |  | LaoOddo
1.3.4.10.6.6 | 6 | Development |  |  | Conducting Trainings |  | 0% | Not Started |  | 2026-04-01 | 2026-04-28 | 20d | 529SS +5d |  |  | LaoOddo
1.3.4.10.6.7 | 6 | Development |  |  | Completion of all Trainings and Change Management Activities |  | 0% | Not Started |  | 2026-05-01 | 2026-05-01 | 0 | 531FS +3d |  |  | PIU/TBG
1.3.4.10.7 | 5 | Development |  |  | Key Manager and HSM |  | 0% | Not Started |  | 2026-05-18 | 2026-06-01 | 11d | 524 |  |  | TBG
1.3.4.10.8 | 5 | Development |  |  | VAPT and NC Closure |  | 0% | Not Started |  | 2026-05-18 | 2026-06-16 | 22d | 524 |  |  | TBG
1.3.4.10.9 | 5 | Development |  |  | Third-Party Audit of the Solution |  | 0% | Not Started |  | 2026-05-18 | 2026-05-27 | 8d | 524 |  |  | TBG
1.3.4.10.10 | 5 |  |  |  | Pilot Phase Activities |  | 0% |  |  | 2026-11-02 | 2026-12-29 | 42d
1.3.4.10.10.1 | 6 | Development |  |  | Pilot Go Live |  | 0% | Not Started |  | 2026-11-02 | 2026-11-02 | 0 |  |  |  | TBG
1.3.4.10.10.2 | 6 | Development |  |  | Perform Pilot site level activities |  | 0% | Not Started |  | 2026-11-02 | 2026-12-25 | 40d | 537SS |  |  | TBG
1.3.4.10.10.3 | 6 | Development |  |  | Pilot Phase assessment and Completion Report Preparation |  | 0% | Not Started |  | 2026-12-07 | 2026-12-18 | 10d | 538FS -15d |  |  | TBG/LaoOdoo
1.3.4.10.10.4 | 6 | Development |  |  | Pilot Phase Completion Report Review |  | 0% | Not Started |  | 2026-12-21 | 2026-12-29 | 7d | 539 |  |  | TBG/LaoOdoo
1.3.4.10.10.5 | 6 | Development |  |  | Approval of Pilot Phase Completion Report |  | 0% | Not Started |  | 2026-12-29 | 2026-12-29 | 0 | 540 |  |  | PIU
| 2 |  |  |  | Implementation Phase |  | 0% |  |  | 2026-11-02 | 2027-08-30 | 216d
1.3.4.11 | 4 |  |  |  | Phase 1: Rollout Implementation |  | 0% |  |  | 2026-11-02 | 2027-02-25 | 84d
1.3.4.11.1 | 5 | Implementation |  |  | Lesson Learned and Improvement areas from Pilot Phase |  | 0% | Not Started |  | 2026-11-02 | 2026-11-06 | 5d |  |  |  | PIU/TBG/LaoOdd
1.3.4.11.2 | 5 | Implementation |  |  | Location/Site Readiness Assessment |  | 0% | Not Started |  | 2026-11-02 | 2026-11-13 | 10d | 544SS |  |  | PIU/TBG/LaoOdd
1.3.4.11.3 | 5 | Implementation |  |  | Data Collection Template distribution and orientation |  | 0% | Not Started |  | 2026-11-02 | 2026-11-13 | 10d | 545SS |  |  | PIU/TBG/LaoOdd
1.3.4.11.4 | 5 | Implementation |  |  | Provision of cloud services for Go-Live including Cloud environment setup with High Availability and Disaster Recovery |  | 0% | Not Started |  | 2026-11-09 | 2026-11-18 | 8d | 544 |  |  | TBG
1.3.4.11.5 | 5 | Implementation |  |  | Provisioning for Cloud facility for Roll-Out |  | 0% | Not Started |  | 2026-11-09 | 2026-12-02 | 18d | 547SS |  |  | TBG
1.3.4.11.6 | 5 | Implementation |  |  | Configuration of production environment for roll-out to phase 1 locations |  | 0% | Not Started |  | 2026-12-03 | 2026-12-23 | 15d | 548 |  |  | TBG
1.3.4.11.7 | 5 |  |  |  | Data Collection and Migration Activities |  | 0% |  |  | 2026-11-04 | 2026-12-29 | 40d
1.3.4.11.7.1 | 6 | Implementation |  |  | Data Collection as per the Templates and Cleansing |  | 0% | Not Started |  | 2026-11-04 | 2026-12-08 | 25d | 546SS +2d |  |  | PIU/TBG/LaoOdd
1.3.4.11.7.2 | 6 | Implementation |  |  | Data Verification and Sign Off |  | 0% | Not Started |  | 2026-11-09 | 2026-12-11 | 25d | 551SS +3d |  |  | PIU
1.3.4.11.7.3 | 6 | Implementation |  |  | Data Migration to Production as of Cut-Off Date |  | 0% | Not Started |  | 2026-12-14 | 2026-12-29 | 12d | 552 |  |  | TBG
1.3.4.11.8 | 5 |  |  |  | Training and Change Management |  | 0% |  |  | 2026-11-02 | 2026-12-29 | 42d
1.3.4.11.8.1 | 6 | Implementation |  |  | Change Management Program and Preparation |  | 0% | Not Started |  | 2026-11-02 | 2026-11-06 | 5d | 545SS
1.3.4.11.8.2 | 6 | Implementation |  |  | Conduct Change Management Activities |  | 0% | Not Started |  | 2026-11-09 | 2026-11-20 | 10d | 555
1.3.4.11.8.3 | 6 | Implementation |  |  | Phase 1 Site Trainee Identification |  | 0% | Not Started |  | 2026-11-02 | 2026-11-13 | 10d | 545SS |  |  | PIU
1.3.4.11.8.4 | 6 | Implementation |  |  | Preparing Detail Training Program |  | 0% | Not Started |  | 2026-11-04 | 2026-11-13 | 8d | 545SS +2d |  |  | TBG/LaoOdoo
1.3.4.11.8.5 | 6 | Implementation |  |  | Conducting Trainings |  | 0% | Not Started |  | 2026-11-16 | 2026-12-25 | 30d | 558 |  |  | LaoOddo
1.3.4.11.8.6 | 6 | Implementation |  |  | Completion of all Trainings and Change Management Activities |  | 0% | Not Started |  | 2026-12-29 | 2026-12-29 | 0 | 559FS +2d |  |  | TBG/LaoOdoo
1.3.4.11.9 | 5 | Implementation |  |  | Go Live Readiness Assessment and confirmation |  | 0% | Not Started |  | 2026-12-24 | 2026-12-30 | 5d | 559FS -2d |  |  | PIU/TBG
1.3.4.11.10 | 5 | Implementation |  |  | Site System Cutover and Ceasing Legacy System |  | 0% | Not Started |  | 2026-12-30 | 2026-12-30 | 1d | 561FS -1d |  |  | PIU
1.3.4.11.11 | 5 | Implementation |  |  | Issuance of Go Live Certificate |  | 0% | Not Started |  | 2026-12-31 | 2026-12-31 | 0 | 562FS +1d |  |  | PIU
1.3.4.11.12 | 5 | Implementation |  |  | Go-Live for phase 1 Locations |  | 0% | Not Started |  | 2027-01-01 | 2027-01-01 | 0 |  |  |  | PIU/TBG
1.3.4.11.13 | 5 | Implementation |  |  | Perform Phase 1 Rollout site level activities |  | 0% | Not Started |  | 2027-01-01 | 2027-02-25 | 40d | 564SS |  |  | TBG/LaoOdoo
1.3.4.11.14 | 5 | Implementation |  |  | Completion of Roll-out to phase 1 Locations |  | 0% | Not Started |  | 2027-02-25 | 2027-02-25 | 0 | 565 |  |  | PIU/TBG
1.3.4.12 | 4 |  |  |  | Phase 2: Rollout Implementation |  | 0% |  |  | 2027-02-01 | 2027-06-30 | 108d
1.3.4.12.1 | 5 | Implementation |  |  | Lesson Learned and Improvement areas from Phase 1 Rollout |  | 0% | Not Started |  | 2027-02-01 | 2027-02-05 | 5d |  |  |  | PIU/TBG/LaoOdd
1.3.4.12.2 | 5 | Implementation |  |  | Location/Site Readiness Assessment |  | 0% | Not Started |  | 2027-02-01 | 2027-02-12 | 10d | 568SS |  |  | PIU/TBG/LaoOdd
1.3.4.12.3 | 5 | Implementation |  |  | Data Collection Template distribution and orientation |  | 0% | Not Started |  | 2027-02-01 | 2027-02-12 | 10d | 568SS |  |  | PIU
1.3.4.12.4 | 5 | Implementation |  |  | Provision of cloud services for Go-Live including Cloud environment setup with High Availability and Disaster Recovery |  | 0% | Not Started |  | 2027-02-08 | 2027-02-17 | 8d | 568 |  |  | TBG
1.3.4.12.5 | 5 | Implementation |  |  | Provisioning for Cloud facility for Roll-Out |  | 0% | Not Started |  | 2027-02-08 | 2027-03-03 | 18d | 571SS |  |  | TBG
1.3.4.12.6 | 5 | Implementation |  |  | Configuration of production environment for roll-out to phase 2 locations |  | 0% | Not Started |  | 2027-03-04 | 2027-03-29 | 18d | 572 |  |  | TBG
1.3.4.12.7 | 5 | Implementation |  |  | Configuration/Customization/Development of Solution Proposed for IFMIS - Module 3 |  | 0% | Not Started |  | 2027-05-31 | 2027-06-30 | 23d | 621SS -23d |  |  | TBG
1.3.4.12.8 | 5 |  |  |  | Data Collection and Migration Activities |  | 0% |  |  | 2027-02-03 | 2027-03-30 | 40d
1.3.4.12.8.1 | 6 | Implementation |  |  | Data Collection as per the Templates and Cleansing |  | 0% | Not Started |  | 2027-02-03 | 2027-03-09 | 25d | 570SS +2d |  |  | PIU/TBG/LaoOdd
1.3.4.12.8.2 | 6 | Implementation |  |  | Data Verification and Sign Off |  | 0% | Not Started |  | 2027-02-08 | 2027-03-12 | 25d | 576SS +3d |  |  | PIU
1.3.4.12.8.3 | 6 | Implementation |  |  | Data Migration to Production as of Cut-Off Date |  | 0% | Not Started |  | 2027-03-15 | 2027-03-30 | 12d | 577 |  |  | TBG
1.3.4.12.9 | 5 |  |  |  | Training and Change Management |  | 0% |  |  | 2027-02-01 | 2027-03-29 | 41d
1.3.4.12.9.1 | 6 | Implementation |  |  | Change Management Program and Preparation |  | 0% | Not Started |  | 2027-02-01 | 2027-02-05 | 5d | 569SS |  |  | TBG/PIU
1.3.4.12.9.2 | 6 | Implementation |  |  | Conduct Change Management Activities |  | 0% | Not Started |  | 2027-02-08 | 2027-02-19 | 10d | 580 |  |  | TBG
1.3.4.12.9.3 | 6 | Implementation |  |  | Phase 2 Site Trainee Identification |  | 0% | Not Started |  | 2027-02-01 | 2027-02-12 | 10d | 569SS |  |  | PIU
1.3.4.12.9.4 | 6 | Implementation |  |  | Preparing Detail Training and Program |  | 0% | Not Started |  | 2027-02-03 | 2027-02-12 | 8d | 568SS +2d |  |  | TBG/LaoOdoo
1.3.4.12.9.5 | 6 | Implementation |  |  | Conducting Trainings |  | 0% | Not Started |  | 2027-02-15 | 2027-03-26 | 30d | 583 |  |  | LaoOddo
1.3.4.12.9.6 | 6 | Implementation |  |  | Completion of all Trainings and Change Management Activities |  | 0% | Not Started |  | 2027-03-29 | 2027-03-29 | 0 | 584FS +1d |  |  | PIU/TBG/LaoOdd
1.3.4.12.10 | 5 | Implementation |  |  | Go Live Readiness Assessment and confirmation |  | 0% | Not Started |  | 2027-03-24 | 2027-03-30 | 5d | 584FS -3d |  |  | PIU/TBG/LaoOdd
1.3.4.12.11 | 5 | Implementation |  |  | Site System Cutover and Ceasing Legacy System |  | 0% | Not Started |  | 2027-03-30 | 2027-03-30 | 1d | 586FS -1d |  |  | PIU
1.3.4.12.12 | 5 | Implementation |  |  | Issuance of Go Live Certificate |  | 0% | Not Started |  | 2027-04-01 | 2027-04-01 | 0 |  |  |  | PIU
1.3.4.12.13 | 5 | Implementation |  |  | Go-Live for phase 2 Locations |  | 0% | Not Started |  | 2027-04-01 | 2027-04-01 | 0 | 588SS |  |  | PIU/TBG
1.3.4.12.14 | 5 | Implementation |  |  | Perform Phase 2 Rollout site level activities |  | 0% | Not Started |  | 2027-04-01 | 2027-05-28 | 42d | 589SS |  |  | TBG/LaoOdoo
1.3.4.12.15 | 5 | Implementation |  |  | Completion of Roll-out to phase 2 Locations |  | 0% | Not Started |  | 2027-05-28 | 2027-05-28 | 0 | 590 |  |  | PIU/TBG/LaoOdd
1.3.4.13 | 4 |  |  |  | Module 3: Standalone System |  | 0% |  |  | 2027-03-01 | 2027-05-19 | 58d
1.3.4.13.1 | 5 | Development |  |  | Developing remote locations with poor connectivity |  | 0% | Not Started |  | 2027-03-01 | 2027-04-09 | 30d |  |  |  | TBG
1.3.4.13.2 | 5 | Development |  |  | Activities for remote system |  | 0% | Not Started |  | 2027-04-12 | 2027-05-14 | 25d | 593 |  |  | TBG
1.3.4.13.3 | 5 |  |  |  | Module 3: Standalone System Process Testing |  | 0% |  |  | 2027-04-12 | 2027-04-30 | 15d
1.3.4.13.3.1 | 6 | Development |  |  | Test case, Test Scenarion and Test Script Preparation |  | 0% | Not Started |  | 2027-04-12 | 2027-04-23 | 10d | 593 |  |  | TBG
1.3.4.13.3.2 | 6 | Development |  |  | Testing of the Standalone System Functionalities |  | 0% | Not Started |  | 2027-04-26 | 2027-04-30 | 5d | 596 |  |  | PIU-TBA
1.3.4.13.4 | 5 | Development |  |  | Preparation for UAT for Module 3 |  | 0% | Not Started |  | 2027-05-03 | 2027-05-07 | 5d | 597
1.3.4.13.5 | 5 | Development |  |  | UAT for Module 3 |  | 0% | Not Started |  | 2027-05-10 | 2027-05-19 | 8d | 598
1.3.4.14 | 4 |  |  |  | Phase 3: Rollout Implementation |  | 0% |  |  | 2027-05-03 | 2027-08-30 | 86d
1.3.4.14.1 | 5 | Implementation |  |  | Lesson Learned and Improvement areas from Phase 2 Rollout |  | 0% | Not Started |  | 2027-05-03 | 2027-05-07 | 5d |  |  |  | PIU/TBG
1.3.4.14.2 | 5 | Implementation |  |  | Location/Site Readiness Assessment |  | 0% | Not Started |  | 2027-05-03 | 2027-05-14 | 10d | 601SS |  |  | PIU/TBG
1.3.4.14.3 | 5 | Implementation |  |  | Data Collection Template distribution and orientation |  | 0% | Not Started |  | 2027-05-03 | 2027-05-14 | 10d | 601SS |  |  | PIU/TBG
1.3.4.14.4 | 5 | Implementation |  |  | Provision of cloud services for Go-Live including Cloud environment setup with High Availability and Disaster Recovery |  | 0% | Not Started |  | 2027-05-10 | 2027-05-19 | 8d | 601 |  |  | TBG
1.3.4.14.5 | 5 | Implementation |  |  | Provisioning for Cloud facility for Roll-Out |  | 0% | Not Started |  | 2027-05-10 | 2027-06-02 | 18d | 604SS |  |  | TBG
1.3.4.14.6 | 5 | Implementation |  |  | Configuration of production environment for roll-out to phase 3 locations |  | 0% | Not Started |  | 2027-06-03 | 2027-06-28 | 18d | 605 |  |  | TBG
1.3.4.14.7 | 5 |  |  |  | Data Collection and Migration Activities |  | 0% |  |  | 2027-05-05 | 2027-06-29 | 40d
1.3.4.14.7.1 | 6 | Implementation |  |  | Data Collection as per the Templates and Cleansing |  | 0% | Not Started |  | 2027-05-05 | 2027-06-08 | 25d | 603SS +2d |  |  | PIU/TBG/LaoOdd
1.3.4.14.7.2 | 6 | Implementation |  |  | Data Verification and Sign Off |  | 0% | Not Started |  | 2027-05-10 | 2027-06-11 | 25d | 608SS +3d |  |  | PIU
1.3.4.14.7.3 | 6 | Implementation |  |  | Data Migration to Production as of Cut-Off Date |  | 0% | Not Started |  | 2027-06-14 | 2027-06-29 | 12d | 609 |  |  | TBG
1.3.4.14.8 | 5 |  |  |  | Training and Change Management |  | 0% |  |  | 2027-05-03 | 2027-06-29 | 42d
1.3.4.14.8.1 | 6 | Implementation |  |  | Change Management Program and Preparation |  | 0% | Not Started |  | 2027-05-03 | 2027-05-07 | 5d | 601SS
1.3.4.14.8.2 | 6 | Implementation |  |  | Conduct Change Management Activities |  | 0% | Not Started |  | 2027-05-10 | 2027-05-21 | 10d | 612
1.3.4.14.8.3 | 6 | Implementation |  |  | Phase 3 Site Trainee Identification |  | 0% | Not Started |  | 2027-05-03 | 2027-05-14 | 10d | 601SS |  |  | PIU
1.3.4.14.8.4 | 6 | Implementation |  |  | Preparing Detail Training and Program |  | 0% | Not Started |  | 2027-05-05 | 2027-05-14 | 8d | 614SS +2d |  |  | TBG/LaoOdoo
1.3.4.14.8.5 | 6 | Implementation |  |  | Conducting Trainings |  | 0% | Not Started |  | 2027-05-19 | 2027-06-29 | 30d | 615FS +2d |  |  | LaoOddo
1.3.4.14.8.6 | 6 | Implementation |  |  | Completion of all Trainings and Change Management Activities |  | 0% | Not Started |  | 2027-06-29 | 2027-06-29 | 1d | 616FS -1d |  |  | TBG/LaoOdoo
1.3.4.14.9 | 5 | Implementation |  |  | Go Live Readiness Assessment and confirmation |  | 0% | Not Started |  | 2027-06-14 | 2027-06-18 | 5d | 610SS |  |  | TBG/LaoOdoo
1.3.4.14.10 | 5 | Implementation |  |  | Site System Cutover and Ceasing Legacy System |  | 0% | Not Started |  | 2027-06-29 | 2027-06-29 | 1d | 610FS -1d |  |  | PIU
1.3.4.14.11 | 5 | Implementation |  |  | Issuance of Go Live Certificate |  | 0% | Not Started |  | 2027-07-01 | 2027-07-01 | 0 |  |  |  | PIU
1.3.4.14.12 | 5 | Implementation |  |  | Go-Live for phase 3 Locations |  | 0% | Not Started |  | 2027-07-01 | 2027-07-01 | 0 | 620SS |  |  | PIU
1.3.4.14.13 | 5 | Implementation |  |  | Perform Phase 3 Rollout site level activities |  | 0% | Not Started |  | 2027-07-01 | 2027-08-30 | 43d | 621SS |  |  | TBG/LaoOdoo
1.3.4.14.14 | 5 | Implementation |  |  | Completion of Roll-out to phase 3 Locations |  | 0% | Not Started |  | 2027-08-30 | 2027-08-30 | 0 | 622 |  |  | PIU/TBG/LaoOdd
1.3.4.15 | 4 |  |  |  | Project Closure and Sign Off |  | 0% |  |  | 2027-07-01 | 2027-08-27 | 42d
1.3.4.15.1 | 5 | Post-Implementation |  |  | Finalizing Project Documentation and Handover |  | 0% | Not Started |  | 2027-07-01 | 2027-07-14 | 10d | 621 |  |  | TBG/LaoOdoo
1.3.4.15.2 | 5 | Post-Implementation |  |  | Open Issues Resolution and Finalization |  | 0% | Not Started |  | 2027-07-15 | 2027-07-23 | 7d | 625 |  |  | TBG/LaoOdoo
1.3.4.15.3 | 5 | Post-Implementation |  |  | Develop and Submit Project Final Completion Report |  | 0% | Not Started |  | 2027-07-26 | 2027-08-06 | 10d | 626 |  |  | TBG/LaoOdoo
1.3.4.15.4 | 5 | Post-Implementation |  |  | Review of Project Final Completion Report |  | 0% | Not Started |  | 2027-08-09 | 2027-08-13 | 5d | 627 |  |  | PIU
1.3.4.15.5 | 5 | Post-Implementation |  |  | Re-Work on the Customer Comments and Recommendations |  | 0% | Not Started |  | 2027-08-16 | 2027-08-20 | 5d | 628 |  |  | TBG/LaoOdoo
1.3.4.15.6 | 5 | Post-Implementation |  |  | Submit Final Project Completion Report |  | 0% | Not Started |  | 2027-08-23 | 2027-08-26 | 4d | 629 |  |  | TBG/LaoOdoo
1.3.4.15.7 | 5 | Post-Implementation |  |  | Experience Sharing and Lesson Learned Workshop |  | 0% | Not Started |  | 2027-08-27 | 2027-08-27 | 1d | 630 |  |  | PIU/TBG/LaoOd
1.3.4.15.8 | 5 | Post-Implementation |  |  | Project Final Acceptance Sign off |  | 0% | Not Started |  | 2027-08-27 | 2027-08-27 | 0 | 631 |  |  | PIU
| 2 |  |  |  | Post-Implementation Phase |  | 0% |  |  | 2027-01-01 | 2029-12-28 | 781d
1.3.4.16 | 3 |  |  |  | Post Go-Live Support |  | 0% |  |  | 2027-01-01 | 2029-12-28 | 781d
1.3.4.16.1 | 4 | Post-Implementation |  |  | Warranty Support Activities |  | 0% | Not Started |  | 2027-01-01 | 2029-12-28 | 781d | 564SS |  |  | TBG/LaoOdoo
1.3.4.16.2 | 4 | Post-Implementation |  |  | Operational and Maintenance Support Activities |  | 0% | Not Started |  | 2027-01-01 | 2029-12-28 | 781d | 564SS |  |  | TBG/LaoOdoo