## New Tasks (one Time)
S. No | Tasks | Subtasks | Estimated Completion Date | Status | No of taxpayer | Potential | Uplaoded on Feedback (Yes/No) | Comment | Incharge
1 | Analysis of Credit Notes issued by service sectors | - Identification of Taxpayers who are primarily dealing in Service Sector | 2026-06-10 | Done |  |  | NO |  | Jitendra P
2 | Analysis of Credit Notes issued by service sectors | - Identification of taxpayers who are frequently issuing credit notes to the recepient | 2026-06-10 | Done |  |  | NO |  | Jitendra P
3 | Place of supply of Car Rental Services | Detailed analysis of place of supply of car rental services | 2026-06-11 | Inprogress |  |  | NO | Connect with rajesh gadwal ji | Sanjay Giri
4 | Lessees RCM liability on royalty | - Integartion of Lessees with GSTN data based on GSTIN and PAN | 2026-06-12 | Done |  |  | NO | SHARED to ACCT_BIU | DP
5 | Lessees RCM liability on royalty | - Identification of RCM paid by Lessees | 2026-06-12 | Done |  |  | NO | SHARED to ACCT_BIU | DP
6 | Lessees RCM liability on royalty | - Calculation of estimated RCM liability to be paid by the Lessees based on royalty amount | 2026-06-12 | Done |  |  | NO | SHARED to ACCT_BIU | DP
7 | Lessees RCM liability on royalty | - Identification of lessees who were declared lesser RCM liability compared with their estimated RCM liability | 2026-06-12 | Done |  |  | NO | SHARED to ACCT_BIU | DP
8 | Lessees RCM liability on royalty | - Mapping these lessees with ERCC contractors along with information such as contract amount, royalty collected by ERCC | 2026-06-12 | Done |  |  | NO | SHARED to ACCT_BIU | DP
9 | Analysis GTA to GTA Supply | - Identification of GST Taxpayers dealing in SAC 996511 | 2026-06-12 | Done |  |  | NO | SHARED | DP, JP
10 | Analysis GTA to GTA Supply | - Taxpayers who are dealing more than 70% in SAC 996511 | 2026-06-12 | Done |  |  | NO | SHARED | DP, JP
11 | Analysis GTA to GTA Supply | - Analysis of R1 data of these taxpayers at invoice level | 2026-06-12 | Done |  |  | NO | SHARED | DP, JP
12 | Analysis GTA to GTA Supply | - Filter out the taxpayers who are deling more than 90% in 12% rate across the year | 2026-06-12 | Done |  |  | NO | SHARED | DP, JP
13 | Analysis GTA to GTA Supply | - Identifiy the taxpayers who are dealing in SAC 996601 | 2026-06-12 | Done |  |  | NO | SHARED | DP, JP
14 | Analysis GTA to GTA Supply | - Analysis of other suplly made by same taxpayers | 2026-06-12 | Done |  |  | NO | SHARED | DP, JP
15 | Analysis GTA to GTA Supply | - Analysis of exempted supply declared by the taxpayers | 2026-06-12 | Done |  |  | NO | SHARED | DP, JP
16 | Adhoc Request | Provide Individual taxpayer - Royalty collection and e-Ravnna data | 2026-06-12 | Done |  |  | NO | SHARED | DP
17 | Adhoc Request | PPT (Zonal Review Meeting : on 22th June) | 2026-06-15 | Inprogress |  |  | NO | Meeting date has been postponed | RK
18 | Audit Module | - Functional and Technical Requirement gathering | 2026-06-15 | Inprogress |  |  | NO |  | SG
19 | Adhoc Request | Action Plan PPT (CM & CS review update) | 2026-06-16 | Done |  |  | NO | SHARED | AJ
20 | Adhoc Request | Vidhan sabha Question response regarding IT company renenue number | 2026-06-16 | Done |  |  | NO | Mailed | DP
21 | Adhoc Request | Transaction of cancelled taxpayer with TDS dealer | 2026-06-16 | Done |  |  | NO | To be shared | JP
22 | Mining ERCC GST Liability | -Consolidated data recevied from Mining Department | 2026-06-17 | Done |  |  | NO |  | DP
23 | Mining ERCC GST Liability | - Verification of contracts with contract master | 2026-06-17 | Done |  |  | NO |  | DP
24 | Mining ERCC GST Liability | - Identification of leases mapped with ERCC | 2026-06-17 | Done |  |  | NO |  | DP
25 | Mining ERCC GST Liability | - Integration of ERCC with GST data based on GSTN or PAN | 2026-06-17 | Done |  |  | NO |  | DP
26 | Mining ERCC GST Liability | - Calculation of Royalty collected by ERCC during the period thorugh eRawanna | 2026-06-17 | Done |  |  | NO |  | DP
27 | Mining ERCC GST Liability | - Identification of ERCC contractors where royalty collected by ERCC is lesser than the actual contract amount during the period | 2026-06-17 | Done |  |  | NO |  | DP
28 | GST 2.0 Impact analysis | Usecase developer for taxpayer who are paying @12 % instead of 18%, | 2026-06-18 | Done |  |  | NO |  | LP
29 | Vahan integration with GST | - Analysis of vehicle registered or selled in last 3 years | 2026-06-25 | Inprogress |  |  | NO | API not provided by Transport, Sample data for 1 month of 1 RTO provided on 19 June, without PAN no. | DP
30 | Vahan integration with GST | - Identification of different categories of Vehicles based on their tax rate | 2026-06-25 | Inprogress |  |  | NO | API not provided by Transport, Sample data for 1 month of 1 RTO provided on 19 June, without PAN no. | DP
31 | Vahan integration with GST | - Estimation of vehicles selled by the dealer in different tax rate | 2026-06-25 | Inprogress |  |  | NO | API not provided by Transport, Sample data for 1 month of 1 RTO provided on 19 June, without PAN no. | DP
32 | Vahan integration with GST | - Vehicle dealer integration with GSTN data | 2026-06-25 | Inprogress |  |  | NO | API not provided by Transport, Sample data for 1 month of 1 RTO provided on 19 June, without PAN no. | DP
33 | Vahan integration with GST | - Analysis of GST liability declared by the dealers | 2026-06-25 | Inprogress |  |  | NO | API not provided by Transport, Sample data for 1 month of 1 RTO provided on 19 June, without PAN no. | DP
34 | Vahan integration with GST | - Identification of dealers where mismatch in liability will be found | 2026-06-25 | Inprogress |  |  | NO | API not provided by Transport, Sample data for 1 month of 1 RTO provided on 19 June, without PAN no. | DP
35 | Secondment related cases | - Analysis of registration data to find out Directos, Board of Director or any executive director of the firm | 2026-06-19 | Done |  |  | NO | Jitendra, upload in GDRIVE (RJ CTD) | JP
36 | Secondment related cases | - Identification of cases where directors, board of directors or any executive director are from foreign nation and providing their services in the State | 2026-06-19 | Done |  |  | NO | Jitendra, upload in GDRIVE (RJ CTD) | JP
37 | Adhoc Request | Raise ticket to IT cell (Rajesh L) for Whitelisting of SAS Server (db ctd_gst, user: GST_READ) | 2026-06-19 | Done |  |  | NO |  | JP
38 | Analysis of Road Cutting Data | - Analysis of GST liability though road cutting contract or permit fee | 2026-06-20 | Inprogress |  |  | NO |  | Palash
39 | TDS and GSTR1 analysis | Estimated liability derived from TDS dedcution and GSTR1 against government invoices | 2026-06-22 | Inprogress |  |  | NO |  | JP
40 | Adhoc Request | Analysis of Workorder report from JDA | 2026-06-22 | Inprogress |  |  | NO |  | JP/LP
41 | RCM Liability on permit fee | - Identification of premit fee deposited by the dealer against STP in mining department | 2026-06-24 |  |  |  | NO |  | DP
42 | RCM Liability on permit fee | - Estimation of RCM liability on permit fee against each dealer | 2026-06-24 |  |  |  | NO |  | DP
43 | RCM Liability on permit fee | - Identification of dealers who were declared lesser RCM compared with their estimated RCM liability | 2026-06-24 |  |  |  | NO |  | DP
44 | Analysis of inward eway bills | - Analysis of inward ewaybills with "no supply" from same PAN | 2026-06-24 |  |  |  | NO |  | JP/LP
45 | Adhoc Request | GSTR1 HSN Summary Mismatch Correction (FY25-26): Jitu | 2026-06-25 | Inprogress |  |  | NO |  | JP/LP
46 | Misclassification of product | - Analysis of taxpayers supplying to Vehicle Industry on HSN chapter 84 or 85 instead of 87 prior to 22nd Sep'25 | 2026-06-25 |  |  |  | NO |  | LP
47 | Interest liability due to delay in issuance of Credit and Debit note | - Calculation of liability due to delay in issuance of Credit and Debit note | 2026-06-29 |  |  |  | NO |  | JP
48 | Other Ad-hoc Tasks | Such as validation of Red Flag matrics report, Data requirement by different sections, CS presentation etc. | 2026-06-30 |  |  |  | NO |  | SL/RK
49 | Risk Profiling | Risk profiling of each taxpayers based on risk scores generated through multiple parameters | 2026-07-15 |  |  |  | NO |  | YK/DP/AJ
50 | Standardise P&L statements | Standardise P&L statements | 2026-07-15 |  |  |  | NO |  | YK/AJ
51 | VAT Development functional and Testing support | - Functional and Technical Requirement gathering |  |  |  |  | NO |  | MC
52 | VAT Development functional and Testing support | - Explain the requirement to technical team |  |  |  |  | NO |  | MC
53 | VAT Development functional and Testing support | - Review of different forms |  |  |  |  | NO |  | MC
54 | VAT Development functional and Testing support | - Preparing Functional Requirement document for the team |  |  |  |  | NO |  | MC
55 | VAT Development functional and Testing support | - Testing and bug identification |  |  |  |  | NO |  | MC
56 | VAT Development functional and Testing support | - Communicating the status of development to VAT committee and other stakeholders |  |  |  |  | NO |  | MC
57 | VAT Development functional and Testing support | - Preparing MoM of all the meetings |  |  |  |  | NO |  | MC
58 | Audit Module | - Explain the requirements to technical team |  |  |  |  | NO |  | SG/AJ
59 | Audit Module | Development of prototype and discussions with BA Officers |  |  |  |  | NO |  | SG/AJ
60 | Audit Module | - Preparing Functional Requirement document for the team |  |  |  |  | NO |  | SG/AJ
61 | Audit Module | - Testing and bug identification |  |  |  |  | NO |  | SG/AJ
62 | Adhoc Request | IFMS Integration |  | Blocked |  |  | NO | IFMS has not yet shared the API's. | JP

## Monthly Tasks (Updation)
S. No | Tasks | Subtasks | Estimated Completion Date
1 | Sector Analysis (Commodity Level) | - Identification of top 100 taxpayers basis GTO for every circle basis FY 2025-26 upto the month | 2026-06-19
- Extraction of GSTR 1 of FY 2025-26 these taxpayers
- Identification of primary commodities of taxpayer based on HSN code mentioned by the taxpayers in GSTR 1
2 | Monthly Report 2b Vs 3B | - Analysis of 2b data for each taxpayers | 2026-06-23
- Analysis of ITC declared in 3B by the taxpayers
- Identify the taxpayers who are declaring more ITC in 3B compared with their 2B
- Development of multidimensional report to share this information with field formation
- Providing access to the field officers
3 | Non filer dashboard | Monthly Updation of Dashboard | Daily update after 21st of every month
4 | Sector Analysis (Top 1 Lakh) |  | Daily update after 21st of every month
5 | Zonal Performance |  | Between 5 to 7 of every month
6 | Sector Outliers |  | Between 5 to 7 of every month
1 | Performance Report from Feedback Portal |  | Daily update after 21st of every month
8 | Adjudiction done during the month |  | Between 5 to 7 of every month
9 | SCN Issued during the month |  | Between 5 to 7 of every month
10 | Recovery Pendency Report |  | Between 5 to 7 of every month
11 | Appeal Dashboard |  | Between 5 to 7 of every month
12 | Revenue Dashboard |  | Between 5 to 7 of every month
13 | Zonal Profile Dashboard |  | Between 5 to 7 of every month

## Monthly Compliance
S. No | Tasks | Subtasks | Estimated Completion Date
1 | Review Meeting Presentation or any other meetings | - Finaliztion of meeting template | As and when required
- Gathering data from different sections
- Consolidate all the information in proper format
- Present the presentation for review to all the stakeholders
2 | IGST Reversal Potential Cases | - Cases where ITC reflected in 2B is sigincantly higher than 3B | 2026-06-17
- Taxpayers having high balance in reclaim ledger
- Taxpayer dealing in exempted supply, but reversing any amount
- Taxpayers having high IGST RCM balance in ledger but not reversing the same
3 | A, B and C Pattern list | -A, B, C component wise detailed analysis report of taxpyers | 2026-06-18
4 | Compliance Report | Non Filer from top 1 Lakh taxpayers | 2026-06-21
5 | Updation of list uploaded in Feedback portal | Updation of list uploaded in Feedback portal | 1st of every month